## Read Me
Urban Integrated Municipal ERP: GWMC project plan
Hake Technologies ¦ Version 0.1 draft ¦ 23 October 2026 ¦ Based on product SRS v0.35 and Technical Architecture v0.1
What is in this workbook
Assumptions: project start date, contingency, holidays and optional day rates. Yellow cells are yours to change; everything else recalculates.
Project Plan: phases, tasks and subtasks with start offset, duration, dates, predecessors, effort in person-days by team role, and a monthly Gantt.
Team Summary: effort by phase and by module for each team role, with contingency and optional cost.
Resource Loading: full-time staff needed per role per month, from the Gantt allocation.
Milestones: phase go-lives and sign-offs with dates.
Planner Import: one row per subtask (title, bucket, start, due, label, effort, notes) for Microsoft Planner in Teams.
MS Project Import: ID, name, outline level, duration, start, finish, predecessors and work, for the Microsoft Project import wizard.
Risks: top delivery risks with owners and mitigations.
How to edit
Blue text = estimates and inputs you can change (start offset, duration, person-days, predecessors). Black = formulas. Yellow fill = key assumptions.
Only Subtask rows hold estimates; Task and Phase rows add up their subtasks. Milestones have duration 0.
Example: to move the start of a subtask by two weeks, add 10 to its 'Start offset (wd)'. Dates, Gantt and resource loading update automatically.
Importing into Microsoft Teams
Option A, Planner (Teams Planner tab): copy the Planner Import sheet into a new workbook and save it to OneDrive or SharePoint. Then use a Power Automate flow ('List rows present in a table', then 'Create a task') to create the tasks, mapping Bucket, Title, Start and Due. Add the plan to your Teams channel as a Planner tab.
Option B, Microsoft Project or Planner premium: in Project desktop choose File > Open, pick this workbook and follow the Import Wizard. Map Name, Outline Level, Duration, Start, Finish, Predecessors and Work from the MS Project Import sheet. Publish to Project for the web or Planner premium and add it to Teams.
Import wizards read the saved values. After changing estimates, save the workbook in Excel before importing.
How the estimates were made
Module effort = base person-days per activity x a size factor of (processes + requirements) / 40, kept between 0.6 and 1.8, using the counts in SRS v0.35. Interface effort = 1.5 person-days per I-xx link; adapter effort = 5 person-days per external system first owned by the module.
Field-app, citizen-service, GIS and migration activities are included only for modules that need them. Platform, release, governance and infrastructure tasks are estimated directly.
These are planning estimates for a first plan. Refine them with the module teams after the Phase 1 design workshops.

## Assumptions
Assumptions and inputs
Item |  | Value | Note | Holidays (enter GWMC / Telangana holidays)
Project start date (Monday) |  | 2026-11-02 | Assumed; set to the agreed start
Contingency on effort |  | 15% | Assumed 15% for estimation uncertainty
Working hours per person-day |  | 8 | Standard day
Currency for optional costing |  | INR | Day rates below are optional
Team roles and optional day rates
Code | Role | Day rate (optional)
PM | Project manager | 0
BA | Business analyst | 0
ARC | Solution / technical architect | 0
BE | Backend developer | 0
FE | Frontend developer | 0
MOB | Mobile developer | 0
GIS | GIS engineer | 0
DEV | DevOps / infrastructure | 0
QA | QA / test engineer | 0
DATA | Data migration engineer | 0
TRN | Trainer / change manager | 0
Note on C12: Leave 0 to plan effort only, or enter your day rates per role to see cost in Team Summary.
Note on F4: Add holiday dates in F4:F44. WORKDAY and NETWORKDAYS in the plan skip them.

## Project Plan
Project plan: Urban ERP for GWMC (all phases)
Blue = editable estimates. Dates use working days from the start date and holidays on the Assumptions sheet. Gantt cells show the share of each subtask falling in that month.
Gantt (share of subtask effort per month)
ID | WBS | Level | Type | Task / subtask | Phase | Module | Lead team | Start offset (wd) | Duration (wd) | Start | Finish | Predecessors (ID) | PM | BA | ARC | BE | FE | MOB | GIS | DEV | QA | DATA | TRN | Total effort (pd) | Effort + contingency (pd) | Deliverable / reference | Status | Owner | % complete | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01
1 | 1 | 1 | Phase | Programme management and governance | All |  |  |  | 440 | 2026-11-02 | 2028-07-07 |  | 345 | 30 | 89 | 30 | 0 | 0 | 0 | 15 | 8 | 0 | 10 | 527 | 606.05 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 1.1 | 2 | Task | Project governance and PMO | All |  |  |  | 440 | 2026-11-02 | 2028-07-07 |  | 313 | 10 | 71 | 30 | 0 | 0 | 0 | 15 | 0 | 0 | 10 | 449 | 516.35 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 1.1.1 | 3 | Subtask | PMO, planning, status reporting and steering committee: Phase 1 | All |  | PM | 0 | 140 | 2026-11-02 | 2027-05-14 |  | 70 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 96.6 | Weekly status, monthly steering minutes, RAID log | Not started |  | 0% | 0.15 | 0.16429 | 0.15 | 0.14286 | 0.16429 | 0.15714 | 0.071429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 1.1.2 | 3 | Subtask | PMO, planning, status reporting and steering committee: Phase 2 | All |  | PM | 88 | 141 | 2027-03-04 | 2027-09-16 |  | 71 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 97.75 | Weekly status, monthly steering minutes, RAID log | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.14184 | 0.15603 | 0.14894 | 0.15603 | 0.15603 | 0.15603 | 0.085106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 1.1.3 | 3 | Subtask | PMO, planning, status reporting and steering committee: Phase 3 | All |  | PM | 176 | 141 | 2027-07-06 | 2028-01-18 |  | 71 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 97.75 | Weekly status, monthly steering minutes, RAID log | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13475 | 0.15603 | 0.15603 | 0.14894 | 0.15603 | 0.16312 | 0.085106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 1.1.4 | 3 | Subtask | PMO, planning, status reporting and steering committee: Phase 4 | All |  | PM | 264 | 141 | 2027-11-05 | 2028-05-19 |  | 71 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 97.75 | Weekly status, monthly steering minutes, RAID log | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12766 | 0.16312 | 0.14894 | 0.14894 | 0.16312 | 0.14184 | 0.10638 | 0 | 0 | 0 | 0 | 0
7 | 1.1.5 | 3 | Subtask | Final stabilisation, knowledge transfer and handover | All |  | PM | 400 | 40 | 2028-05-15 | 2028-07-07 |  | 30 | 10 | 15 | 30 | 0 | 0 | 0 | 15 | 0 | 0 | 10 | 110 | 126.5 | Handover pack, runbooks, KT sign-off | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.325 | 0.55 | 0.125 | 0 | 0 | 0
8 | 1.2 | 2 | Task | Change control and quality | All |  |  |  | 400 | 2026-11-30 | 2028-06-09 |  | 32 | 20 | 18 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 78 | 89.7 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 1.2.1 | 3 | Subtask | Change request process and impact assessments (whole programme) | All |  | PM | 20 | 400 | 2026-11-30 | 2028-06-09 |  | 20 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 57.5 | CR register | Not started |  | 0% | 0.0025 | 0.0575 | 0.0525 | 0.05 | 0.0575 | 0.055 | 0.0525 | 0.055 | 0.055 | 0.055 | 0.055 | 0.0525 | 0.055 | 0.0575 | 0.0525 | 0.0525 | 0.0575 | 0.05 | 0.0575 | 0.0175 | 0 | 0 | 0 | 0
10 | 1.2.2 | 3 | Subtask | Quality audits and phase-gate reviews (4 gates) | All |  | PM | 100 | 300 | 2027-03-22 | 2028-05-12 |  | 12 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 28 | 32.2 | Gate review reports | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.026667 | 0.073333 | 0.07 | 0.073333 | 0.073333 | 0.073333 | 0.073333 | 0.07 | 0.073333 | 0.076667 | 0.07 | 0.07 | 0.076667 | 0.066667 | 0.033333 | 0 | 0 | 0 | 0 | 0
11 | 2 | 1 | Phase | Phase 0: Inception and mobilisation | Phase 0 |  |  |  | 26 | 2026-11-02 | 2026-12-07 |  | 18 | 50 | 30 | 3 | 15 | 0 | 0 | 34 | 0 | 10 | 0 | 160 | 184 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 2.1 | 2 | Task | Mobilisation | Phase 0 |  |  |  | 25 | 2026-11-02 | 2026-12-04 |  | 11 | 5 | 11 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 58 | 66.7 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 2.1.1 | 3 | Subtask | Kick-off with GWMC and team onboarding | Phase 0 |  | PM | 0 | 5 | 2026-11-02 | 2026-11-06 |  | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 14.95 | Kick-off deck, project charter | Not started |  | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 2.1.2 | 3 | Subtask | Tooling: repositories, CI/CD, tracker, Teams workspace | Phase 0 |  | DEV | 0 | 10 | 2026-11-02 | 2026-11-13 |  | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 15 | 17.25 | Working toolchain | Not started |  | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 2.1.3 | 3 | Subtask | Dev and test environments provisioned | Phase 0 |  | DEV | 3 | 15 | 2026-11-05 | 2026-11-25 |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 18 | 20.7 | Dev and test clusters | Not started |  | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 2.1.4 | 3 | Subtask | State Data Centre slot request and network approvals | Phase 0 |  | PM | 0 | 25 | 2026-11-02 | 2026-12-04 |  | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 12 | 13.8 | SDC allocation letter | Not started |  | 0% | 0.84 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 2.2 | 2 | Task | Requirements and design baseline | Phase 0 |  |  |  | 20 | 2026-11-09 | 2026-12-04 |  | 7 | 45 | 19 | 3 | 15 | 0 | 0 | 3 | 0 | 10 | 0 | 102 | 117.3 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 2.2.1 | 3 | Subtask | SRS walkthroughs with GWMC departments (Phase 1 modules) | Phase 0 |  | BA | 5 | 15 | 2026-11-09 | 2026-11-27 | 13 | 4 | 25 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 39.1 | Workshop minutes, clarifications | Not started |  | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 2.2.2 | 3 | Subtask | GWMC Deployment SRS open items closed for Phase 1 | Phase 0 |  | BA | 10 | 15 | 2026-11-16 | 2026-12-04 |  | 3 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 17.25 | Signed open-items list | Not started |  | 0% | 0.73333 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 2.2.3 | 3 | Subtask | Architecture decisions (ADR-001 to 016) reviewed and signed off | Phase 0 |  | ARC | 5 | 15 | 2026-11-09 | 2026-11-27 |  | 0 | 0 | 12 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 18 | 20.7 | Signed ADRs | Not started |  | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 2.2.4 | 3 | Subtask | UX research, design system and accessibility baseline | Phase 0 |  | FE | 5 | 20 | 2026-11-09 | 2026-12-04 |  | 0 | 4 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 21.85 | Design system, UI kit, GIGW checklist | Not started |  | 0% | 0.8 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 2.2.5 | 3 | Subtask | Data migration strategy and legacy data assessment | Phase 0 |  | DATA | 10 | 15 | 2026-11-16 | 2026-12-04 |  | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 16 | 18.4 | Migration strategy | Not started |  | 0% | 0.73333 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 2.3 | 2 | Milestone | M0: Inception complete, Phase 1 build starts | Phase 0 |  |  | 25 | 0 | 2026-12-07 | 2026-12-07 | 18,20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 3 | 1 | Phase | Platform foundation (built in Phase 1) | Phase 1 |  |  |  | 84 | 2026-11-16 | 2027-03-11 |  | 0 | 15 | 56 | 320 | 97 | 49 | 32 | 95 | 112 | 9 | 0 | 785 | 902.75 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 3.1 | 2 | Task | Identity, OTP, CAPTCHA and step-up (Keycloak) | Phase 1 | Platform |  |  | 51 | 2026-11-16 | 2027-01-25 |  | 0 | 0 | 4 | 33 | 7 | 0 | 0 | 4 | 10 | 0 | 0 | 58 | 66.7 | PLT-FR-001, 026, 028 to 032 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 3.1.1 | 3 | Subtask | Detailed design and contracts | Phase 1 | Platform | ARC | 10 | 10 | 2026-11-16 | 2026-11-27 | 20 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8.05 | Design note, OpenAPI and event schemas | Not started |  | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 3.1.2 | 3 | Subtask | Build and unit tests | Phase 1 | Platform | BE | 20 | 30 | 2026-11-30 | 2027-01-08 |  | 0 | 0 | 0 | 27 | 7 | 0 | 0 | 4 | 0 | 0 | 0 | 38 | 43.7 | Working service | Not started |  | 0% | 0.033333 | 0.76667 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 3.1.3 | 3 | Subtask | Component, security and contract tests | Phase 1 | Platform | QA | 48 | 13 | 2027-01-07 | 2027-01-25 |  | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 13 | 14.95 | Test report | Not started |  | 0% | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 3.2 | 2 | Task | Tenant, configuration console and Telangana state pack | Phase 1 | Platform |  |  | 50 | 2026-11-24 | 2027-02-01 |  | 0 | 7 | 3 | 26 | 14 | 0 | 0 | 0 | 8 | 0 | 0 | 58 | 66.7 | PLT-FR-015 to 018, 022 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 3.2.1 | 3 | Subtask | Detailed design and contracts | Phase 1 | Platform | ARC | 16 | 10 | 2026-11-24 | 2026-12-07 | 20 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5.75 | Design note, OpenAPI and event schemas | Not started |  | 0% | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 3.2.2 | 3 | Subtask | Build and unit tests | Phase 1 | Platform | BE | 26 | 30 | 2026-12-08 | 2027-01-18 |  | 0 | 7 | 0 | 22 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 49.45 | Working service | Not started |  | 0% | 0 | 0.6 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 3.2.3 | 3 | Subtask | Component, security and contract tests | Phase 1 | Platform | QA | 53 | 13 | 2027-01-14 | 2027-02-01 |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 10 | 11.5 | Test report | Not started |  | 0% | 0 | 0 | 0.92308 | 0.076923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 3.3 | 2 | Task | Workflow and rules engine (Flowable BPMN and DMN) | Phase 1 | Platform |  |  | 50 | 2026-11-24 | 2027-02-01 |  | 0 | 0 | 4 | 31 | 9 | 0 | 0 | 0 | 8 | 0 | 0 | 52 | 59.8 | PLT-FR-003, 004 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 3.3.1 | 3 | Subtask | Detailed design and contracts | Phase 1 | Platform | ARC | 16 | 10 | 2026-11-24 | 2026-12-07 | 20 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8.05 | Design note, OpenAPI and event schemas | Not started |  | 0% | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 3.3.2 | 3 | Subtask | Build and unit tests | Phase 1 | Platform | BE | 26 | 30 | 2026-12-08 | 2027-01-18 |  | 0 | 0 | 0 | 25 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 39.1 | Working service | Not started |  | 0% | 0 | 0.6 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 3.3.3 | 3 | Subtask | Component, security and contract tests | Phase 1 | Platform | QA | 53 | 13 | 2027-01-14 | 2027-02-01 |  | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 11 | 12.65 | Test report | Not started |  | 0% | 0 | 0 | 0.92308 | 0.076923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 3.4 | 2 | Task | API gateway, BFFs and service mesh | Phase 1 | Platform |  |  | 39 | 2026-11-16 | 2027-01-07 |  | 0 | 0 | 3 | 18 | 0 | 0 | 0 | 9 | 4 | 0 | 0 | 34 | 39.1 | PLT-FR-010 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 3.4.1 | 3 | Subtask | Detailed design and contracts | Phase 1 | Platform | ARC | 10 | 8 | 2026-11-16 | 2026-11-25 | 20 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5.75 | Design note, OpenAPI and event schemas | Not started |  | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 3.4.2 | 3 | Subtask | Build and unit tests | Phase 1 | Platform | BE | 18 | 24 | 2026-11-26 | 2026-12-29 |  | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 23 | 26.45 | Working service | Not started |  | 0% | 0.125 | 0.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 3.4.3 | 3 | Subtask | Component, security and contract tests | Phase 1 | Platform | QA | 39 | 10 | 2026-12-25 | 2027-01-07 |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 6 | 6.9 | Test report | Not started |  | 0% | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 3.5 | 2 | Task | Event bus, outbox/inbox library and schema registry | Phase 1 | Platform |  |  | 39 | 2026-11-16 | 2027-01-07 |  | 0 | 0 | 4 | 20 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 34 | 39.1 | NFR-003 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 3.5.1 | 3 | Subtask | Detailed design and contracts | Phase 1 | Platform | ARC | 10 | 8 | 2026-11-16 | 2026-11-25 | 20 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6.9 | Design note, OpenAPI and event schemas | Not started |  | 0% | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 3.5.2 | 3 | Subtask | Build and unit tests | Phase 1 | Platform | BE | 18 | 24 | 2026-11-26 | 2026-12-29 |  | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 21 | 24.15 | Working service | Not started |  | 0% | 0.125 | 0.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 3.5.3 | 3 | Subtask | Component, security and contract tests | Phase 1 | Platform | QA | 39 | 10 | 2026-12-25 | 2027-01-07 |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 7 | 8.05 | Test report | Not started |  | 0% | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 3.6 | 2 | Task | Payment service, gateway, UPI and BBPS | Phase 1 | Platform |  |  | 44 | 2026-12-09 | 2027-02-08 |  | 0 | 0 | 2 | 33 | 5 | 0 | 0 | 0 | 10 | 0 | 0 | 50 | 57.5 | PLT-FR-008 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 3.6.1 | 3 | Subtask | Detailed design and contracts | Phase 1 | Platform | ARC | 27 | 9 | 2026-12-09 | 2026-12-21 | 20 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5.75 | Design note, OpenAPI and event schemas | Not started |  | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 3.6.2 | 3 | Subtask | Build and unit tests | Phase 1 | Platform | BE | 36 | 27 | 2026-12-22 | 2027-01-27 |  | 0 | 0 | 0 | 27 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 36.8 | Working service | Not started |  | 0% | 0 | 0.2963 | 0.7037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 3.6.3 | 3 | Subtask | Component, security and contract tests | Phase 1 | Platform | QA | 60 | 11 | 2027-01-25 | 2027-02-08 |  | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 13 | 14.95 | Test report | Not started |  | 0% | 0 | 0 | 0.45455 | 0.54545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 3.7 | 2 | Task | Notification service (DLT SMS, WhatsApp, email, IVRS) | Phase 1 | Platform |  |  | 39 | 2026-12-09 | 2027-02-01 |  | 0 | 4 | 2 | 20 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 32 | 36.8 | PLT-FR-007 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 3.7.1 | 3 | Subtask | Detailed design and contracts | Phase 1 | Platform | ARC | 27 | 8 | 2026-12-09 | 2026-12-18 | 20 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4.6 | Design note, OpenAPI and event schemas | Not started |  | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 3.7.2 | 3 | Subtask | Build and unit tests | Phase 1 | Platform | BE | 35 | 24 | 2026-12-21 | 2027-01-21 |  | 0 | 4 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 23 | Working service | Not started |  | 0% | 0 | 0.375 | 0.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 3.7.3 | 3 | Subtask | Component, security and contract tests | Phase 1 | Platform | QA | 56 | 10 | 2027-01-19 | 2027-02-01 |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 8 | 9.2 | Test report | Not started |  | 0% | 0 | 0 | 0.9 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 3.8 | 2 | Task | GIS base: PostGIS, GeoServer, base map, imagery, ward layers | Phase 1 | Platform |  |  | 56 | 2026-11-24 | 2027-02-09 |  | 0 | 0 | 2 | 9 | 9 | 0 | 32 | 0 | 5 | 0 | 0 | 57 | 65.55 | PLT-FR-005, I-20 interim |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 3.8.1 | 3 | Subtask | Detailed design and contracts | Phase 1 | Platform | ARC | 16 | 11 | 2026-11-24 | 2026-12-08 | 20 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3.45 | Design note, OpenAPI and event schemas | Not started |  | 0% | 0.45455 | 0.54545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 3.8.2 | 3 | Subtask | Build and unit tests | Phase 1 | Platform | GIS | 27 | 34 | 2026-12-09 | 2027-01-25 |  | 0 | 0 | 0 | 7 | 9 | 0 | 32 | 0 | 0 | 0 | 0 | 48 | 55.2 | Working service | Not started |  | 0% | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 3.8.3 | 3 | Subtask | Component, security and contract tests | Phase 1 | Platform | QA | 58 | 14 | 2027-01-21 | 2027-02-09 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 6 | 6.9 | Test report | Not started |  | 0% | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 3.9 | 2 | Task | Document pipeline: OCR, translation, eSign, anchoring, DigiLocker | Phase 1 | Platform |  |  | 56 | 2026-12-01 | 2027-02-16 |  | 0 | 0 | 4 | 40 | 0 | 0 | 0 | 4 | 10 | 0 | 0 | 58 | 66.7 | PLT-FR-006, 025 to 027 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 3.9.1 | 3 | Subtask | Detailed design and contracts | Phase 1 | Platform | ARC | 21 | 11 | 2026-12-01 | 2026-12-15 | 20 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9.2 | Design note, OpenAPI and event schemas | Not started |  | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 3.9.2 | 3 | Subtask | Build and unit tests | Phase 1 | Platform | BE | 32 | 34 | 2026-12-16 | 2027-02-01 |  | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 36 | 41.4 | Working service | Not started |  | 0% | 0 | 0.35294 | 0.61765 | 0.029412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 3.9.3 | 3 | Subtask | Component, security and contract tests | Phase 1 | Platform | QA | 63 | 14 | 2027-01-28 | 2027-02-16 |  | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 14 | 16.1 | Test report | Not started |  | 0% | 0 | 0 | 0.14286 | 0.85714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 3.10 | 2 | Task | Search service (OpenSearch, Indic analysers) | Phase 1 | Platform |  |  | 40 | 2026-12-16 | 2027-02-09 |  | 0 | 0 | 2 | 18 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 24 | 27.6 | PLT-FR-014 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 3.10.1 | 3 | Subtask | Detailed design and contracts | Phase 1 | Platform | ARC | 32 | 8 | 2026-12-16 | 2026-12-25 | 20 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4.6 | Design note, OpenAPI and event schemas | Not started |  | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 3.10.2 | 3 | Subtask | Build and unit tests | Phase 1 | Platform | BE | 40 | 24 | 2026-12-28 | 2027-01-28 |  | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 16.1 | Working service | Not started |  | 0% | 0 | 0.16667 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 3.10.3 | 3 | Subtask | Component, security and contract tests | Phase 1 | Platform | QA | 62 | 10 | 2027-01-27 | 2027-02-09 |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 6 | 6.9 | Test report | Not started |  | 0% | 0 | 0 | 0.3 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 3.11 | 2 | Task | Audit service, SIEM feed and CERT-In logging | Phase 1 | Platform |  |  | 40 | 2026-12-16 | 2027-02-09 |  | 0 | 0 | 2 | 11 | 0 | 0 | 0 | 9 | 4 | 0 | 0 | 26 | 29.9 | PLT-FR-012, 035 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 3.11.1 | 3 | Subtask | Detailed design and contracts | Phase 1 | Platform | ARC | 32 | 8 | 2026-12-16 | 2026-12-25 | 20 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3.45 | Design note, OpenAPI and event schemas | Not started |  | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 3.11.2 | 3 | Subtask | Build and unit tests | Phase 1 | Platform | BE | 40 | 24 | 2026-12-28 | 2027-01-28 |  | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 18 | 20.7 | Working service | Not started |  | 0% | 0 | 0.16667 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 3.11.3 | 3 | Subtask | Component, security and contract tests | Phase 1 | Platform | QA | 62 | 10 | 2027-01-27 | 2027-02-09 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 5 | 5.75 | Test report | Not started |  | 0% | 0 | 0 | 0.3 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 3.12 | 2 | Task | Aadhaar Data Vault with HSM | Phase 1 | Platform |  |  | 34 | 2026-12-16 | 2027-02-01 |  | 0 | 0 | 3 | 13 | 0 | 0 | 0 | 5 | 4 | 0 | 0 | 25 | 28.75 | PLT-FR-034 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 3.12.1 | 3 | Subtask | Detailed design and contracts | Phase 1 | Platform | ARC | 32 | 7 | 2026-12-16 | 2026-12-24 | 20 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4.6 | Design note, OpenAPI and event schemas | Not started |  | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 3.12.2 | 3 | Subtask | Build and unit tests | Phase 1 | Platform | BE | 39 | 20 | 2026-12-25 | 2027-01-21 |  | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 16 | 18.4 | Working service | Not started |  | 0% | 0 | 0.25 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 3.12.3 | 3 | Subtask | Component, security and contract tests | Phase 1 | Platform | QA | 58 | 8 | 2027-01-21 | 2027-02-01 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 5 | 5.75 | Test report | Not started |  | 0% | 0 | 0 | 0.875 | 0.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 3.13 | 2 | Task | Adapter hub framework | Phase 1 | Platform |  |  | 33 | 2026-12-01 | 2027-01-14 |  | 0 | 0 | 3 | 13 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 19 | 21.85 | PLT-FR-019 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 3.13.1 | 3 | Subtask | Detailed design and contracts | Phase 1 | Platform | ARC | 21 | 7 | 2026-12-01 | 2026-12-09 | 20 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4.6 | Design note, OpenAPI and event schemas | Not started |  | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | 3.13.2 | 3 | Subtask | Build and unit tests | Phase 1 | Platform | BE | 28 | 20 | 2026-12-10 | 2027-01-06 |  | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 12.65 | Working service | Not started |  | 0% | 0 | 0.8 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 3.13.3 | 3 | Subtask | Component, security and contract tests | Phase 1 | Platform | QA | 46 | 8 | 2027-01-05 | 2027-01-14 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 4 | 4.6 | Test report | Not started |  | 0% | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 3.14 | 2 | Task | Citizen portal and app shell (MyGWMC branding, 22-language i18n) | Phase 1 | Platform |  |  | 56 | 2026-12-01 | 2027-02-16 |  | 0 | 4 | 2 | 0 | 27 | 22 | 0 | 0 | 10 | 0 | 0 | 65 | 74.75 | PLT-FR-009, 021, 022 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 3.14.1 | 3 | Subtask | Detailed design and contracts | Phase 1 | Platform | ARC | 21 | 11 | 2026-12-01 | 2026-12-15 | 20 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2.3 | Design note, OpenAPI and event schemas | Not started |  | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 3.14.2 | 3 | Subtask | Build and unit tests | Phase 1 | Platform | FE | 32 | 34 | 2026-12-16 | 2027-02-01 |  | 0 | 4 | 0 | 0 | 27 | 22 | 0 | 0 | 0 | 0 | 0 | 53 | 60.95 | Working service | Not started |  | 0% | 0 | 0.35294 | 0.61765 | 0.029412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 3.14.3 | 3 | Subtask | Component, security and contract tests | Phase 1 | Platform | QA | 63 | 14 | 2027-01-28 | 2027-02-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 11.5 | Test report | Not started |  | 0% | 0 | 0 | 0.14286 | 0.85714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 3.15 | 2 | Task | Staff console shell, work queues and maps | Phase 1 | Platform |  |  | 45 | 2026-12-01 | 2027-02-01 |  | 0 | 0 | 2 | 0 | 22 | 0 | 0 | 0 | 6 | 0 | 0 | 30 | 34.5 | Console |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 3.15.1 | 3 | Subtask | Detailed design and contracts | Phase 1 | Platform | ARC | 21 | 9 | 2026-12-01 | 2026-12-11 | 20 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2.3 | Design note, OpenAPI and event schemas | Not started |  | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 3.15.2 | 3 | Subtask | Build and unit tests | Phase 1 | Platform | FE | 30 | 27 | 2026-12-14 | 2027-01-19 |  | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 25.3 | Working service | Not started |  | 0% | 0 | 0.51852 | 0.48148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 3.15.3 | 3 | Subtask | Component, security and contract tests | Phase 1 | Platform | QA | 55 | 11 | 2027-01-18 | 2027-02-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 6.9 | Test report | Not started |  | 0% | 0 | 0 | 0.90909 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | 3.16 | 2 | Task | Field app shell and offline sync service | Phase 1 | Platform |  |  | 51 | 2026-12-09 | 2027-02-17 |  | 0 | 0 | 2 | 13 | 0 | 27 | 0 | 0 | 8 | 0 | 0 | 50 | 57.5 | PLT-FR-013 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 3.16.1 | 3 | Subtask | Detailed design and contracts | Phase 1 | Platform | ARC | 27 | 10 | 2026-12-09 | 2026-12-22 | 20 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3.45 | Design note, OpenAPI and event schemas | Not started |  | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 3.16.2 | 3 | Subtask | Build and unit tests | Phase 1 | Platform | MOB | 37 | 30 | 2026-12-23 | 2027-02-02 |  | 0 | 0 | 0 | 11 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 38 | 43.7 | Working service | Not started |  | 0% | 0 | 0.23333 | 0.7 | 0.066667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 3.16.3 | 3 | Subtask | Component, security and contract tests | Phase 1 | Platform | QA | 65 | 13 | 2027-02-01 | 2027-02-17 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 9 | 10.35 | Test report | Not started |  | 0% | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 3.17 | 2 | Task | Reporting warehouse, ELT and Superset dashboards | Phase 1 | Platform |  |  | 45 | 2027-01-08 | 2027-03-11 |  | 0 | 0 | 2 | 18 | 4 | 0 | 0 | 0 | 4 | 9 | 0 | 37 | 42.55 | PLT-FR-011 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 3.17.1 | 3 | Subtask | Detailed design and contracts | Phase 1 | Platform | ARC | 49 | 9 | 2027-01-08 | 2027-01-20 | 20 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4.6 | Design note, OpenAPI and event schemas | Not started |  | 0% | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 3.17.2 | 3 | Subtask | Build and unit tests | Phase 1 | Platform | BE | 58 | 27 | 2027-01-21 | 2027-02-26 |  | 0 | 0 | 0 | 14 | 4 | 0 | 0 | 0 | 0 | 9 | 0 | 27 | 31.05 | Working service | Not started |  | 0% | 0 | 0 | 0.25926 | 0.74074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 3.17.3 | 3 | Subtask | Component, security and contract tests | Phase 1 | Platform | QA | 83 | 11 | 2027-02-25 | 2027-03-11 |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 6 | 6.9 | Test report | Not started |  | 0% | 0 | 0 | 0 | 0.18182 | 0.81818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 3.18 | 2 | Task | Observability: OpenTelemetry, Prometheus, Grafana, Loki | Phase 1 | Platform |  |  | 39 | 2026-11-24 | 2027-01-15 |  | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 11 | 3 | 0 | 0 | 20 | 23 | NFR-018 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 3.18.1 | 3 | Subtask | Detailed design and contracts | Phase 1 | Platform | ARC | 16 | 8 | 2026-11-24 | 2026-12-03 | 20 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2.3 | Design note, OpenAPI and event schemas | Not started |  | 0% | 0.625 | 0.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 3.18.2 | 3 | Subtask | Build and unit tests | Phase 1 | Platform | DEV | 23 | 24 | 2026-12-03 | 2027-01-05 |  | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 15 | 17.25 | Working service | Not started |  | 0% | 0 | 0.875 | 0.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 3.18.3 | 3 | Subtask | Component, security and contract tests | Phase 1 | Platform | QA | 45 | 10 | 2027-01-04 | 2027-01-15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 3.45 | Test report | Not started |  | 0% | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 3.19 | 2 | Task | Infrastructure and security (production) | Phase 1 | Platform |  |  | 45 | 2026-12-28 | 2027-02-26 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 56 | 64.4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 3.19.1 | 3 | Subtask | Production cluster in State Data Centre | Phase 1 | Platform | DEV | 40 | 30 | 2026-12-28 | 2027-02-05 |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 21 | 24.15 | Production environment | Not started |  | 0% | 0 | 0.13333 | 0.7 | 0.16667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 3.19.2 | 3 | Subtask | DR site, replication and backup | Phase 1 | Platform | DEV | 60 | 25 | 2027-01-25 | 2027-02-26 |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 14 | 16.1 | DR environment | Not started |  | 0% | 0 | 0 | 0.2 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 3.19.3 | 3 | Subtask | HSM, secrets (OpenBao), hardening and network policies | Phase 1 | Platform | DEV | 50 | 25 | 2027-01-11 | 2027-02-12 |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 13 | 14.95 | Hardening checklist | Not started |  | 0% | 0 | 0 | 0.6 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 3.19.4 | 3 | Subtask | SIEM (Wazuh) and NTP to NIC/NPL time servers | Phase 1 | Platform | DEV | 60 | 20 | 2027-01-25 | 2027-02-19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 9.2 | SIEM live | Not started |  | 0% | 0 | 0 | 0.25 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 4 | 1 | Phase | Phase 1: Foundation and revenue core | Phase 1 |  |  |  | 120 | 2026-11-30 | 2027-05-14 |  | 5 | 213 | 60 | 693 | 402 | 80 | 50 | 20 | 297 | 89 | 63 | 1972 | 2267.8 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 4.1 | 2 | Task | Module 1: Property Tax & Revenue Management | Phase 1 | 1 Property Tax |  |  | 101 | 2026-11-30 | 2027-04-19 |  | 1 | 46 | 13 | 160 | 92 | 32 | 18 | 0 | 59 | 21 | 11 | 453 | 520.95 | 33 processes, 38 requirements (PTX) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 4.1.1 | 3 | Subtask | Process validation workshops and to-be sign-off | Phase 1 | 1 Property Tax | BA | 20 | 13 | 2026-11-30 | 2026-12-16 | 23 | 1 | 14 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 21.85 | Signed process maps | Not started |  | 0% | 0.076923 | 0.92308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | 4.1.2 | 3 | Subtask | LLD, data model and API/event contracts | Phase 1 | 1 Property Tax | ARC | 29 | 13 | 2026-12-11 | 2026-12-29 | 104 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 20.7 | LLD, OpenAPI, schemas | Not started |  | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | 4.1.3 | 3 | Subtask | UX wireframes and UI design | Phase 1 | 1 Property Tax | FE | 29 | 13 | 2026-12-11 | 2026-12-29 | 104 | 0 | 4 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 17.25 | Approved wireframes | Not started |  | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | 4.1.4 | 3 | Subtask | Database schema, domain logic and APIs | Phase 1 | 1 Property Tax | BE | 40 | 47 | 2026-12-28 | 2027-03-02 | 105 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 60.95 | Service build | Not started |  | 0% | 0 | 0.085106 | 0.44681 | 0.42553 | 0.042553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | 4.1.5 | 3 | Subtask | Workflows (BPMN) and rules (DMN) configuration | Phase 1 | 1 Property Tax | BE | 54 | 34 | 2027-01-15 | 2027-03-03 | 105 | 0 | 7 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 28.75 | Deployed workflows and decision tables | Not started |  | 0% | 0 | 0 | 0.32353 | 0.58824 | 0.088235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | 4.1.6 | 3 | Subtask | Staff console screens | Phase 1 | 1 Property Tax | FE | 48 | 45 | 2027-01-07 | 2027-03-10 | 106 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 50.6 | Staff screens | Not started |  | 0% | 0 | 0 | 0.37778 | 0.44444 | 0.17778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | 4.1.7 | 3 | Subtask | Citizen portal and app services | Phase 1 | 1 Property Tax | FE | 59 | 34 | 2027-01-22 | 2027-03-10 | 106 | 0 | 0 | 0 | 0 | 21 | 11 | 0 | 0 | 0 | 0 | 0 | 32 | 36.8 | Citizen services live in MyGWMC | Not started |  | 0% | 0 | 0 | 0.17647 | 0.58824 | 0.23529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | 4.1.8 | 3 | Subtask | Field app tasks (offline) | Phase 1 | 1 Property Tax | MOB | 59 | 34 | 2027-01-22 | 2027-03-10 | 106 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 21 | 24.15 | Field app plug-in | Not started |  | 0% | 0 | 0 | 0.17647 | 0.58824 | 0.23529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | 4.1.9 | 3 | Subtask | GIS layers, map views and spatial checks | Phase 1 | 1 Property Tax | GIS | 48 | 39 | 2027-01-07 | 2027-03-02 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 18 | 20.7 | Layers and map features | Not started |  | 0% | 0 | 0 | 0.4359 | 0.51282 | 0.051282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | 4.1.10 | 3 | Subtask | Module interfaces (16 I-xx links): events and APIs | Phase 1 | 1 Property Tax | BE | 65 | 31 | 2027-02-01 | 2027-03-15 | 107 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 27.6 | Contract-tested interfaces | Not started |  | 0% | 0 | 0 | 0 | 0.64516 | 0.35484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 | 4.1.11 | 3 | Subtask | External system adapters (7) | Phase 1 | 1 Property Tax | BE | 59 | 37 | 2027-01-22 | 2027-03-15 | 105 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 42 | 48.3 | Adapters tested with provider sandboxes | Not started |  | 0% | 0 | 0 | 0.16216 | 0.54054 | 0.2973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | 4.1.12 | 3 | Subtask | Reports, dashboards, notices and templates (all active languages) | Phase 1 | 1 Property Tax | BE | 76 | 22 | 2027-02-16 | 2027-03-17 | 107 | 0 | 4 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 20.7 | Reports and templates | Not started |  | 0% | 0 | 0 | 0 | 0.40909 | 0.59091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | 4.1.13 | 3 | Subtask | Data migration: CDMA property, demand and arrears | Phase 1 | 1 Property Tax | DATA | 54 | 50 | 2027-01-15 | 2027-03-25 | 105 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 25 | 28.75 | Migration scripts and reconciliation report | Not started |  | 0% | 0 | 0 | 0.22 | 0.4 | 0.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | 4.1.14 | 3 | Subtask | System integration testing | Phase 1 | 1 Property Tax | QA | 89 | 18 | 2027-03-05 | 2027-03-30 | 107,109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 36 | 41.4 | SIT report | Not started |  | 0% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | 4.1.15 | 3 | Subtask | Defect fixing and regression | Phase 1 | 1 Property Tax | BE | 93 | 22 | 2027-03-11 | 2027-04-09 | 117 | 0 | 0 | 0 | 14 | 9 | 0 | 0 | 0 | 7 | 0 | 0 | 30 | 34.5 | Closed defects | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.68182 | 0.31818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | 4.1.16 | 3 | Subtask | UAT support with GWMC department | Phase 1 | 1 Property Tax | BA | 107 | 11 | 2027-03-31 | 2027-04-14 | 117 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 18 | 20.7 | UAT sign-off | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.090909 | 0.90909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | 4.1.17 | 3 | Subtask | Training material and department training | Phase 1 | 1 Property Tax | TRN | 110 | 11 | 2027-04-05 | 2027-04-19 | 119 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 15 | 17.25 | Trained users, manuals in Telugu and English | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | 4.2 | 2 | Task | Module 2: Water, Sewerage & Utility Billing | Phase 1 | 2 Water & Sewerage |  |  | 101 | 2026-11-30 | 2027-04-19 |  | 1 | 40 | 11 | 131 | 87 | 30 | 17 | 0 | 51 | 20 | 10 | 398 | 457.7 | 32 processes, 35 requirements (WTR) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | 4.2.1 | 3 | Subtask | Process validation workshops and to-be sign-off | Phase 1 | 2 Water & Sewerage | BA | 20 | 13 | 2026-11-30 | 2026-12-16 | 23 | 1 | 13 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 19.55 | Signed process maps | Not started |  | 0% | 0.076923 | 0.92308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 | 4.2.2 | 3 | Subtask | LLD, data model and API/event contracts | Phase 1 | 2 Water & Sewerage | ARC | 29 | 13 | 2026-12-11 | 2026-12-29 | 122 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18.4 | LLD, OpenAPI, schemas | Not started |  | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | 4.2.3 | 3 | Subtask | UX wireframes and UI design | Phase 1 | 2 Water & Sewerage | FE | 29 | 13 | 2026-12-11 | 2026-12-29 | 122 | 0 | 3 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 14.95 | Approved wireframes | Not started |  | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | 4.2.4 | 3 | Subtask | Database schema, domain logic and APIs | Phase 1 | 2 Water & Sewerage | BE | 40 | 47 | 2026-12-28 | 2027-03-02 | 123 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 57.5 | Service build | Not started |  | 0% | 0 | 0.085106 | 0.44681 | 0.42553 | 0.042553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | 4.2.5 | 3 | Subtask | Workflows (BPMN) and rules (DMN) configuration | Phase 1 | 2 Water & Sewerage | BE | 54 | 34 | 2027-01-15 | 2027-03-03 | 123 | 0 | 7 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 27.6 | Deployed workflows and decision tables | Not started |  | 0% | 0 | 0 | 0.32353 | 0.58824 | 0.088235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | 4.2.6 | 3 | Subtask | Staff console screens | Phase 1 | 2 Water & Sewerage | FE | 48 | 45 | 2027-01-07 | 2027-03-10 | 124 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 48.3 | Staff screens | Not started |  | 0% | 0 | 0 | 0.37778 | 0.44444 | 0.17778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | 4.2.7 | 3 | Subtask | Citizen portal and app services | Phase 1 | 2 Water & Sewerage | FE | 59 | 34 | 2027-01-22 | 2027-03-10 | 124 | 0 | 0 | 0 | 0 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 30 | 34.5 | Citizen services live in MyGWMC | Not started |  | 0% | 0 | 0 | 0.17647 | 0.58824 | 0.23529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 | 4.2.8 | 3 | Subtask | Field app tasks (offline) | Phase 1 | 2 Water & Sewerage | MOB | 59 | 34 | 2027-01-22 | 2027-03-10 | 124 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 20 | 23 | Field app plug-in | Not started |  | 0% | 0 | 0 | 0.17647 | 0.58824 | 0.23529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | 4.2.9 | 3 | Subtask | GIS layers, map views and spatial checks | Phase 1 | 2 Water & Sewerage | GIS | 48 | 39 | 2027-01-07 | 2027-03-02 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 17 | 19.55 | Layers and map features | Not started |  | 0% | 0 | 0 | 0.4359 | 0.51282 | 0.051282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 | 4.2.10 | 3 | Subtask | Module interfaces (17 I-xx links): events and APIs | Phase 1 | 2 Water & Sewerage | BE | 65 | 31 | 2027-02-01 | 2027-03-15 | 125 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 29.9 | Contract-tested interfaces | Not started |  | 0% | 0 | 0 | 0 | 0.64516 | 0.35484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | 4.2.11 | 3 | Subtask | External system adapters (2) | Phase 1 | 2 Water & Sewerage | BE | 59 | 37 | 2027-01-22 | 2027-03-15 | 123 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 12 | 13.8 | Adapters tested with provider sandboxes | Not started |  | 0% | 0 | 0 | 0.16216 | 0.54054 | 0.2973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | 4.2.12 | 3 | Subtask | Reports, dashboards, notices and templates (all active languages) | Phase 1 | 2 Water & Sewerage | BE | 76 | 22 | 2027-02-16 | 2027-03-17 | 125 | 0 | 3 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 19.55 | Reports and templates | Not started |  | 0% | 0 | 0 | 0 | 0.40909 | 0.59091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | 4.2.13 | 3 | Subtask | Data migration: consumer, meter and arrears data | Phase 1 | 2 Water & Sewerage | DATA | 54 | 50 | 2027-01-15 | 2027-03-25 | 123 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 23 | 26.45 | Migration scripts and reconciliation report | Not started |  | 0% | 0 | 0 | 0.22 | 0.4 | 0.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | 4.2.14 | 3 | Subtask | System integration testing | Phase 1 | 2 Water & Sewerage | QA | 89 | 18 | 2027-03-05 | 2027-03-30 | 125,127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 34 | 39.1 | SIT report | Not started |  | 0% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | 4.2.15 | 3 | Subtask | Defect fixing and regression | Phase 1 | 2 Water & Sewerage | BE | 93 | 22 | 2027-03-11 | 2027-04-09 | 135 | 0 | 0 | 0 | 13 | 8 | 0 | 0 | 0 | 7 | 0 | 0 | 28 | 32.2 | Closed defects | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.68182 | 0.31818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | 4.2.16 | 3 | Subtask | UAT support with GWMC department | Phase 1 | 2 Water & Sewerage | BA | 107 | 11 | 2027-03-31 | 2027-04-14 | 135 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 16 | 18.4 | UAT sign-off | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.090909 | 0.90909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | 4.2.17 | 3 | Subtask | Training material and department training | Phase 1 | 2 Water & Sewerage | TRN | 110 | 11 | 2027-04-05 | 2027-04-19 | 137 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 13 | 14.95 | Trained users, manuals in Telugu and English | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139 | 4.3 | 2 | Task | Module 3: Citizen Service Desk, Grievance & RTI | Phase 1 | 3 Citizen Desk & RTI |  |  | 101 | 2026-11-30 | 2027-04-19 |  | 1 | 35 | 11 | 124 | 79 | 9 | 15 | 0 | 50 | 0 | 9 | 333 | 382.95 | 30 processes, 30 requirements (GRV) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | 4.3.1 | 3 | Subtask | Process validation workshops and to-be sign-off | Phase 1 | 3 Citizen Desk & RTI | BA | 20 | 13 | 2026-11-30 | 2026-12-16 | 23 | 1 | 12 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18.4 | Signed process maps | Not started |  | 0% | 0.076923 | 0.92308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | 4.3.2 | 3 | Subtask | LLD, data model and API/event contracts | Phase 1 | 3 Citizen Desk & RTI | ARC | 29 | 13 | 2026-12-11 | 2026-12-29 | 140 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18.4 | LLD, OpenAPI, schemas | Not started |  | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | 4.3.3 | 3 | Subtask | UX wireframes and UI design | Phase 1 | 3 Citizen Desk & RTI | FE | 29 | 13 | 2026-12-11 | 2026-12-29 | 140 | 0 | 3 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 13.8 | Approved wireframes | Not started |  | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | 4.3.4 | 3 | Subtask | Database schema, domain logic and APIs | Phase 1 | 3 Citizen Desk & RTI | BE | 40 | 47 | 2026-12-28 | 2027-03-02 | 141 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 51.75 | Service build | Not started |  | 0% | 0 | 0.085106 | 0.44681 | 0.42553 | 0.042553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | 4.3.5 | 3 | Subtask | Workflows (BPMN) and rules (DMN) configuration | Phase 1 | 3 Citizen Desk & RTI | BE | 54 | 34 | 2027-01-15 | 2027-03-03 | 141 | 0 | 6 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 24.15 | Deployed workflows and decision tables | Not started |  | 0% | 0 | 0 | 0.32353 | 0.58824 | 0.088235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | 4.3.6 | 3 | Subtask | Staff console screens | Phase 1 | 3 Citizen Desk & RTI | FE | 48 | 45 | 2027-01-07 | 2027-03-10 | 142 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 43.7 | Staff screens | Not started |  | 0% | 0 | 0 | 0.37778 | 0.44444 | 0.17778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | 4.3.7 | 3 | Subtask | Citizen portal and app services | Phase 1 | 3 Citizen Desk & RTI | FE | 59 | 34 | 2027-01-22 | 2027-03-10 | 142 | 0 | 0 | 0 | 0 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 27 | 31.05 | Citizen services live in MyGWMC | Not started |  | 0% | 0 | 0 | 0.17647 | 0.58824 | 0.23529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
147 | 4.3.8 | 3 | Subtask | GIS layers, map views and spatial checks | Phase 1 | 3 Citizen Desk & RTI | GIS | 48 | 39 | 2027-01-07 | 2027-03-02 | 141 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 15 | 17.25 | Layers and map features | Not started |  | 0% | 0 | 0 | 0.4359 | 0.51282 | 0.051282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
148 | 4.3.9 | 3 | Subtask | Module interfaces (5 I-xx links): events and APIs | Phase 1 | 3 Citizen Desk & RTI | BE | 65 | 31 | 2027-02-01 | 2027-03-15 | 143 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9.2 | Contract-tested interfaces | Not started |  | 0% | 0 | 0 | 0 | 0.64516 | 0.35484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 | 4.3.10 | 3 | Subtask | External system adapters (6) | Phase 1 | 3 Citizen Desk & RTI | BE | 59 | 37 | 2027-01-22 | 2027-03-15 | 141 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 36 | 41.4 | Adapters tested with provider sandboxes | Not started |  | 0% | 0 | 0 | 0.16216 | 0.54054 | 0.2973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 | 4.3.11 | 3 | Subtask | Reports, dashboards, notices and templates (all active languages) | Phase 1 | 3 Citizen Desk & RTI | BE | 76 | 22 | 2027-02-16 | 2027-03-17 | 143 | 0 | 3 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 17.25 | Reports and templates | Not started |  | 0% | 0 | 0 | 0 | 0.40909 | 0.59091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
151 | 4.3.12 | 3 | Subtask | System integration testing | Phase 1 | 3 Citizen Desk & RTI | QA | 89 | 18 | 2027-03-05 | 2027-03-30 | 143,145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 34.5 | SIT report | Not started |  | 0% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
152 | 4.3.13 | 3 | Subtask | Defect fixing and regression | Phase 1 | 3 Citizen Desk & RTI | BE | 93 | 22 | 2027-03-11 | 2027-04-09 | 151 | 0 | 0 | 0 | 12 | 8 | 0 | 0 | 0 | 6 | 0 | 0 | 26 | 29.9 | Closed defects | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.68182 | 0.31818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
153 | 4.3.14 | 3 | Subtask | UAT support with GWMC department | Phase 1 | 3 Citizen Desk & RTI | BA | 107 | 11 | 2027-03-31 | 2027-04-14 | 151 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 16 | 18.4 | UAT sign-off | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.090909 | 0.90909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
154 | 4.3.15 | 3 | Subtask | Training material and department training | Phase 1 | 3 Citizen Desk & RTI | TRN | 110 | 11 | 2027-04-05 | 2027-04-19 | 153 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 12 | 13.8 | Trained users, manuals in Telugu and English | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
155 | 4.4 | 2 | Task | Module 4: Finance & Accounting | Phase 1 | 4 Finance & Accounting |  |  | 101 | 2026-11-30 | 2027-04-19 |  | 1 | 38 | 11 | 126 | 61 | 0 | 0 | 0 | 49 | 18 | 9 | 313 | 359.95 | 30 processes, 30 requirements (FIN) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
156 | 4.4.1 | 3 | Subtask | Process validation workshops and to-be sign-off | Phase 1 | 4 Finance & Accounting | BA | 20 | 13 | 2026-11-30 | 2026-12-16 | 23 | 1 | 12 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18.4 | Signed process maps | Not started |  | 0% | 0.076923 | 0.92308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | 4.4.2 | 3 | Subtask | LLD, data model and API/event contracts | Phase 1 | 4 Finance & Accounting | ARC | 29 | 13 | 2026-12-11 | 2026-12-29 | 156 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18.4 | LLD, OpenAPI, schemas | Not started |  | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 | 4.4.3 | 3 | Subtask | UX wireframes and UI design | Phase 1 | 4 Finance & Accounting | FE | 29 | 13 | 2026-12-11 | 2026-12-29 | 156 | 0 | 3 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 13.8 | Approved wireframes | Not started |  | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
159 | 4.4.4 | 3 | Subtask | Database schema, domain logic and APIs | Phase 1 | 4 Finance & Accounting | BE | 40 | 47 | 2026-12-28 | 2027-03-02 | 157 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 51.75 | Service build | Not started |  | 0% | 0 | 0.085106 | 0.44681 | 0.42553 | 0.042553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 | 4.4.5 | 3 | Subtask | Workflows (BPMN) and rules (DMN) configuration | Phase 1 | 4 Finance & Accounting | BE | 54 | 34 | 2027-01-15 | 2027-03-03 | 157 | 0 | 6 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 24.15 | Deployed workflows and decision tables | Not started |  | 0% | 0 | 0 | 0.32353 | 0.58824 | 0.088235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
161 | 4.4.6 | 3 | Subtask | Staff console screens | Phase 1 | 4 Finance & Accounting | FE | 48 | 45 | 2027-01-07 | 2027-03-10 | 158 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 43.7 | Staff screens | Not started |  | 0% | 0 | 0 | 0.37778 | 0.44444 | 0.17778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | 4.4.7 | 3 | Subtask | Module interfaces (10 I-xx links): events and APIs | Phase 1 | 4 Finance & Accounting | BE | 65 | 31 | 2027-02-01 | 2027-03-15 | 159 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 17.25 | Contract-tested interfaces | Not started |  | 0% | 0 | 0 | 0 | 0.64516 | 0.35484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
163 | 4.4.8 | 3 | Subtask | External system adapters (5) | Phase 1 | 4 Finance & Accounting | BE | 59 | 37 | 2027-01-22 | 2027-03-15 | 157 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 30 | 34.5 | Adapters tested with provider sandboxes | Not started |  | 0% | 0 | 0 | 0.16216 | 0.54054 | 0.2973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
164 | 4.4.9 | 3 | Subtask | Reports, dashboards, notices and templates (all active languages) | Phase 1 | 4 Finance & Accounting | BE | 76 | 22 | 2027-02-16 | 2027-03-17 | 159 | 0 | 3 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 17.25 | Reports and templates | Not started |  | 0% | 0 | 0 | 0 | 0.40909 | 0.59091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 | 4.4.10 | 3 | Subtask | Data migration: opening balances, budgets, vendors | Phase 1 | 4 Finance & Accounting | DATA | 54 | 50 | 2027-01-15 | 2027-03-25 | 157 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 21 | 24.15 | Migration scripts and reconciliation report | Not started |  | 0% | 0 | 0 | 0.22 | 0.4 | 0.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
166 | 4.4.11 | 3 | Subtask | System integration testing | Phase 1 | 4 Finance & Accounting | QA | 89 | 18 | 2027-03-05 | 2027-03-30 | 159,161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 34.5 | SIT report | Not started |  | 0% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
167 | 4.4.12 | 3 | Subtask | Defect fixing and regression | Phase 1 | 4 Finance & Accounting | BE | 93 | 22 | 2027-03-11 | 2027-04-09 | 166 | 0 | 0 | 0 | 12 | 8 | 0 | 0 | 0 | 6 | 0 | 0 | 26 | 29.9 | Closed defects | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.68182 | 0.31818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
168 | 4.4.13 | 3 | Subtask | UAT support with GWMC department | Phase 1 | 4 Finance & Accounting | BA | 107 | 11 | 2027-03-31 | 2027-04-14 | 166 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 16 | 18.4 | UAT sign-off | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.090909 | 0.90909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169 | 4.4.14 | 3 | Subtask | Training material and department training | Phase 1 | 4 Finance & Accounting | TRN | 110 | 11 | 2027-04-05 | 2027-04-19 | 168 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 12 | 13.8 | Trained users, manuals in Telugu and English | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | 4.5 | 2 | Task | Module 9: Document Management System | Phase 1 | 9 Document Management |  |  | 101 | 2026-11-30 | 2027-04-19 |  | 1 | 38 | 11 | 116 | 79 | 9 | 0 | 0 | 49 | 18 | 9 | 330 | 379.5 | 30 processes, 31 requirements (DMS) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
171 | 4.5.1 | 3 | Subtask | Process validation workshops and to-be sign-off | Phase 1 | 9 Document Management | BA | 20 | 13 | 2026-11-30 | 2026-12-16 | 23 | 1 | 12 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18.4 | Signed process maps | Not started |  | 0% | 0.076923 | 0.92308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
172 | 4.5.2 | 3 | Subtask | LLD, data model and API/event contracts | Phase 1 | 9 Document Management | ARC | 29 | 13 | 2026-12-11 | 2026-12-29 | 171 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18.4 | LLD, OpenAPI, schemas | Not started |  | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
173 | 4.5.3 | 3 | Subtask | UX wireframes and UI design | Phase 1 | 9 Document Management | FE | 29 | 13 | 2026-12-11 | 2026-12-29 | 171 | 0 | 3 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 13.8 | Approved wireframes | Not started |  | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
174 | 4.5.4 | 3 | Subtask | Database schema, domain logic and APIs | Phase 1 | 9 Document Management | BE | 40 | 47 | 2026-12-28 | 2027-03-02 | 172 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 52.9 | Service build | Not started |  | 0% | 0 | 0.085106 | 0.44681 | 0.42553 | 0.042553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
175 | 4.5.5 | 3 | Subtask | Workflows (BPMN) and rules (DMN) configuration | Phase 1 | 9 Document Management | BE | 54 | 34 | 2027-01-15 | 2027-03-03 | 172 | 0 | 6 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 24.15 | Deployed workflows and decision tables | Not started |  | 0% | 0 | 0 | 0.32353 | 0.58824 | 0.088235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
176 | 4.5.6 | 3 | Subtask | Staff console screens | Phase 1 | 9 Document Management | FE | 48 | 45 | 2027-01-07 | 2027-03-10 | 173 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 43.7 | Staff screens | Not started |  | 0% | 0 | 0 | 0.37778 | 0.44444 | 0.17778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 | 4.5.7 | 3 | Subtask | Citizen portal and app services | Phase 1 | 9 Document Management | FE | 59 | 34 | 2027-01-22 | 2027-03-10 | 173 | 0 | 0 | 0 | 0 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 27 | 31.05 | Citizen services live in MyGWMC | Not started |  | 0% | 0 | 0 | 0.17647 | 0.58824 | 0.23529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 | 4.5.8 | 3 | Subtask | Module interfaces (3 I-xx links): events and APIs | Phase 1 | 9 Document Management | BE | 65 | 31 | 2027-02-01 | 2027-03-15 | 174 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4.6 | Contract-tested interfaces | Not started |  | 0% | 0 | 0 | 0 | 0.64516 | 0.35484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 | 4.5.9 | 3 | Subtask | External system adapters (5) | Phase 1 | 9 Document Management | BE | 59 | 37 | 2027-01-22 | 2027-03-15 | 172 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 30 | 34.5 | Adapters tested with provider sandboxes | Not started |  | 0% | 0 | 0 | 0.16216 | 0.54054 | 0.2973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 | 4.5.10 | 3 | Subtask | Reports, dashboards, notices and templates (all active languages) | Phase 1 | 9 Document Management | BE | 76 | 22 | 2027-02-16 | 2027-03-17 | 174 | 0 | 3 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 17.25 | Reports and templates | Not started |  | 0% | 0 | 0 | 0 | 0.40909 | 0.59091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 | 4.5.11 | 3 | Subtask | Data migration: legacy files for scanning and indexing | Phase 1 | 9 Document Management | DATA | 54 | 50 | 2027-01-15 | 2027-03-25 | 172 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 21 | 24.15 | Migration scripts and reconciliation report | Not started |  | 0% | 0 | 0 | 0.22 | 0.4 | 0.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
182 | 4.5.12 | 3 | Subtask | System integration testing | Phase 1 | 9 Document Management | QA | 89 | 18 | 2027-03-05 | 2027-03-30 | 174,176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 34.5 | SIT report | Not started |  | 0% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
183 | 4.5.13 | 3 | Subtask | Defect fixing and regression | Phase 1 | 9 Document Management | BE | 93 | 22 | 2027-03-11 | 2027-04-09 | 182 | 0 | 0 | 0 | 12 | 8 | 0 | 0 | 0 | 6 | 0 | 0 | 26 | 29.9 | Closed defects | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.68182 | 0.31818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
184 | 4.5.14 | 3 | Subtask | UAT support with GWMC department | Phase 1 | 9 Document Management | BA | 107 | 11 | 2027-03-31 | 2027-04-14 | 182 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 16 | 18.4 | UAT sign-off | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.090909 | 0.90909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 | 4.5.15 | 3 | Subtask | Training material and department training | Phase 1 | 9 Document Management | TRN | 110 | 11 | 2027-04-05 | 2027-04-19 | 184 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 12 | 13.8 | Trained users, manuals in Telugu and English | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186 | 4.6 | 2 | Task | Phase 1 release, testing and go-live | Phase 1 | Release |  |  | 22 | 2027-03-23 | 2027-04-21 |  | 0 | 11 | 3 | 24 | 0 | 0 | 0 | 16 | 35 | 12 | 15 | 116 | 133.4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
187 | 4.6.1 | 3 | Subtask | End-to-end integration testing (SRS E2E scenarios) | Phase 1 | Release | QA | 101 | 11 | 2027-03-23 | 2027-04-06 | 117,135,151,166,182 | 0 | 4 | 0 | 6 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 30 | 34.5 | E2E report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.63636 | 0.36364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
188 | 4.6.2 | 3 | Subtask | Performance and load testing (NFR-001/002) | Phase 1 | Release | QA | 104 | 8 | 2027-03-26 | 2027-04-06 |  | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 8 | 0 | 0 | 16 | 18.4 | Performance report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
189 | 4.6.3 | 3 | Subtask | Security audit by CERT-In empanelled auditor and fixes | Phase 1 | Release | QA | 107 | 11 | 2027-03-31 | 2027-04-14 |  | 0 | 0 | 3 | 10 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 21 | 24.15 | Audit certificate | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.090909 | 0.90909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
190 | 4.6.4 | 3 | Subtask | Training of trainers and end-user training programme | Phase 1 | Release | TRN | 112 | 11 | 2027-04-07 | 2027-04-21 |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 20 | 23 | Training attendance and feedback | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
191 | 4.6.5 | 3 | Subtask | Migration dress rehearsal and cut-over plan | Phase 1 | Release | DATA | 114 | 7 | 2027-04-09 | 2027-04-19 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 8 | 0 | 13 | 14.95 | Cut-over runbook | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
192 | 4.6.6 | 3 | Subtask | Production deployment and cut-over | Phase 1 | Release | DEV | 121 | 2 | 2027-04-20 | 2027-04-21 | 189,191,119,137,153,168,184 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 5 | 3 | 4 | 0 | 16 | 18.4 | Go-live | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
193 | 4.7 | 2 | Milestone | M1: Phase 1 go-live | Phase 1 |  |  | 123 | 0 | 2027-04-22 | 2027-04-22 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
194 | 4.7.1 | 3 | Subtask | Hypercare and stabilisation (4 weeks) | Phase 1 | Release | BE | 123 | 17 | 2027-04-22 | 2027-05-14 | 193 | 0 | 5 | 0 | 12 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 29 | 33.35 | Hypercare closure report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.41176 | 0.58824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
195 | 4.8 | 2 | Milestone | Phase 1 acceptance and sign-off | Phase 1 |  |  | 139 | 0 | 2027-05-14 | 2027-05-14 | 194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
196 | 4.9 | 2 | Milestone | Phase 1 build mid-point (next phase design may start) | Phase 1 |  |  | 76 | 0 | 2027-02-16 | 2027-02-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
197 | 5 | 1 | Phase | Phase 2: Regulation and licensing | Phase 2 |  |  |  | 142 | 2027-03-04 | 2027-09-17 |  | 5 | 153 | 42 | 558 | 303 | 102 | 88 | 20 | 229 | 73 | 49 | 1622 | 1865.3 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
198 | 5.1 | 2 | Task | Platform increments for Phase 2 | Phase 2 | Platform |  |  | 59 | 2027-03-23 | 2027-06-11 |  | 0 | 0 | 0 | 10 | 6 | 0 | 31 | 0 | 4 | 3 | 0 | 54 | 62.1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
199 | 5.1.1 | 3 | Subtask | GIS elevation and 3D service (DTM, DSM, 3D Tiles) | Phase 2 | Platform | GIS | 101 | 59 | 2027-03-23 | 2027-06-11 |  | 0 | 0 | 0 | 6 | 6 | 0 | 25 | 0 | 4 | 0 | 0 | 41 | 47.15 | Platform release | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.11864 | 0.37288 | 0.35593 | 0.15254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | 5.1.2 | 3 | Subtask | Hand over ward and planning layers to Town Planning (I-20) | Phase 2 | Platform | GIS | 101 | 59 | 2027-03-23 | 2027-06-11 |  | 0 | 0 | 0 | 4 | 0 | 0 | 6 | 0 | 0 | 3 | 0 | 13 | 14.95 | Platform release | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.11864 | 0.37288 | 0.35593 | 0.15254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | 5.2 | 2 | Task | Module 5: Trade Licence Management | Phase 2 | 5 Trade Licence |  |  | 119 | 2027-03-04 | 2027-08-17 |  | 1 | 33 | 9 | 103 | 67 | 24 | 13 | 0 | 40 | 16 | 8 | 314 | 361.1 | 26 processes, 26 requirements (TRL) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | 5.2.1 | 3 | Subtask | Process validation workshops and to-be sign-off | Phase 2 | 5 Trade Licence | BA | 88 | 16 | 2027-03-04 | 2027-03-25 | 196 | 1 | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 16.1 | Signed process maps | Not started |  | 0% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | 5.2.2 | 3 | Subtask | LLD, data model and API/event contracts | Phase 2 | 5 Trade Licence | ARC | 99 | 16 | 2027-03-19 | 2027-04-09 | 202 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 13.8 | LLD, OpenAPI, schemas | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.5625 | 0.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 5.2.3 | 3 | Subtask | UX wireframes and UI design | Phase 2 | 5 Trade Licence | FE | 99 | 16 | 2027-03-19 | 2027-04-09 | 202 | 0 | 3 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 12.65 | Approved wireframes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.5625 | 0.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | 5.2.4 | 3 | Subtask | Database schema, domain logic and APIs | Phase 2 | 5 Trade Licence | BE | 112 | 55 | 2027-04-07 | 2027-06-22 | 203 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 44.85 | Service build | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.32727 | 0.38182 | 0.29091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | 5.2.5 | 3 | Subtask | Workflows (BPMN) and rules (DMN) configuration | Phase 2 | 5 Trade Licence | BE | 128 | 40 | 2027-04-29 | 2027-06-23 | 203 | 0 | 5 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 20.7 | Deployed workflows and decision tables | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.525 | 0.425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | 5.2.6 | 3 | Subtask | Staff console screens | Phase 2 | 5 Trade Licence | FE | 121 | 53 | 2027-04-20 | 2027-07-01 | 204 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 36.8 | Staff screens | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.16981 | 0.39623 | 0.41509 | 0.018868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | 5.2.7 | 3 | Subtask | Citizen portal and app services | Phase 2 | 5 Trade Licence | FE | 134 | 40 | 2027-05-07 | 2027-07-01 | 204 | 0 | 0 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 24 | 27.6 | Citizen services live in MyGWMC | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.425 | 0.55 | 0.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
209 | 5.2.8 | 3 | Subtask | Field app tasks (offline) | Phase 2 | 5 Trade Licence | MOB | 134 | 40 | 2027-05-07 | 2027-07-01 | 204 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 16 | 18.4 | Field app plug-in | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.425 | 0.55 | 0.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
210 | 5.2.9 | 3 | Subtask | GIS layers, map views and spatial checks | Phase 2 | 5 Trade Licence | GIS | 121 | 46 | 2027-04-20 | 2027-06-22 | 203 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 13 | 14.95 | Layers and map features | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.19565 | 0.45652 | 0.34783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 | 5.2.10 | 3 | Subtask | Module interfaces (10 I-xx links): events and APIs | Phase 2 | 5 Trade Licence | BE | 141 | 37 | 2027-05-18 | 2027-07-07 | 205 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 17.25 | Contract-tested interfaces | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.27027 | 0.59459 | 0.13514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 | 5.2.11 | 3 | Subtask | External system adapters (3) | Phase 2 | 5 Trade Licence | BE | 134 | 44 | 2027-05-07 | 2027-07-07 | 203 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 18 | 20.7 | Adapters tested with provider sandboxes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.38636 | 0.5 | 0.11364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
213 | 5.2.12 | 3 | Subtask | Reports, dashboards, notices and templates (all active languages) | Phase 2 | 5 Trade Licence | BE | 154 | 26 | 2027-06-04 | 2027-07-09 | 205 | 0 | 3 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 14.95 | Reports and templates | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73077 | 0.26923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
214 | 5.2.13 | 3 | Subtask | Data migration: existing licences | Phase 2 | 5 Trade Licence | DATA | 128 | 59 | 2027-04-29 | 2027-07-20 | 203 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 19 | 21.85 | Migration scripts and reconciliation report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.033898 | 0.35593 | 0.37288 | 0.23729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
215 | 5.2.14 | 3 | Subtask | System integration testing | Phase 2 | 5 Trade Licence | QA | 170 | 21 | 2027-06-28 | 2027-07-26 | 205,207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 26 | 29.9 | SIT report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.85714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 5.2.15 | 3 | Subtask | Defect fixing and regression | Phase 2 | 5 Trade Licence | BE | 174 | 26 | 2027-07-02 | 2027-08-06 | 215 | 0 | 0 | 0 | 10 | 6 | 0 | 0 | 0 | 5 | 0 | 0 | 21 | 24.15 | Closed defects | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.80769 | 0.19231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 | 5.2.16 | 3 | Subtask | UAT support with GWMC department | Phase 2 | 5 Trade Licence | BA | 191 | 13 | 2027-07-27 | 2027-08-12 | 215 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 12 | 13.8 | UAT sign-off | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30769 | 0.69231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 | 5.2.17 | 3 | Subtask | Training material and department training | Phase 2 | 5 Trade Licence | TRN | 194 | 13 | 2027-07-30 | 2027-08-17 | 217 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 11 | 12.65 | Trained users, manuals in Telugu and English | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.076923 | 0.92308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 5.3 | 2 | Task | Module 6: User Charges Management | Phase 2 | 6 User Charges |  |  | 119 | 2027-03-04 | 2027-08-17 |  | 1 | 27 | 8 | 92 | 59 | 21 | 11 | 0 | 34 | 14 | 7 | 274 | 315.1 | 23 processes, 22 requirements (UCH) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220 | 5.3.1 | 3 | Subtask | Process validation workshops and to-be sign-off | Phase 2 | 6 User Charges | BA | 88 | 16 | 2027-03-04 | 2027-03-25 | 196 | 1 | 9 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 13.8 | Signed process maps | Not started |  | 0% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
221 | 5.3.2 | 3 | Subtask | LLD, data model and API/event contracts | Phase 2 | 6 User Charges | ARC | 99 | 16 | 2027-03-19 | 2027-04-09 | 220 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 13.8 | LLD, OpenAPI, schemas | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.5625 | 0.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 5.3.3 | 3 | Subtask | UX wireframes and UI design | Phase 2 | 6 User Charges | FE | 99 | 16 | 2027-03-19 | 2027-04-09 | 220 | 0 | 2 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 10.35 | Approved wireframes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.5625 | 0.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
223 | 5.3.4 | 3 | Subtask | Database schema, domain logic and APIs | Phase 2 | 6 User Charges | BE | 112 | 55 | 2027-04-07 | 2027-06-22 | 221 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 39.1 | Service build | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.32727 | 0.38182 | 0.29091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 5.3.5 | 3 | Subtask | Workflows (BPMN) and rules (DMN) configuration | Phase 2 | 6 User Charges | BE | 128 | 40 | 2027-04-29 | 2027-06-23 | 221 | 0 | 4 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 17.25 | Deployed workflows and decision tables | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.525 | 0.425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 | 5.3.6 | 3 | Subtask | Staff console screens | Phase 2 | 6 User Charges | FE | 121 | 53 | 2027-04-20 | 2027-07-01 | 222 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 32.2 | Staff screens | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.16981 | 0.39623 | 0.41509 | 0.018868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 | 5.3.7 | 3 | Subtask | Citizen portal and app services | Phase 2 | 6 User Charges | FE | 134 | 40 | 2027-05-07 | 2027-07-01 | 222 | 0 | 0 | 0 | 0 | 14 | 7 | 0 | 0 | 0 | 0 | 0 | 21 | 24.15 | Citizen services live in MyGWMC | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.425 | 0.55 | 0.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | 5.3.8 | 3 | Subtask | Field app tasks (offline) | Phase 2 | 6 User Charges | MOB | 134 | 40 | 2027-05-07 | 2027-07-01 | 222 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 14 | 16.1 | Field app plug-in | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.425 | 0.55 | 0.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | 5.3.9 | 3 | Subtask | GIS layers, map views and spatial checks | Phase 2 | 6 User Charges | GIS | 121 | 46 | 2027-04-20 | 2027-06-22 | 221 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 11 | 12.65 | Layers and map features | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.19565 | 0.45652 | 0.34783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | 5.3.10 | 3 | Subtask | Module interfaces (12 I-xx links): events and APIs | Phase 2 | 6 User Charges | BE | 141 | 37 | 2027-05-18 | 2027-07-07 | 223 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 20.7 | Contract-tested interfaces | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.27027 | 0.59459 | 0.13514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | 5.3.11 | 3 | Subtask | External system adapters (2) | Phase 2 | 6 User Charges | BE | 134 | 44 | 2027-05-07 | 2027-07-07 | 221 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 12 | 13.8 | Adapters tested with provider sandboxes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.38636 | 0.5 | 0.11364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | 5.3.12 | 3 | Subtask | Reports, dashboards, notices and templates (all active languages) | Phase 2 | 6 User Charges | BE | 154 | 26 | 2027-06-04 | 2027-07-09 | 223 | 0 | 2 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11.5 | Reports and templates | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73077 | 0.26923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | 5.3.13 | 3 | Subtask | Data migration: existing user-charge accounts | Phase 2 | 6 User Charges | DATA | 128 | 59 | 2027-04-29 | 2027-07-20 | 221 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 16 | 18.4 | Migration scripts and reconciliation report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.033898 | 0.35593 | 0.37288 | 0.23729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 | 5.3.14 | 3 | Subtask | System integration testing | Phase 2 | 6 User Charges | QA | 170 | 21 | 2027-06-28 | 2027-07-26 | 223,225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 22 | 25.3 | SIT report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.85714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
234 | 5.3.15 | 3 | Subtask | Defect fixing and regression | Phase 2 | 6 User Charges | BE | 174 | 26 | 2027-07-02 | 2027-08-06 | 233 | 0 | 0 | 0 | 9 | 6 | 0 | 0 | 0 | 4 | 0 | 0 | 19 | 21.85 | Closed defects | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.80769 | 0.19231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
235 | 5.3.16 | 3 | Subtask | UAT support with GWMC department | Phase 2 | 6 User Charges | BA | 191 | 13 | 2027-07-27 | 2027-08-12 | 233 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 12 | 13.8 | UAT sign-off | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30769 | 0.69231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
236 | 5.3.17 | 3 | Subtask | Training material and department training | Phase 2 | 6 User Charges | TRN | 194 | 13 | 2027-07-30 | 2027-08-17 | 235 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 9 | 10.35 | Trained users, manuals in Telugu and English | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.076923 | 0.92308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
237 | 5.4 | 2 | Task | Module 11: Building Permission Management / Integration | Phase 2 | 11 Building Permission |  |  | 119 | 2027-03-04 | 2027-08-17 |  | 1 | 28 | 8 | 138 | 61 | 21 | 12 | 0 | 45 | 14 | 7 | 335 | 385.25 | 22 processes, 25 requirements (BPM) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
238 | 5.4.1 | 3 | Subtask | Process validation workshops and to-be sign-off | Phase 2 | 11 Building Permission | BA | 88 | 16 | 2027-03-04 | 2027-03-25 | 196 | 1 | 9 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 13.8 | Signed process maps | Not started |  | 0% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
239 | 5.4.2 | 3 | Subtask | LLD, data model and API/event contracts | Phase 2 | 11 Building Permission | ARC | 99 | 16 | 2027-03-19 | 2027-04-09 | 238 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 13.8 | LLD, OpenAPI, schemas | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.5625 | 0.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
240 | 5.4.3 | 3 | Subtask | UX wireframes and UI design | Phase 2 | 11 Building Permission | FE | 99 | 16 | 2027-03-19 | 2027-04-09 | 238 | 0 | 2 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 10.35 | Approved wireframes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.5625 | 0.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
241 | 5.4.4 | 3 | Subtask | Database schema, domain logic and APIs | Phase 2 | 11 Building Permission | BE | 112 | 55 | 2027-04-07 | 2027-06-22 | 239 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 40.25 | Service build | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.32727 | 0.38182 | 0.29091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 5.4.5 | 3 | Subtask | Workflows (BPMN) and rules (DMN) configuration | Phase 2 | 11 Building Permission | BE | 128 | 40 | 2027-04-29 | 2027-06-23 | 239 | 0 | 5 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 19.55 | Deployed workflows and decision tables | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.525 | 0.425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
243 | 5.4.6 | 3 | Subtask | Staff console screens | Phase 2 | 11 Building Permission | FE | 121 | 53 | 2027-04-20 | 2027-07-01 | 240 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 33.35 | Staff screens | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.16981 | 0.39623 | 0.41509 | 0.018868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
244 | 5.4.7 | 3 | Subtask | Citizen portal and app services | Phase 2 | 11 Building Permission | FE | 134 | 40 | 2027-05-07 | 2027-07-01 | 240 | 0 | 0 | 0 | 0 | 14 | 7 | 0 | 0 | 0 | 0 | 0 | 21 | 24.15 | Citizen services live in MyGWMC | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.425 | 0.55 | 0.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
245 | 5.4.8 | 3 | Subtask | Field app tasks (offline) | Phase 2 | 11 Building Permission | MOB | 134 | 40 | 2027-05-07 | 2027-07-01 | 240 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 14 | 16.1 | Field app plug-in | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.425 | 0.55 | 0.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
246 | 5.4.9 | 3 | Subtask | GIS layers, map views and spatial checks | Phase 2 | 11 Building Permission | GIS | 121 | 46 | 2027-04-20 | 2027-06-22 | 239 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12 | 13.8 | Layers and map features | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.19565 | 0.45652 | 0.34783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
247 | 5.4.10 | 3 | Subtask | Module interfaces (14 I-xx links): events and APIs | Phase 2 | 11 Building Permission | BE | 141 | 37 | 2027-05-18 | 2027-07-07 | 241 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 24.15 | Contract-tested interfaces | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.27027 | 0.59459 | 0.13514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
248 | 5.4.11 | 3 | Subtask | External system adapters (10) | Phase 2 | 11 Building Permission | BE | 134 | 44 | 2027-05-07 | 2027-07-07 | 239 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 60 | 69 | Adapters tested with provider sandboxes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.38636 | 0.5 | 0.11364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
249 | 5.4.12 | 3 | Subtask | Reports, dashboards, notices and templates (all active languages) | Phase 2 | 11 Building Permission | BE | 154 | 26 | 2027-06-04 | 2027-07-09 | 241 | 0 | 2 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 13.8 | Reports and templates | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73077 | 0.26923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
250 | 5.4.13 | 3 | Subtask | Data migration: permits in TG-bPASS | Phase 2 | 11 Building Permission | DATA | 128 | 59 | 2027-04-29 | 2027-07-20 | 239 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 16 | 18.4 | Migration scripts and reconciliation report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.033898 | 0.35593 | 0.37288 | 0.23729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
251 | 5.4.14 | 3 | Subtask | System integration testing | Phase 2 | 11 Building Permission | QA | 170 | 21 | 2027-06-28 | 2027-07-26 | 241,243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 24 | 27.6 | SIT report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.85714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
252 | 5.4.15 | 3 | Subtask | Defect fixing and regression | Phase 2 | 11 Building Permission | BE | 174 | 26 | 2027-07-02 | 2027-08-06 | 251 | 0 | 0 | 0 | 9 | 6 | 0 | 0 | 0 | 5 | 0 | 0 | 20 | 23 | Closed defects | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.80769 | 0.19231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
253 | 5.4.16 | 3 | Subtask | UAT support with GWMC department | Phase 2 | 11 Building Permission | BA | 191 | 13 | 2027-07-27 | 2027-08-12 | 251 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 12 | 13.8 | UAT sign-off | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30769 | 0.69231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
254 | 5.4.17 | 3 | Subtask | Training material and department training | Phase 2 | 11 Building Permission | TRN | 194 | 13 | 2027-07-30 | 2027-08-17 | 253 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 9 | 10.35 | Trained users, manuals in Telugu and English | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.076923 | 0.92308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 5.5 | 2 | Task | Module 13: Town Planning | Phase 2 | 13 Town Planning |  |  | 119 | 2027-03-04 | 2027-08-17 |  | 1 | 28 | 8 | 98 | 61 | 21 | 12 | 0 | 38 | 14 | 7 | 288 | 331.2 | 23 processes, 24 requirements (TPL) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
256 | 5.5.1 | 3 | Subtask | Process validation workshops and to-be sign-off | Phase 2 | 13 Town Planning | BA | 88 | 16 | 2027-03-04 | 2027-03-25 | 196 | 1 | 9 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 13.8 | Signed process maps | Not started |  | 0% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
257 | 5.5.2 | 3 | Subtask | LLD, data model and API/event contracts | Phase 2 | 13 Town Planning | ARC | 99 | 16 | 2027-03-19 | 2027-04-09 | 256 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 13.8 | LLD, OpenAPI, schemas | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.5625 | 0.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
258 | 5.5.3 | 3 | Subtask | UX wireframes and UI design | Phase 2 | 13 Town Planning | FE | 99 | 16 | 2027-03-19 | 2027-04-09 | 256 | 0 | 2 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 10.35 | Approved wireframes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.5625 | 0.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
259 | 5.5.4 | 3 | Subtask | Database schema, domain logic and APIs | Phase 2 | 13 Town Planning | BE | 112 | 55 | 2027-04-07 | 2027-06-22 | 257 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 40.25 | Service build | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.32727 | 0.38182 | 0.29091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
260 | 5.5.5 | 3 | Subtask | Workflows (BPMN) and rules (DMN) configuration | Phase 2 | 13 Town Planning | BE | 128 | 40 | 2027-04-29 | 2027-06-23 | 257 | 0 | 5 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 19.55 | Deployed workflows and decision tables | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.525 | 0.425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
261 | 5.5.6 | 3 | Subtask | Staff console screens | Phase 2 | 13 Town Planning | FE | 121 | 53 | 2027-04-20 | 2027-07-01 | 258 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 33.35 | Staff screens | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.16981 | 0.39623 | 0.41509 | 0.018868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
262 | 5.5.7 | 3 | Subtask | Citizen portal and app services | Phase 2 | 13 Town Planning | FE | 134 | 40 | 2027-05-07 | 2027-07-01 | 258 | 0 | 0 | 0 | 0 | 14 | 7 | 0 | 0 | 0 | 0 | 0 | 21 | 24.15 | Citizen services live in MyGWMC | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.425 | 0.55 | 0.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
263 | 5.5.8 | 3 | Subtask | Field app tasks (offline) | Phase 2 | 13 Town Planning | MOB | 134 | 40 | 2027-05-07 | 2027-07-01 | 258 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 14 | 16.1 | Field app plug-in | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.425 | 0.55 | 0.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
264 | 5.5.9 | 3 | Subtask | GIS layers, map views and spatial checks | Phase 2 | 13 Town Planning | GIS | 121 | 46 | 2027-04-20 | 2027-06-22 | 257 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12 | 13.8 | Layers and map features | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.19565 | 0.45652 | 0.34783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
265 | 5.5.10 | 3 | Subtask | Module interfaces (11 I-xx links): events and APIs | Phase 2 | 13 Town Planning | BE | 141 | 37 | 2027-05-18 | 2027-07-07 | 259 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18.4 | Contract-tested interfaces | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.27027 | 0.59459 | 0.13514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 5.5.11 | 3 | Subtask | External system adapters (3) | Phase 2 | 13 Town Planning | BE | 134 | 44 | 2027-05-07 | 2027-07-07 | 257 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 18 | 20.7 | Adapters tested with provider sandboxes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.38636 | 0.5 | 0.11364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
267 | 5.5.12 | 3 | Subtask | Reports, dashboards, notices and templates (all active languages) | Phase 2 | 13 Town Planning | BE | 154 | 26 | 2027-06-04 | 2027-07-09 | 259 | 0 | 2 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 13.8 | Reports and templates | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73077 | 0.26923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
268 | 5.5.13 | 3 | Subtask | Data migration: layouts and LRS records | Phase 2 | 13 Town Planning | DATA | 128 | 59 | 2027-04-29 | 2027-07-20 | 257 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 16 | 18.4 | Migration scripts and reconciliation report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.033898 | 0.35593 | 0.37288 | 0.23729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
269 | 5.5.14 | 3 | Subtask | System integration testing | Phase 2 | 13 Town Planning | QA | 170 | 21 | 2027-06-28 | 2027-07-26 | 259,261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 24 | 27.6 | SIT report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.85714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
270 | 5.5.15 | 3 | Subtask | Defect fixing and regression | Phase 2 | 13 Town Planning | BE | 174 | 26 | 2027-07-02 | 2027-08-06 | 269 | 0 | 0 | 0 | 9 | 6 | 0 | 0 | 0 | 5 | 0 | 0 | 20 | 23 | Closed defects | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.80769 | 0.19231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 5.5.16 | 3 | Subtask | UAT support with GWMC department | Phase 2 | 13 Town Planning | BA | 191 | 13 | 2027-07-27 | 2027-08-12 | 269 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 12 | 13.8 | UAT sign-off | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30769 | 0.69231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
272 | 5.5.17 | 3 | Subtask | Training material and department training | Phase 2 | 13 Town Planning | TRN | 194 | 13 | 2027-07-30 | 2027-08-17 | 271 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 9 | 10.35 | Trained users, manuals in Telugu and English | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.076923 | 0.92308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
273 | 5.6 | 2 | Task | Module 18: Fire NOC Management | Phase 2 | 18 Fire NOC |  |  | 119 | 2027-03-04 | 2027-08-17 |  | 1 | 21 | 6 | 81 | 45 | 15 | 9 | 0 | 29 | 0 | 5 | 212 | 243.8 | 17 processes, 18 requirements (FNC) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
274 | 5.6.1 | 3 | Subtask | Process validation workshops and to-be sign-off | Phase 2 | 18 Fire NOC | BA | 88 | 16 | 2027-03-04 | 2027-03-25 | 196 | 1 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11.5 | Signed process maps | Not started |  | 0% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
275 | 5.6.2 | 3 | Subtask | LLD, data model and API/event contracts | Phase 2 | 18 Fire NOC | ARC | 99 | 16 | 2027-03-19 | 2027-04-09 | 274 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9.2 | LLD, OpenAPI, schemas | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.5625 | 0.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
276 | 5.6.3 | 3 | Subtask | UX wireframes and UI design | Phase 2 | 18 Fire NOC | FE | 99 | 16 | 2027-03-19 | 2027-04-09 | 274 | 0 | 2 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8.05 | Approved wireframes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0.5625 | 0.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
277 | 5.6.4 | 3 | Subtask | Database schema, domain logic and APIs | Phase 2 | 18 Fire NOC | BE | 112 | 55 | 2027-04-07 | 2027-06-22 | 275 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 29.9 | Service build | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.32727 | 0.38182 | 0.29091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
278 | 5.6.5 | 3 | Subtask | Workflows (BPMN) and rules (DMN) configuration | Phase 2 | 18 Fire NOC | BE | 128 | 40 | 2027-04-29 | 2027-06-23 | 275 | 0 | 4 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 14.95 | Deployed workflows and decision tables | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.525 | 0.425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
279 | 5.6.6 | 3 | Subtask | Staff console screens | Phase 2 | 18 Fire NOC | FE | 121 | 53 | 2027-04-20 | 2027-07-01 | 276 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 25.3 | Staff screens | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.16981 | 0.39623 | 0.41509 | 0.018868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
280 | 5.6.7 | 3 | Subtask | Citizen portal and app services | Phase 2 | 18 Fire NOC | FE | 134 | 40 | 2027-05-07 | 2027-07-01 | 276 | 0 | 0 | 0 | 0 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 15 | 17.25 | Citizen services live in MyGWMC | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.425 | 0.55 | 0.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
281 | 5.6.8 | 3 | Subtask | Field app tasks (offline) | Phase 2 | 18 Fire NOC | MOB | 134 | 40 | 2027-05-07 | 2027-07-01 | 276 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 11.5 | Field app plug-in | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.425 | 0.55 | 0.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 5.6.9 | 3 | Subtask | GIS layers, map views and spatial checks | Phase 2 | 18 Fire NOC | GIS | 121 | 46 | 2027-04-20 | 2027-06-22 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 9 | 10.35 | Layers and map features | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0.19565 | 0.45652 | 0.34783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
283 | 5.6.10 | 3 | Subtask | Module interfaces (11 I-xx links): events and APIs | Phase 2 | 18 Fire NOC | BE | 141 | 37 | 2027-05-18 | 2027-07-07 | 277 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18.4 | Contract-tested interfaces | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.27027 | 0.59459 | 0.13514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
284 | 5.6.11 | 3 | Subtask | External system adapters (3) | Phase 2 | 18 Fire NOC | BE | 134 | 44 | 2027-05-07 | 2027-07-07 | 275 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 18 | 20.7 | Adapters tested with provider sandboxes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.38636 | 0.5 | 0.11364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
285 | 5.6.12 | 3 | Subtask | Reports, dashboards, notices and templates (all active languages) | Phase 2 | 18 Fire NOC | BE | 154 | 26 | 2027-06-04 | 2027-07-09 | 277 | 0 | 2 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11.5 | Reports and templates | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73077 | 0.26923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
286 | 5.6.13 | 3 | Subtask | System integration testing | Phase 2 | 18 Fire NOC | QA | 170 | 21 | 2027-06-28 | 2027-07-26 | 277,279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 18 | 20.7 | SIT report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.85714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
287 | 5.6.14 | 3 | Subtask | Defect fixing and regression | Phase 2 | 18 Fire NOC | BE | 174 | 26 | 2027-07-02 | 2027-08-06 | 286 | 0 | 0 | 0 | 7 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 15 | 17.25 | Closed defects | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.80769 | 0.19231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
288 | 5.6.15 | 3 | Subtask | UAT support with GWMC department | Phase 2 | 18 Fire NOC | BA | 191 | 13 | 2027-07-27 | 2027-08-12 | 286 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 8 | 9.2 | UAT sign-off | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30769 | 0.69231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
289 | 5.6.16 | 3 | Subtask | Training material and department training | Phase 2 | 18 Fire NOC | TRN | 194 | 13 | 2027-07-30 | 2027-08-17 | 288 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 7 | 8.05 | Trained users, manuals in Telugu and English | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.076923 | 0.92308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
290 | 5.7 | 2 | Task | Phase 2 release, testing and go-live | Phase 2 | Release |  |  | 27 | 2027-07-15 | 2027-08-20 |  | 0 | 11 | 3 | 24 | 0 | 0 | 0 | 16 | 35 | 12 | 15 | 116 | 133.4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
291 | 5.7.1 | 3 | Subtask | End-to-end integration testing (SRS E2E scenarios) | Phase 2 | Release | QA | 183 | 13 | 2027-07-15 | 2027-08-02 | 215,233,251,269,286 | 0 | 4 | 0 | 6 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 30 | 34.5 | E2E report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92308 | 0.076923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
292 | 5.7.2 | 3 | Subtask | Performance and load testing (NFR-001/002) | Phase 2 | Release | QA | 187 | 9 | 2027-07-21 | 2027-08-02 |  | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 8 | 0 | 0 | 16 | 18.4 | Performance report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88889 | 0.11111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
293 | 5.7.3 | 3 | Subtask | Security audit by CERT-In empanelled auditor and fixes | Phase 2 | Release | QA | 191 | 13 | 2027-07-27 | 2027-08-12 |  | 0 | 0 | 3 | 10 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 21 | 24.15 | Audit certificate | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30769 | 0.69231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
294 | 5.7.4 | 3 | Subtask | Training of trainers and end-user training programme | Phase 2 | Release | TRN | 196 | 13 | 2027-08-03 | 2027-08-19 |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 20 | 23 | Training attendance and feedback | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
295 | 5.7.5 | 3 | Subtask | Migration dress rehearsal and cut-over plan | Phase 2 | Release | DATA | 199 | 8 | 2027-08-06 | 2027-08-17 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 8 | 0 | 13 | 14.95 | Cut-over runbook | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
296 | 5.7.6 | 3 | Subtask | Production deployment and cut-over | Phase 2 | Release | DEV | 207 | 3 | 2027-08-18 | 2027-08-20 | 293,295,217,235,253,271,288 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 5 | 3 | 4 | 0 | 16 | 18.4 | Go-live | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
297 | 5.8 | 2 | Milestone | M2: Phase 2 go-live | Phase 2 |  |  | 209 | 0 | 2027-08-20 | 2027-08-20 | 296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
298 | 5.8.1 | 3 | Subtask | Hypercare and stabilisation (4 weeks) | Phase 2 | Release | BE | 209 | 20 | 2027-08-20 | 2027-09-16 | 297 | 0 | 5 | 0 | 12 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 29 | 33.35 | Hypercare closure report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
299 | 5.9 | 2 | Milestone | Phase 2 acceptance and sign-off | Phase 2 |  |  | 229 | 0 | 2027-09-17 | 2027-09-17 | 298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
300 | 5.10 | 2 | Milestone | Phase 2 build mid-point (next phase design may start) | Phase 2 |  |  | 154 | 0 | 2027-06-04 | 2027-06-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
301 | 6 | 1 | Phase | Phase 3: Field operations | Phase 3 |  |  |  | 142 | 2027-07-06 | 2028-01-19 |  | 5 | 114 | 32 | 399 | 184 | 57 | 39 | 24 | 179 | 15 | 40 | 1088 | 1251.2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
302 | 6.1 | 2 | Task | Platform increments for Phase 3 | Phase 3 | Platform |  |  | 59 | 2027-07-23 | 2027-10-13 |  | 0 | 0 | 0 | 21 | 0 | 10 | 5 | 4 | 10 | 3 | 0 | 53 | 60.95 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
303 | 6.1.1 | 3 | Subtask | Field app scale-up and offline sync load test | Phase 3 | Platform | MOB | 189 | 59 | 2027-07-23 | 2027-10-13 |  | 0 | 0 | 0 | 5 | 0 | 10 | 0 | 0 | 6 | 0 | 0 | 21 | 24.15 | Platform release | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10169 | 0.37288 | 0.37288 | 0.15254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
304 | 6.1.2 | 3 | Subtask | AVLS, CCMS and IoT ingestion pipeline | Phase 3 | Platform | BE | 189 | 59 | 2027-07-23 | 2027-10-13 |  | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 20 | 23 | Platform release | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10169 | 0.37288 | 0.37288 | 0.15254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
305 | 6.1.3 | 3 | Subtask | Road register moves to Engineering (I-32) | Phase 3 | Platform | GIS | 189 | 59 | 2027-07-23 | 2027-10-13 |  | 0 | 0 | 0 | 4 | 0 | 0 | 5 | 0 | 0 | 3 | 0 | 12 | 13.8 | Platform release | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10169 | 0.37288 | 0.37288 | 0.15254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
306 | 6.2 | 2 | Task | Module 7: Solid Waste Management | Phase 3 | 7 Solid Waste |  |  | 119 | 2027-07-06 | 2027-12-17 |  | 1 | 21 | 6 | 86 | 35 | 11 | 9 | 0 | 29 | 0 | 5 | 203 | 233.45 | 17 processes, 19 requirements (SWM) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
307 | 6.2.1 | 3 | Subtask | Process validation workshops and to-be sign-off | Phase 3 | 7 Solid Waste | BA | 176 | 16 | 2027-07-06 | 2027-07-27 | 300 | 1 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11.5 | Signed process maps | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
308 | 6.2.2 | 3 | Subtask | LLD, data model and API/event contracts | Phase 3 | 7 Solid Waste | ARC | 187 | 16 | 2027-07-21 | 2027-08-11 | 307 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9.2 | LLD, OpenAPI, schemas | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
309 | 6.2.3 | 3 | Subtask | UX wireframes and UI design | Phase 3 | 7 Solid Waste | FE | 187 | 16 | 2027-07-21 | 2027-08-11 | 307 | 0 | 2 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8.05 | Approved wireframes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
310 | 6.2.4 | 3 | Subtask | Database schema, domain logic and APIs | Phase 3 | 7 Solid Waste | BE | 200 | 55 | 2027-08-09 | 2027-10-22 | 308 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 31.05 | Service build | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30909 | 0.4 | 0.29091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
311 | 6.2.5 | 3 | Subtask | Workflows (BPMN) and rules (DMN) configuration | Phase 3 | 7 Solid Waste | BE | 216 | 40 | 2027-08-31 | 2027-10-25 | 308 | 0 | 4 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 14.95 | Deployed workflows and decision tables | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025 | 0.55 | 0.425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
312 | 6.2.6 | 3 | Subtask | Staff console screens | Phase 3 | 7 Solid Waste | FE | 209 | 53 | 2027-08-20 | 2027-11-02 | 309 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 25.3 | Staff screens | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15094 | 0.41509 | 0.39623 | 0.037736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
313 | 6.2.7 | 3 | Subtask | Field app tasks (offline) | Phase 3 | 7 Solid Waste | MOB | 222 | 40 | 2027-09-08 | 2027-11-02 | 309 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 11 | 12.65 | Field app plug-in | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.425 | 0.525 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
314 | 6.2.8 | 3 | Subtask | GIS layers, map views and spatial checks | Phase 3 | 7 Solid Waste | GIS | 209 | 46 | 2027-08-20 | 2027-10-22 | 308 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 9 | 10.35 | Layers and map features | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17391 | 0.47826 | 0.34783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
315 | 6.2.9 | 3 | Subtask | Module interfaces (13 I-xx links): events and APIs | Phase 3 | 7 Solid Waste | BE | 229 | 37 | 2027-09-17 | 2027-11-08 | 310 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 23 | Contract-tested interfaces | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27027 | 0.56757 | 0.16216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
316 | 6.2.10 | 3 | Subtask | External system adapters (3) | Phase 3 | 7 Solid Waste | BE | 222 | 44 | 2027-09-08 | 2027-11-08 | 308 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 18 | 20.7 | Adapters tested with provider sandboxes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38636 | 0.47727 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
317 | 6.2.11 | 3 | Subtask | Reports, dashboards, notices and templates (all active languages) | Phase 3 | 7 Solid Waste | BE | 242 | 26 | 2027-10-06 | 2027-11-10 | 310 | 0 | 2 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11.5 | Reports and templates | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69231 | 0.30769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
318 | 6.2.12 | 3 | Subtask | System integration testing | Phase 3 | 7 Solid Waste | QA | 258 | 21 | 2027-10-28 | 2027-11-25 | 310,312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 18 | 20.7 | SIT report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.90476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
319 | 6.2.13 | 3 | Subtask | Defect fixing and regression | Phase 3 | 7 Solid Waste | BE | 262 | 26 | 2027-11-03 | 2027-12-08 | 318 | 0 | 0 | 0 | 7 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 15 | 17.25 | Closed defects | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.76923 | 0.23077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
320 | 6.2.14 | 3 | Subtask | UAT support with GWMC department | Phase 3 | 7 Solid Waste | BA | 279 | 13 | 2027-11-26 | 2027-12-14 | 318 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 8 | 9.2 | UAT sign-off | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23077 | 0.76923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
321 | 6.2.15 | 3 | Subtask | Training material and department training | Phase 3 | 7 Solid Waste | TRN | 282 | 13 | 2027-12-01 | 2027-12-17 | 320 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 7 | 8.05 | Trained users, manuals in Telugu and English | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
322 | 6.3 | 2 | Task | Module 10: Engineering Project Management System | Phase 3 | 10 Engineering Projects |  |  | 119 | 2027-07-06 | 2027-12-17 |  | 1 | 23 | 7 | 82 | 41 | 12 | 10 | 0 | 31 | 0 | 6 | 213 | 244.95 | 20 processes, 21 requirements (ENG) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
323 | 6.3.1 | 3 | Subtask | Process validation workshops and to-be sign-off | Phase 3 | 10 Engineering Projects | BA | 176 | 16 | 2027-07-06 | 2027-07-27 | 300 | 1 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 12.65 | Signed process maps | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
324 | 6.3.2 | 3 | Subtask | LLD, data model and API/event contracts | Phase 3 | 10 Engineering Projects | ARC | 187 | 16 | 2027-07-21 | 2027-08-11 | 323 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11.5 | LLD, OpenAPI, schemas | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
325 | 6.3.3 | 3 | Subtask | UX wireframes and UI design | Phase 3 | 10 Engineering Projects | FE | 187 | 16 | 2027-07-21 | 2027-08-11 | 323 | 0 | 2 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9.2 | Approved wireframes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
326 | 6.3.4 | 3 | Subtask | Database schema, domain logic and APIs | Phase 3 | 10 Engineering Projects | BE | 200 | 55 | 2027-08-09 | 2027-10-22 | 324 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 35.65 | Service build | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30909 | 0.4 | 0.29091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
327 | 6.3.5 | 3 | Subtask | Workflows (BPMN) and rules (DMN) configuration | Phase 3 | 10 Engineering Projects | BE | 216 | 40 | 2027-08-31 | 2027-10-25 | 324 | 0 | 4 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 16.1 | Deployed workflows and decision tables | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025 | 0.55 | 0.425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
328 | 6.3.6 | 3 | Subtask | Staff console screens | Phase 3 | 10 Engineering Projects | FE | 209 | 53 | 2027-08-20 | 2027-11-02 | 325 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 29.9 | Staff screens | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15094 | 0.41509 | 0.39623 | 0.037736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
329 | 6.3.7 | 3 | Subtask | Field app tasks (offline) | Phase 3 | 10 Engineering Projects | MOB | 222 | 40 | 2027-09-08 | 2027-11-02 | 325 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 13.8 | Field app plug-in | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.425 | 0.525 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
330 | 6.3.8 | 3 | Subtask | GIS layers, map views and spatial checks | Phase 3 | 10 Engineering Projects | GIS | 209 | 46 | 2027-08-20 | 2027-10-22 | 324 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 10 | 11.5 | Layers and map features | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17391 | 0.47826 | 0.34783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
331 | 6.3.9 | 3 | Subtask | Module interfaces (9 I-xx links): events and APIs | Phase 3 | 10 Engineering Projects | BE | 229 | 37 | 2027-09-17 | 2027-11-08 | 326 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 16.1 | Contract-tested interfaces | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27027 | 0.56757 | 0.16216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
332 | 6.3.10 | 3 | Subtask | External system adapters (2) | Phase 3 | 10 Engineering Projects | BE | 222 | 44 | 2027-09-08 | 2027-11-08 | 324 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 12 | 13.8 | Adapters tested with provider sandboxes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38636 | 0.47727 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
333 | 6.3.11 | 3 | Subtask | Reports, dashboards, notices and templates (all active languages) | Phase 3 | 10 Engineering Projects | BE | 242 | 26 | 2027-10-06 | 2027-11-10 | 326 | 0 | 2 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11.5 | Reports and templates | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69231 | 0.30769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
334 | 6.3.12 | 3 | Subtask | System integration testing | Phase 3 | 10 Engineering Projects | QA | 258 | 21 | 2027-10-28 | 2027-11-25 | 326,328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 20 | 23 | SIT report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.90476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
335 | 6.3.13 | 3 | Subtask | Defect fixing and regression | Phase 3 | 10 Engineering Projects | BE | 262 | 26 | 2027-11-03 | 2027-12-08 | 334 | 0 | 0 | 0 | 8 | 5 | 0 | 0 | 0 | 4 | 0 | 0 | 17 | 19.55 | Closed defects | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.76923 | 0.23077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
336 | 6.3.14 | 3 | Subtask | UAT support with GWMC department | Phase 3 | 10 Engineering Projects | BA | 279 | 13 | 2027-11-26 | 2027-12-14 | 334 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 10 | 11.5 | UAT sign-off | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23077 | 0.76923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
337 | 6.3.15 | 3 | Subtask | Training material and department training | Phase 3 | 10 Engineering Projects | TRN | 282 | 13 | 2027-12-01 | 2027-12-17 | 336 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 9.2 | Trained users, manuals in Telugu and English | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
338 | 6.4 | 2 | Task | Module 12: Street Light Management | Phase 3 | 12 Street Lights |  |  | 119 | 2027-07-06 | 2027-12-17 |  | 1 | 13 | 4 | 57 | 25 | 8 | 6 | 0 | 19 | 0 | 4 | 137 | 157.55 | 12 processes, 13 requirements (SLM) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
339 | 6.4.1 | 3 | Subtask | Process validation workshops and to-be sign-off | Phase 3 | 12 Street Lights | BA | 176 | 16 | 2027-07-06 | 2027-07-27 | 300 | 1 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8.05 | Signed process maps | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
340 | 6.4.2 | 3 | Subtask | LLD, data model and API/event contracts | Phase 3 | 12 Street Lights | ARC | 187 | 16 | 2027-07-21 | 2027-08-11 | 339 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6.9 | LLD, OpenAPI, schemas | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
341 | 6.4.3 | 3 | Subtask | UX wireframes and UI design | Phase 3 | 12 Street Lights | FE | 187 | 16 | 2027-07-21 | 2027-08-11 | 339 | 0 | 1 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5.75 | Approved wireframes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
342 | 6.4.4 | 3 | Subtask | Database schema, domain logic and APIs | Phase 3 | 12 Street Lights | BE | 200 | 55 | 2027-08-09 | 2027-10-22 | 340 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 21.85 | Service build | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30909 | 0.4 | 0.29091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
343 | 6.4.5 | 3 | Subtask | Workflows (BPMN) and rules (DMN) configuration | Phase 3 | 12 Street Lights | BE | 216 | 40 | 2027-08-31 | 2027-10-25 | 340 | 0 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9.2 | Deployed workflows and decision tables | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025 | 0.55 | 0.425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
344 | 6.4.6 | 3 | Subtask | Staff console screens | Phase 3 | 12 Street Lights | FE | 209 | 53 | 2027-08-20 | 2027-11-02 | 341 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18.4 | Staff screens | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15094 | 0.41509 | 0.39623 | 0.037736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
345 | 6.4.7 | 3 | Subtask | Field app tasks (offline) | Phase 3 | 12 Street Lights | MOB | 222 | 40 | 2027-09-08 | 2027-11-02 | 341 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 9.2 | Field app plug-in | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.425 | 0.525 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
346 | 6.4.8 | 3 | Subtask | GIS layers, map views and spatial checks | Phase 3 | 12 Street Lights | GIS | 209 | 46 | 2027-08-20 | 2027-10-22 | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 6 | 6.9 | Layers and map features | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17391 | 0.47826 | 0.34783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
347 | 6.4.9 | 3 | Subtask | Module interfaces (8 I-xx links): events and APIs | Phase 3 | 12 Street Lights | BE | 229 | 37 | 2027-09-17 | 2027-11-08 | 342 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 13.8 | Contract-tested interfaces | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27027 | 0.56757 | 0.16216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
348 | 6.4.10 | 3 | Subtask | External system adapters (2) | Phase 3 | 12 Street Lights | BE | 222 | 44 | 2027-09-08 | 2027-11-08 | 340 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 12 | 13.8 | Adapters tested with provider sandboxes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38636 | 0.47727 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
349 | 6.4.11 | 3 | Subtask | Reports, dashboards, notices and templates (all active languages) | Phase 3 | 12 Street Lights | BE | 242 | 26 | 2027-10-06 | 2027-11-10 | 342 | 0 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5.75 | Reports and templates | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69231 | 0.30769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
350 | 6.4.12 | 3 | Subtask | System integration testing | Phase 3 | 12 Street Lights | QA | 258 | 21 | 2027-10-28 | 2027-11-25 | 342,344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 12 | 13.8 | SIT report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.90476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
351 | 6.4.13 | 3 | Subtask | Defect fixing and regression | Phase 3 | 12 Street Lights | BE | 262 | 26 | 2027-11-03 | 2027-12-08 | 350 | 0 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 10 | 11.5 | Closed defects | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.76923 | 0.23077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
352 | 6.4.14 | 3 | Subtask | UAT support with GWMC department | Phase 3 | 12 Street Lights | BA | 279 | 13 | 2027-11-26 | 2027-12-14 | 350 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 6 | 6.9 | UAT sign-off | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23077 | 0.76923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
353 | 6.4.15 | 3 | Subtask | Training material and department training | Phase 3 | 12 Street Lights | TRN | 282 | 13 | 2027-12-01 | 2027-12-17 | 352 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 5.75 | Trained users, manuals in Telugu and English | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
354 | 6.5 | 2 | Task | Module 14: Parks & Horticulture Management | Phase 3 | 14 Parks & Horticulture |  |  | 119 | 2027-07-06 | 2027-12-17 |  | 1 | 21 | 6 | 60 | 46 | 16 | 9 | 0 | 26 | 0 | 5 | 190 | 218.5 | 18 processes, 18 requirements (PRK) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
355 | 6.5.1 | 3 | Subtask | Process validation workshops and to-be sign-off | Phase 3 | 14 Parks & Horticulture | BA | 176 | 16 | 2027-07-06 | 2027-07-27 | 300 | 1 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11.5 | Signed process maps | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
356 | 6.5.2 | 3 | Subtask | LLD, data model and API/event contracts | Phase 3 | 14 Parks & Horticulture | ARC | 187 | 16 | 2027-07-21 | 2027-08-11 | 355 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9.2 | LLD, OpenAPI, schemas | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
357 | 6.5.3 | 3 | Subtask | UX wireframes and UI design | Phase 3 | 14 Parks & Horticulture | FE | 187 | 16 | 2027-07-21 | 2027-08-11 | 355 | 0 | 2 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8.05 | Approved wireframes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
358 | 6.5.4 | 3 | Subtask | Database schema, domain logic and APIs | Phase 3 | 14 Parks & Horticulture | BE | 200 | 55 | 2027-08-09 | 2027-10-22 | 356 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 31.05 | Service build | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30909 | 0.4 | 0.29091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
359 | 6.5.5 | 3 | Subtask | Workflows (BPMN) and rules (DMN) configuration | Phase 3 | 14 Parks & Horticulture | BE | 216 | 40 | 2027-08-31 | 2027-10-25 | 356 | 0 | 4 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 14.95 | Deployed workflows and decision tables | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025 | 0.55 | 0.425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
360 | 6.5.6 | 3 | Subtask | Staff console screens | Phase 3 | 14 Parks & Horticulture | FE | 209 | 53 | 2027-08-20 | 2027-11-02 | 357 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 25.3 | Staff screens | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15094 | 0.41509 | 0.39623 | 0.037736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
361 | 6.5.7 | 3 | Subtask | Citizen portal and app services | Phase 3 | 14 Parks & Horticulture | FE | 222 | 40 | 2027-09-08 | 2027-11-02 | 357 | 0 | 0 | 0 | 0 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 16 | 18.4 | Citizen services live in MyGWMC | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.425 | 0.525 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
362 | 6.5.8 | 3 | Subtask | Field app tasks (offline) | Phase 3 | 14 Parks & Horticulture | MOB | 222 | 40 | 2027-09-08 | 2027-11-02 | 357 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 11 | 12.65 | Field app plug-in | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.425 | 0.525 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
363 | 6.5.9 | 3 | Subtask | GIS layers, map views and spatial checks | Phase 3 | 14 Parks & Horticulture | GIS | 209 | 46 | 2027-08-20 | 2027-10-22 | 356 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 9 | 10.35 | Layers and map features | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17391 | 0.47826 | 0.34783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
364 | 6.5.10 | 3 | Subtask | Module interfaces (6 I-xx links): events and APIs | Phase 3 | 14 Parks & Horticulture | BE | 229 | 37 | 2027-09-17 | 2027-11-08 | 358 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 10.35 | Contract-tested interfaces | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27027 | 0.56757 | 0.16216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
365 | 6.5.11 | 3 | Subtask | Reports, dashboards, notices and templates (all active languages) | Phase 3 | 14 Parks & Horticulture | BE | 242 | 26 | 2027-10-06 | 2027-11-10 | 358 | 0 | 2 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11.5 | Reports and templates | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69231 | 0.30769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
366 | 6.5.12 | 3 | Subtask | System integration testing | Phase 3 | 14 Parks & Horticulture | QA | 258 | 21 | 2027-10-28 | 2027-11-25 | 358,360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 18 | 20.7 | SIT report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.90476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
367 | 6.5.13 | 3 | Subtask | Defect fixing and regression | Phase 3 | 14 Parks & Horticulture | BE | 262 | 26 | 2027-11-03 | 2027-12-08 | 366 | 0 | 0 | 0 | 7 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 15 | 17.25 | Closed defects | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.76923 | 0.23077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
368 | 6.5.14 | 3 | Subtask | UAT support with GWMC department | Phase 3 | 14 Parks & Horticulture | BA | 279 | 13 | 2027-11-26 | 2027-12-14 | 366 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 8 | 9.2 | UAT sign-off | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23077 | 0.76923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
369 | 6.5.15 | 3 | Subtask | Training material and department training | Phase 3 | 14 Parks & Horticulture | TRN | 282 | 13 | 2027-12-01 | 2027-12-17 | 368 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 7 | 8.05 | Trained users, manuals in Telugu and English | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
370 | 6.6 | 2 | Task | Module 17: Inventory & Stores Management | Phase 3 | 17 Inventory & Stores |  |  | 119 | 2027-07-06 | 2027-12-17 |  | 1 | 20 | 6 | 57 | 33 | 0 | 0 | 0 | 25 | 0 | 5 | 147 | 169.05 | 17 processes, 17 requirements (INV) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
371 | 6.6.1 | 3 | Subtask | Process validation workshops and to-be sign-off | Phase 3 | 17 Inventory & Stores | BA | 176 | 16 | 2027-07-06 | 2027-07-27 | 300 | 1 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11.5 | Signed process maps | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
372 | 6.6.2 | 3 | Subtask | LLD, data model and API/event contracts | Phase 3 | 17 Inventory & Stores | ARC | 187 | 16 | 2027-07-21 | 2027-08-11 | 371 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9.2 | LLD, OpenAPI, schemas | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
373 | 6.6.3 | 3 | Subtask | UX wireframes and UI design | Phase 3 | 17 Inventory & Stores | FE | 187 | 16 | 2027-07-21 | 2027-08-11 | 371 | 0 | 2 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8.05 | Approved wireframes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
374 | 6.6.4 | 3 | Subtask | Database schema, domain logic and APIs | Phase 3 | 17 Inventory & Stores | BE | 200 | 55 | 2027-08-09 | 2027-10-22 | 372 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 29.9 | Service build | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30909 | 0.4 | 0.29091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
375 | 6.6.5 | 3 | Subtask | Workflows (BPMN) and rules (DMN) configuration | Phase 3 | 17 Inventory & Stores | BE | 216 | 40 | 2027-08-31 | 2027-10-25 | 372 | 0 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 12.65 | Deployed workflows and decision tables | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025 | 0.55 | 0.425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
376 | 6.6.6 | 3 | Subtask | Staff console screens | Phase 3 | 17 Inventory & Stores | FE | 209 | 53 | 2027-08-20 | 2027-11-02 | 373 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 24.15 | Staff screens | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15094 | 0.41509 | 0.39623 | 0.037736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
377 | 6.6.7 | 3 | Subtask | Module interfaces (3 I-xx links): events and APIs | Phase 3 | 17 Inventory & Stores | BE | 229 | 37 | 2027-09-17 | 2027-11-08 | 374 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4.6 | Contract-tested interfaces | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27027 | 0.56757 | 0.16216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
378 | 6.6.8 | 3 | Subtask | External system adapters (1) | Phase 3 | 17 Inventory & Stores | BE | 222 | 44 | 2027-09-08 | 2027-11-08 | 372 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 6 | 6.9 | Adapters tested with provider sandboxes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38636 | 0.47727 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
379 | 6.6.9 | 3 | Subtask | Reports, dashboards, notices and templates (all active languages) | Phase 3 | 17 Inventory & Stores | BE | 242 | 26 | 2027-10-06 | 2027-11-10 | 374 | 0 | 2 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9.2 | Reports and templates | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69231 | 0.30769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
380 | 6.6.10 | 3 | Subtask | System integration testing | Phase 3 | 17 Inventory & Stores | QA | 258 | 21 | 2027-10-28 | 2027-11-25 | 374,376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 17 | 19.55 | SIT report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.90476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
381 | 6.6.11 | 3 | Subtask | Defect fixing and regression | Phase 3 | 17 Inventory & Stores | BE | 262 | 26 | 2027-11-03 | 2027-12-08 | 380 | 0 | 0 | 0 | 7 | 4 | 0 | 0 | 0 | 3 | 0 | 0 | 14 | 16.1 | Closed defects | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.76923 | 0.23077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
382 | 6.6.12 | 3 | Subtask | UAT support with GWMC department | Phase 3 | 17 Inventory & Stores | BA | 279 | 13 | 2027-11-26 | 2027-12-14 | 380 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 8 | 9.2 | UAT sign-off | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23077 | 0.76923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
383 | 6.6.13 | 3 | Subtask | Training material and department training | Phase 3 | 17 Inventory & Stores | TRN | 282 | 13 | 2027-12-01 | 2027-12-17 | 382 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 7 | 8.05 | Trained users, manuals in Telugu and English | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
384 | 6.7 | 2 | Task | Phase 3 release, testing and go-live | Phase 3 | Release |  |  | 27 | 2027-11-16 | 2027-12-22 |  | 0 | 11 | 3 | 24 | 0 | 0 | 0 | 16 | 35 | 12 | 15 | 116 | 133.4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
385 | 6.7.1 | 3 | Subtask | End-to-end integration testing (SRS E2E scenarios) | Phase 3 | Release | QA | 271 | 13 | 2027-11-16 | 2027-12-02 | 318,334,350,366,380 | 0 | 4 | 0 | 6 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 30 | 34.5 | E2E report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84615 | 0.15385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
386 | 6.7.2 | 3 | Subtask | Performance and load testing (NFR-001/002) | Phase 3 | Release | QA | 275 | 9 | 2027-11-22 | 2027-12-02 |  | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 8 | 0 | 0 | 16 | 18.4 | Performance report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77778 | 0.22222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
387 | 6.7.3 | 3 | Subtask | Security audit by CERT-In empanelled auditor and fixes | Phase 3 | Release | QA | 279 | 13 | 2027-11-26 | 2027-12-14 |  | 0 | 0 | 3 | 10 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 21 | 24.15 | Audit certificate | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23077 | 0.76923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
388 | 6.7.4 | 3 | Subtask | Training of trainers and end-user training programme | Phase 3 | Release | TRN | 284 | 13 | 2027-12-03 | 2027-12-21 |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 20 | 23 | Training attendance and feedback | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
389 | 6.7.5 | 3 | Subtask | Migration dress rehearsal and cut-over plan | Phase 3 | Release | DATA | 287 | 8 | 2027-12-08 | 2027-12-17 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 8 | 0 | 13 | 14.95 | Cut-over runbook | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
390 | 6.7.6 | 3 | Subtask | Production deployment and cut-over | Phase 3 | Release | DEV | 295 | 3 | 2027-12-20 | 2027-12-22 | 387,389,320,336,352,368,382 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 5 | 3 | 4 | 0 | 16 | 18.4 | Go-live | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
391 | 6.8 | 2 | Milestone | M3: Phase 3 go-live | Phase 3 |  |  | 297 | 0 | 2027-12-22 | 2027-12-22 | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
392 | 6.8.1 | 3 | Subtask | Hypercare and stabilisation (4 weeks) | Phase 3 | Release | BE | 297 | 20 | 2027-12-22 | 2028-01-18 | 391 | 0 | 5 | 0 | 12 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 29 | 33.35 | Hypercare closure report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
393 | 6.9 | 2 | Milestone | Phase 3 acceptance and sign-off | Phase 3 |  |  | 317 | 0 | 2028-01-19 | 2028-01-19 | 392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
394 | 6.10 | 2 | Milestone | Phase 3 build mid-point (next phase design may start) | Phase 3 |  |  | 242 | 0 | 2027-10-06 | 2027-10-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
395 | 7 | 1 | Phase | Phase 4: Administration and welfare | Phase 4 |  |  |  | 142 | 2027-11-05 | 2028-05-22 |  | 4 | 101 | 27 | 306 | 151 | 32 | 8 | 20 | 147 | 66 | 34 | 896 | 1030.4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
396 | 7.1 | 2 | Task | Platform increments for Phase 4 | Phase 4 | Platform |  |  | 59 | 2027-11-24 | 2028-02-14 |  | 0 | 0 | 0 | 20 | 8 | 0 | 0 | 0 | 8 | 16 | 0 | 52 | 59.8 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
397 | 7.1.1 | 3 | Subtask | Org hierarchy and approvers move to HR (workflow switch-over) | Phase 4 | Platform | BE | 277 | 59 | 2027-11-24 | 2028-02-14 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 4 | 3 | 0 | 15 | 17.25 | Platform release | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084746 | 0.38983 | 0.35593 | 0.16949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
398 | 7.1.2 | 3 | Subtask | Legal and asset interim records migrated (I-30, I-42) | Phase 4 | Platform | DATA | 277 | 59 | 2027-11-24 | 2028-02-14 |  | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 12 | 13.8 | Platform release | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084746 | 0.38983 | 0.35593 | 0.16949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
399 | 7.1.3 | 3 | Subtask | Full cross-module MIS and state dashboards | Phase 4 | Platform | BE | 277 | 59 | 2027-11-24 | 2028-02-14 |  | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 4 | 5 | 0 | 25 | 28.75 | Platform release | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084746 | 0.38983 | 0.35593 | 0.16949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
400 | 7.2 | 2 | Task | Module 8: Payroll & HR Management | Phase 4 | 8 Payroll & HR |  |  | 119 | 2027-11-05 | 2028-04-19 |  | 1 | 25 | 7 | 71 | 39 | 11 | 0 | 0 | 30 | 11 | 6 | 201 | 231.15 | 19 processes, 19 requirements (HRM) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
401 | 7.2.1 | 3 | Subtask | Process validation workshops and to-be sign-off | Phase 4 | 8 Payroll & HR | BA | 264 | 16 | 2027-11-05 | 2027-11-26 | 394 | 1 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 12.65 | Signed process maps | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
402 | 7.2.2 | 3 | Subtask | LLD, data model and API/event contracts | Phase 4 | 8 Payroll & HR | ARC | 275 | 16 | 2027-11-22 | 2027-12-13 | 401 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11.5 | LLD, OpenAPI, schemas | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4375 | 0.5625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
403 | 7.2.3 | 3 | Subtask | UX wireframes and UI design | Phase 4 | 8 Payroll & HR | FE | 275 | 16 | 2027-11-22 | 2027-12-13 | 401 | 0 | 2 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9.2 | Approved wireframes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4375 | 0.5625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
404 | 7.2.4 | 3 | Subtask | Database schema, domain logic and APIs | Phase 4 | 8 Payroll & HR | BE | 288 | 55 | 2027-12-09 | 2028-02-23 | 402 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 32.2 | Service build | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30909 | 0.38182 | 0.30909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
405 | 7.2.5 | 3 | Subtask | Workflows (BPMN) and rules (DMN) configuration | Phase 4 | 8 Payroll & HR | BE | 304 | 40 | 2027-12-31 | 2028-02-24 | 402 | 0 | 4 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 16.1 | Deployed workflows and decision tables | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025 | 0.525 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
406 | 7.2.6 | 3 | Subtask | Staff console screens | Phase 4 | 8 Payroll & HR | FE | 297 | 53 | 2027-12-22 | 2028-03-03 | 403 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 27.6 | Staff screens | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15094 | 0.39623 | 0.39623 | 0.056604 | 0 | 0 | 0 | 0 | 0 | 0 | 0
407 | 7.2.7 | 3 | Subtask | Field app tasks (offline) | Phase 4 | 8 Payroll & HR | MOB | 310 | 40 | 2028-01-10 | 2028-03-03 | 403 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 11 | 12.65 | Field app plug-in | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.525 | 0.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0
408 | 7.2.8 | 3 | Subtask | Module interfaces (4 I-xx links): events and APIs | Phase 4 | 8 Payroll & HR | BE | 317 | 37 | 2028-01-19 | 2028-03-09 | 404 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6.9 | Contract-tested interfaces | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24324 | 0.56757 | 0.18919 | 0 | 0 | 0 | 0 | 0 | 0 | 0
409 | 7.2.9 | 3 | Subtask | External system adapters (2) | Phase 4 | 8 Payroll & HR | BE | 310 | 44 | 2028-01-10 | 2028-03-09 | 402 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 12 | 13.8 | Adapters tested with provider sandboxes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36364 | 0.47727 | 0.15909 | 0 | 0 | 0 | 0 | 0 | 0 | 0
410 | 7.2.10 | 3 | Subtask | Reports, dashboards, notices and templates (all active languages) | Phase 4 | 8 Payroll & HR | BE | 330 | 26 | 2028-02-07 | 2028-03-13 | 404 | 0 | 2 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11.5 | Reports and templates | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65385 | 0.34615 | 0 | 0 | 0 | 0 | 0 | 0 | 0
411 | 7.2.11 | 3 | Subtask | Data migration: employee master and service books | Phase 4 | 8 Payroll & HR | DATA | 304 | 59 | 2027-12-31 | 2028-03-22 | 402 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 13 | 14.95 | Migration scripts and reconciliation report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.016949 | 0.35593 | 0.35593 | 0.27119 | 0 | 0 | 0 | 0 | 0 | 0 | 0
412 | 7.2.12 | 3 | Subtask | System integration testing | Phase 4 | 8 Payroll & HR | QA | 346 | 21 | 2028-02-29 | 2028-03-28 | 404,406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 19 | 21.85 | SIT report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0.95238 | 0 | 0 | 0 | 0 | 0 | 0 | 0
413 | 7.2.13 | 3 | Subtask | Defect fixing and regression | Phase 4 | 8 Payroll & HR | BE | 350 | 26 | 2028-03-06 | 2028-04-10 | 412 | 0 | 0 | 0 | 8 | 5 | 0 | 0 | 0 | 4 | 0 | 0 | 17 | 19.55 | Closed defects | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.76923 | 0.23077 | 0 | 0 | 0 | 0 | 0 | 0
414 | 7.2.14 | 3 | Subtask | UAT support with GWMC department | Phase 4 | 8 Payroll & HR | BA | 367 | 13 | 2028-03-29 | 2028-04-14 | 412 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 10 | 11.5 | UAT sign-off | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23077 | 0.76923 | 0 | 0 | 0 | 0 | 0 | 0
415 | 7.2.15 | 3 | Subtask | Training material and department training | Phase 4 | 8 Payroll & HR | TRN | 370 | 13 | 2028-04-03 | 2028-04-19 | 414 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 9.2 | Trained users, manuals in Telugu and English | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
416 | 7.3 | 2 | Task | Module 15: Municipal Property Management | Phase 4 | 15 Municipal Property |  |  | 119 | 2027-11-05 | 2028-04-19 |  | 1 | 21 | 6 | 61 | 30 | 9 | 8 | 0 | 22 | 9 | 4 | 171 | 196.65 | 15 processes, 15 requirements (MPM) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
417 | 7.3.1 | 3 | Subtask | Process validation workshops and to-be sign-off | Phase 4 | 15 Municipal Property | BA | 264 | 16 | 2027-11-05 | 2027-11-26 | 394 | 1 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 10.35 | Signed process maps | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
418 | 7.3.2 | 3 | Subtask | LLD, data model and API/event contracts | Phase 4 | 15 Municipal Property | ARC | 275 | 16 | 2027-11-22 | 2027-12-13 | 417 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9.2 | LLD, OpenAPI, schemas | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4375 | 0.5625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
419 | 7.3.3 | 3 | Subtask | UX wireframes and UI design | Phase 4 | 15 Municipal Property | FE | 275 | 16 | 2027-11-22 | 2027-12-13 | 417 | 0 | 2 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6.9 | Approved wireframes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4375 | 0.5625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
420 | 7.3.4 | 3 | Subtask | Database schema, domain logic and APIs | Phase 4 | 15 Municipal Property | BE | 288 | 55 | 2027-12-09 | 2028-02-23 | 418 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 25.3 | Service build | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30909 | 0.38182 | 0.30909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
421 | 7.3.5 | 3 | Subtask | Workflows (BPMN) and rules (DMN) configuration | Phase 4 | 15 Municipal Property | BE | 304 | 40 | 2027-12-31 | 2028-02-24 | 418 | 0 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 12.65 | Deployed workflows and decision tables | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025 | 0.525 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
422 | 7.3.6 | 3 | Subtask | Staff console screens | Phase 4 | 15 Municipal Property | FE | 297 | 53 | 2027-12-22 | 2028-03-03 | 419 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 21.85 | Staff screens | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15094 | 0.39623 | 0.39623 | 0.056604 | 0 | 0 | 0 | 0 | 0 | 0 | 0
423 | 7.3.7 | 3 | Subtask | Field app tasks (offline) | Phase 4 | 15 Municipal Property | MOB | 310 | 40 | 2028-01-10 | 2028-03-03 | 419 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 9 | 10.35 | Field app plug-in | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.525 | 0.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0
424 | 7.3.8 | 3 | Subtask | GIS layers, map views and spatial checks | Phase 4 | 15 Municipal Property | GIS | 297 | 46 | 2027-12-22 | 2028-02-23 | 418 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 8 | 9.2 | Layers and map features | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17391 | 0.45652 | 0.36957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
425 | 7.3.9 | 3 | Subtask | Module interfaces (12 I-xx links): events and APIs | Phase 4 | 15 Municipal Property | BE | 317 | 37 | 2028-01-19 | 2028-03-09 | 420 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 20.7 | Contract-tested interfaces | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24324 | 0.56757 | 0.18919 | 0 | 0 | 0 | 0 | 0 | 0 | 0
426 | 7.3.10 | 3 | Subtask | Reports, dashboards, notices and templates (all active languages) | Phase 4 | 15 Municipal Property | BE | 330 | 26 | 2028-02-07 | 2028-03-13 | 420 | 0 | 2 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9.2 | Reports and templates | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65385 | 0.34615 | 0 | 0 | 0 | 0 | 0 | 0 | 0
427 | 7.3.11 | 3 | Subtask | Data migration: asset and lease registers | Phase 4 | 15 Municipal Property | DATA | 304 | 59 | 2027-12-31 | 2028-03-22 | 418 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 11 | 12.65 | Migration scripts and reconciliation report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.016949 | 0.35593 | 0.35593 | 0.27119 | 0 | 0 | 0 | 0 | 0 | 0 | 0
428 | 7.3.12 | 3 | Subtask | System integration testing | Phase 4 | 15 Municipal Property | QA | 346 | 21 | 2028-02-29 | 2028-03-28 | 420,422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 15 | 17.25 | SIT report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0.95238 | 0 | 0 | 0 | 0 | 0 | 0 | 0
429 | 7.3.13 | 3 | Subtask | Defect fixing and regression | Phase 4 | 15 Municipal Property | BE | 350 | 26 | 2028-03-06 | 2028-04-10 | 428 | 0 | 0 | 0 | 6 | 4 | 0 | 0 | 0 | 3 | 0 | 0 | 13 | 14.95 | Closed defects | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.76923 | 0.23077 | 0 | 0 | 0 | 0 | 0 | 0
430 | 7.3.14 | 3 | Subtask | UAT support with GWMC department | Phase 4 | 15 Municipal Property | BA | 367 | 13 | 2028-03-29 | 2028-04-14 | 428 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 8 | 9.2 | UAT sign-off | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23077 | 0.76923 | 0 | 0 | 0 | 0 | 0 | 0
431 | 7.3.15 | 3 | Subtask | Training material and department training | Phase 4 | 15 Municipal Property | TRN | 370 | 13 | 2028-04-03 | 2028-04-19 | 430 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 6.9 | Trained users, manuals in Telugu and English | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
432 | 7.4 | 2 | Task | Module 16: Legal Case Management | Phase 4 | 16 Legal Cases |  |  | 119 | 2027-11-05 | 2028-04-19 |  | 1 | 22 | 6 | 59 | 33 | 0 | 0 | 0 | 25 | 10 | 5 | 161 | 185.15 | 17 processes, 17 requirements (LGL) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
433 | 7.4.1 | 3 | Subtask | Process validation workshops and to-be sign-off | Phase 4 | 16 Legal Cases | BA | 264 | 16 | 2027-11-05 | 2027-11-26 | 394 | 1 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11.5 | Signed process maps | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
434 | 7.4.2 | 3 | Subtask | LLD, data model and API/event contracts | Phase 4 | 16 Legal Cases | ARC | 275 | 16 | 2027-11-22 | 2027-12-13 | 433 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9.2 | LLD, OpenAPI, schemas | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4375 | 0.5625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
435 | 7.4.3 | 3 | Subtask | UX wireframes and UI design | Phase 4 | 16 Legal Cases | FE | 275 | 16 | 2027-11-22 | 2027-12-13 | 433 | 0 | 2 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8.05 | Approved wireframes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4375 | 0.5625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
436 | 7.4.4 | 3 | Subtask | Database schema, domain logic and APIs | Phase 4 | 16 Legal Cases | BE | 288 | 55 | 2027-12-09 | 2028-02-23 | 434 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 29.9 | Service build | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30909 | 0.38182 | 0.30909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
437 | 7.4.5 | 3 | Subtask | Workflows (BPMN) and rules (DMN) configuration | Phase 4 | 16 Legal Cases | BE | 304 | 40 | 2027-12-31 | 2028-02-24 | 434 | 0 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 12.65 | Deployed workflows and decision tables | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025 | 0.525 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
438 | 7.4.6 | 3 | Subtask | Staff console screens | Phase 4 | 16 Legal Cases | FE | 297 | 53 | 2027-12-22 | 2028-03-03 | 435 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 24.15 | Staff screens | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15094 | 0.39623 | 0.39623 | 0.056604 | 0 | 0 | 0 | 0 | 0 | 0 | 0
439 | 7.4.7 | 3 | Subtask | Module interfaces (4 I-xx links): events and APIs | Phase 4 | 16 Legal Cases | BE | 317 | 37 | 2028-01-19 | 2028-03-09 | 436 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6.9 | Contract-tested interfaces | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24324 | 0.56757 | 0.18919 | 0 | 0 | 0 | 0 | 0 | 0 | 0
440 | 7.4.8 | 3 | Subtask | External system adapters (1) | Phase 4 | 16 Legal Cases | BE | 310 | 44 | 2028-01-10 | 2028-03-09 | 434 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 6 | 6.9 | Adapters tested with provider sandboxes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36364 | 0.47727 | 0.15909 | 0 | 0 | 0 | 0 | 0 | 0 | 0
441 | 7.4.9 | 3 | Subtask | Reports, dashboards, notices and templates (all active languages) | Phase 4 | 16 Legal Cases | BE | 330 | 26 | 2028-02-07 | 2028-03-13 | 436 | 0 | 2 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9.2 | Reports and templates | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65385 | 0.34615 | 0 | 0 | 0 | 0 | 0 | 0 | 0
442 | 7.4.10 | 3 | Subtask | Data migration: pending court cases | Phase 4 | 16 Legal Cases | DATA | 304 | 59 | 2027-12-31 | 2028-03-22 | 434 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 12 | 13.8 | Migration scripts and reconciliation report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.016949 | 0.35593 | 0.35593 | 0.27119 | 0 | 0 | 0 | 0 | 0 | 0 | 0
443 | 7.4.11 | 3 | Subtask | System integration testing | Phase 4 | 16 Legal Cases | QA | 346 | 21 | 2028-02-29 | 2028-03-28 | 436,438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 17 | 19.55 | SIT report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0.95238 | 0 | 0 | 0 | 0 | 0 | 0 | 0
444 | 7.4.12 | 3 | Subtask | Defect fixing and regression | Phase 4 | 16 Legal Cases | BE | 350 | 26 | 2028-03-06 | 2028-04-10 | 443 | 0 | 0 | 0 | 7 | 4 | 0 | 0 | 0 | 3 | 0 | 0 | 14 | 16.1 | Closed defects | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.76923 | 0.23077 | 0 | 0 | 0 | 0 | 0 | 0
445 | 7.4.13 | 3 | Subtask | UAT support with GWMC department | Phase 4 | 16 Legal Cases | BA | 367 | 13 | 2028-03-29 | 2028-04-14 | 443 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 8 | 9.2 | UAT sign-off | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23077 | 0.76923 | 0 | 0 | 0 | 0 | 0 | 0
446 | 7.4.14 | 3 | Subtask | Training material and department training | Phase 4 | 16 Legal Cases | TRN | 370 | 13 | 2028-04-03 | 2028-04-19 | 445 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 7 | 8.05 | Trained users, manuals in Telugu and English | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
447 | 7.5 | 2 | Task | Module 19: Government Schemes Management | Phase 4 | 19 Government Schemes |  |  | 119 | 2027-11-05 | 2028-04-19 |  | 1 | 17 | 5 | 59 | 37 | 12 | 0 | 0 | 23 | 8 | 4 | 166 | 190.9 | 14 processes, 14 requirements (GSC) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
448 | 7.5.1 | 3 | Subtask | Process validation workshops and to-be sign-off | Phase 4 | 19 Government Schemes | BA | 264 | 16 | 2027-11-05 | 2027-11-26 | 394 | 1 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9.2 | Signed process maps | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
449 | 7.5.2 | 3 | Subtask | LLD, data model and API/event contracts | Phase 4 | 19 Government Schemes | ARC | 275 | 16 | 2027-11-22 | 2027-12-13 | 448 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9.2 | LLD, OpenAPI, schemas | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4375 | 0.5625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
450 | 7.5.3 | 3 | Subtask | UX wireframes and UI design | Phase 4 | 19 Government Schemes | FE | 275 | 16 | 2027-11-22 | 2027-12-13 | 448 | 0 | 1 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5.75 | Approved wireframes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4375 | 0.5625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
451 | 7.5.4 | 3 | Subtask | Database schema, domain logic and APIs | Phase 4 | 19 Government Schemes | BE | 288 | 55 | 2027-12-09 | 2028-02-23 | 449 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 24.15 | Service build | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30909 | 0.38182 | 0.30909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
452 | 7.5.5 | 3 | Subtask | Workflows (BPMN) and rules (DMN) configuration | Phase 4 | 19 Government Schemes | BE | 304 | 40 | 2027-12-31 | 2028-02-24 | 449 | 0 | 3 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11.5 | Deployed workflows and decision tables | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.025 | 0.525 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
453 | 7.5.6 | 3 | Subtask | Staff console screens | Phase 4 | 19 Government Schemes | FE | 297 | 53 | 2027-12-22 | 2028-03-03 | 450 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 20.7 | Staff screens | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15094 | 0.39623 | 0.39623 | 0.056604 | 0 | 0 | 0 | 0 | 0 | 0 | 0
454 | 7.5.7 | 3 | Subtask | Citizen portal and app services | Phase 4 | 19 Government Schemes | FE | 310 | 40 | 2028-01-10 | 2028-03-03 | 450 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 12 | 13.8 | Citizen services live in MyGWMC | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.525 | 0.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0
455 | 7.5.8 | 3 | Subtask | Field app tasks (offline) | Phase 4 | 19 Government Schemes | MOB | 310 | 40 | 2028-01-10 | 2028-03-03 | 450 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 9.2 | Field app plug-in | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.525 | 0.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0
456 | 7.5.9 | 3 | Subtask | Module interfaces (5 I-xx links): events and APIs | Phase 4 | 19 Government Schemes | BE | 317 | 37 | 2028-01-19 | 2028-03-09 | 451 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9.2 | Contract-tested interfaces | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24324 | 0.56757 | 0.18919 | 0 | 0 | 0 | 0 | 0 | 0 | 0
457 | 7.5.10 | 3 | Subtask | External system adapters (2) | Phase 4 | 19 Government Schemes | BE | 310 | 44 | 2028-01-10 | 2028-03-09 | 449 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 12 | 13.8 | Adapters tested with provider sandboxes | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36364 | 0.47727 | 0.15909 | 0 | 0 | 0 | 0 | 0 | 0 | 0
458 | 7.5.11 | 3 | Subtask | Reports, dashboards, notices and templates (all active languages) | Phase 4 | 19 Government Schemes | BE | 330 | 26 | 2028-02-07 | 2028-03-13 | 451 | 0 | 1 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8.05 | Reports and templates | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65385 | 0.34615 | 0 | 0 | 0 | 0 | 0 | 0 | 0
459 | 7.5.12 | 3 | Subtask | Data migration: existing beneficiaries | Phase 4 | 19 Government Schemes | DATA | 304 | 59 | 2027-12-31 | 2028-03-22 | 449 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 9 | 10.35 | Migration scripts and reconciliation report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.016949 | 0.35593 | 0.35593 | 0.27119 | 0 | 0 | 0 | 0 | 0 | 0 | 0
460 | 7.5.13 | 3 | Subtask | System integration testing | Phase 4 | 19 Government Schemes | QA | 346 | 21 | 2028-02-29 | 2028-03-28 | 451,453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 14 | 16.1 | SIT report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0.95238 | 0 | 0 | 0 | 0 | 0 | 0 | 0
461 | 7.5.14 | 3 | Subtask | Defect fixing and regression | Phase 4 | 19 Government Schemes | BE | 350 | 26 | 2028-03-06 | 2028-04-10 | 460 | 0 | 0 | 0 | 6 | 4 | 0 | 0 | 0 | 3 | 0 | 0 | 13 | 14.95 | Closed defects | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.76923 | 0.23077 | 0 | 0 | 0 | 0 | 0 | 0
462 | 7.5.15 | 3 | Subtask | UAT support with GWMC department | Phase 4 | 19 Government Schemes | BA | 367 | 13 | 2028-03-29 | 2028-04-14 | 460 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 8 | 9.2 | UAT sign-off | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23077 | 0.76923 | 0 | 0 | 0 | 0 | 0 | 0
463 | 7.5.16 | 3 | Subtask | Training material and department training | Phase 4 | 19 Government Schemes | TRN | 370 | 13 | 2028-04-03 | 2028-04-19 | 462 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 5.75 | Trained users, manuals in Telugu and English | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
464 | 7.6 | 2 | Task | Phase 4 release, testing and go-live | Phase 4 | Release |  |  | 27 | 2028-03-17 | 2028-04-24 |  | 0 | 11 | 3 | 24 | 0 | 0 | 0 | 16 | 35 | 12 | 15 | 116 | 133.4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
465 | 7.6.1 | 3 | Subtask | End-to-end integration testing (SRS E2E scenarios) | Phase 4 | Release | QA | 359 | 13 | 2028-03-17 | 2028-04-04 | 412,428,443,460 | 0 | 4 | 0 | 6 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 30 | 34.5 | E2E report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84615 | 0.15385 | 0 | 0 | 0 | 0 | 0 | 0
466 | 7.6.2 | 3 | Subtask | Performance and load testing (NFR-001/002) | Phase 4 | Release | QA | 363 | 9 | 2028-03-23 | 2028-04-04 |  | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 8 | 0 | 0 | 16 | 18.4 | Performance report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77778 | 0.22222 | 0 | 0 | 0 | 0 | 0 | 0
467 | 7.6.3 | 3 | Subtask | Security audit by CERT-In empanelled auditor and fixes | Phase 4 | Release | QA | 367 | 13 | 2028-03-29 | 2028-04-14 |  | 0 | 0 | 3 | 10 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 21 | 24.15 | Audit certificate | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23077 | 0.76923 | 0 | 0 | 0 | 0 | 0 | 0
468 | 7.6.4 | 3 | Subtask | Training of trainers and end-user training programme | Phase 4 | Release | TRN | 372 | 13 | 2028-04-05 | 2028-04-21 |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 20 | 23 | Training attendance and feedback | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
469 | 7.6.5 | 3 | Subtask | Migration dress rehearsal and cut-over plan | Phase 4 | Release | DATA | 375 | 8 | 2028-04-10 | 2028-04-19 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 8 | 0 | 13 | 14.95 | Cut-over runbook | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
470 | 7.6.6 | 3 | Subtask | Production deployment and cut-over | Phase 4 | Release | DEV | 383 | 3 | 2028-04-20 | 2028-04-24 | 467,469,414,430,445,462 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 5 | 3 | 4 | 0 | 16 | 18.4 | Go-live | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
471 | 7.7 | 2 | Milestone | M4: Phase 4 go-live | Phase 4 |  |  | 385 | 0 | 2028-04-24 | 2028-04-24 | 470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
472 | 7.7.1 | 3 | Subtask | Hypercare and stabilisation (4 weeks) | Phase 4 | Release | BE | 385 | 20 | 2028-04-24 | 2028-05-19 | 471 | 0 | 5 | 0 | 12 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 29 | 33.35 | Hypercare closure report | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.75 | 0 | 0 | 0 | 0 | 0
473 | 7.8 | 2 | Milestone | Phase 4 acceptance and sign-off | Phase 4 |  |  | 405 | 0 | 2028-05-22 | 2028-05-22 | 472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
474 | 7.9 | 2 | Milestone | Phase 4 build mid-point (next phase design may start) | Phase 4 |  |  | 330 | 0 | 2028-02-07 | 2028-02-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
475 | 8 | 1 | Phase | Programme close | Close |  |  |  | 1 | 2028-07-10 | 2028-07-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
476 | 8.1 | 2 | Milestone | Programme completion and handover to operations | Close |  |  | 440 | 0 | 2028-07-10 | 2028-07-10 | 473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Not started |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Team Summary
Effort by team role (person-days)
From subtask estimates in the Project Plan. Contingency and day rates come from the Assumptions sheet.
By phase
Group | PM | BA | ARC | BE | FE | MOB | GIS | DEV | QA | DATA | TRN | Total | With contingency | Cost (optional)
All | 345 | 30 | 89 | 30 | 0 | 0 | 0 | 15 | 8 | 0 | 10 | 527 | 606.05 | 0
Phase 0 | 18 | 50 | 30 | 3 | 15 | 0 | 0 | 34 | 0 | 10 | 0 | 160 | 184 | 0
Phase 1 | 5 | 228 | 116 | 1013 | 499 | 129 | 82 | 115 | 409 | 98 | 63 | 2757 | 3170.55 | 0
Phase 2 | 5 | 153 | 42 | 558 | 303 | 102 | 88 | 20 | 229 | 73 | 49 | 1622 | 1865.3 | 0
Phase 3 | 5 | 114 | 32 | 399 | 184 | 57 | 39 | 24 | 179 | 15 | 40 | 1088 | 1251.2 | 0
Phase 4 | 4 | 101 | 27 | 306 | 151 | 32 | 8 | 20 | 147 | 66 | 34 | 896 | 1030.4 | 0
Total | 382 | 676 | 336 | 2309 | 1152 | 320 | 217 | 228 | 972 | 262 | 196 | 7050 | 8107.5 | 0
By module (Platform, modules, release activities; blank = governance and inception)
Group | PM | BA | ARC | BE | FE | MOB | GIS | DEV | QA | DATA | TRN | Total | With contingency | Cost (optional)
Platform | 0 | 15 | 56 | 371 | 111 | 59 | 68 | 99 | 134 | 31 | 0 | 944 | 1085.6 | 0
1 Property Tax | 1 | 46 | 13 | 160 | 92 | 32 | 18 | 0 | 59 | 21 | 11 | 453 | 520.95 | 0
2 Water & Sewerage | 1 | 40 | 11 | 131 | 87 | 30 | 17 | 0 | 51 | 20 | 10 | 398 | 457.7 | 0
3 Citizen Desk & RTI | 1 | 35 | 11 | 124 | 79 | 9 | 15 | 0 | 50 | 0 | 9 | 333 | 382.95 | 0
4 Finance & Accounting | 1 | 38 | 11 | 126 | 61 | 0 | 0 | 0 | 49 | 18 | 9 | 313 | 359.95 | 0
9 Document Management | 1 | 38 | 11 | 116 | 79 | 9 | 0 | 0 | 49 | 18 | 9 | 330 | 379.5 | 0
5 Trade Licence | 1 | 33 | 9 | 103 | 67 | 24 | 13 | 0 | 40 | 16 | 8 | 314 | 361.1 | 0
6 User Charges | 1 | 27 | 8 | 92 | 59 | 21 | 11 | 0 | 34 | 14 | 7 | 274 | 315.1 | 0
11 Building Permission | 1 | 28 | 8 | 138 | 61 | 21 | 12 | 0 | 45 | 14 | 7 | 335 | 385.25 | 0
13 Town Planning | 1 | 28 | 8 | 98 | 61 | 21 | 12 | 0 | 38 | 14 | 7 | 288 | 331.2 | 0
18 Fire NOC | 1 | 21 | 6 | 81 | 45 | 15 | 9 | 0 | 29 | 0 | 5 | 212 | 243.8 | 0
7 Solid Waste | 1 | 21 | 6 | 86 | 35 | 11 | 9 | 0 | 29 | 0 | 5 | 203 | 233.45 | 0
10 Engineering Projects | 1 | 23 | 7 | 82 | 41 | 12 | 10 | 0 | 31 | 0 | 6 | 213 | 244.95 | 0
12 Street Lights | 1 | 13 | 4 | 57 | 25 | 8 | 6 | 0 | 19 | 0 | 4 | 137 | 157.55 | 0
14 Parks & Horticulture | 1 | 21 | 6 | 60 | 46 | 16 | 9 | 0 | 26 | 0 | 5 | 190 | 218.5 | 0
17 Inventory & Stores | 1 | 20 | 6 | 57 | 33 | 0 | 0 | 0 | 25 | 0 | 5 | 147 | 169.05 | 0
8 Payroll & HR | 1 | 25 | 7 | 71 | 39 | 11 | 0 | 0 | 30 | 11 | 6 | 201 | 231.15 | 0
15 Municipal Property | 1 | 21 | 6 | 61 | 30 | 9 | 8 | 0 | 22 | 9 | 4 | 171 | 196.65 | 0
16 Legal Cases | 1 | 22 | 6 | 59 | 33 | 0 | 0 | 0 | 25 | 10 | 5 | 161 | 185.15 | 0
19 Government Schemes | 1 | 17 | 5 | 59 | 37 | 12 | 0 | 0 | 23 | 8 | 4 | 166 | 190.9 | 0
Release | 0 | 64 | 12 | 144 | 16 | 0 | 0 | 80 | 156 | 48 | 60 | 580 | 667 | 0
| 363 | 80 | 119 | 33 | 15 | 0 | 0 | 49 | 8 | 10 | 10 | 687 | 790.05 | 0
Total | 382 | 676 | 336 | 2309 | 1152 | 320 | 217 | 228 | 972 | 262 | 196 | 7050 | 8107.5 | 0
Check: totals by phase and by module must match |  |  |  |  | OK

## Resource Loading
Staff needed per month (full-time equivalents)
FTE = person-days scheduled in the month / working days in the month. Includes contingency. Use it to plan hiring and team ramp-up.
Month | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01
Working days | 21 | 23 | 21 | 20 | 23 | 22 | 21 | 22 | 22 | 22 | 22 | 21 | 22 | 23 | 21 | 21 | 23 | 20 | 23 | 22 | 21 | 23 | 21 | 22
PM Project manager | 1.5057 | 0.93527 | 0.6325 | 0.6325 | 1.402 | 1.2576 | 0.95639 | 0.68258 | 1.4441 | 1.2617 | 0.99844 | 0.68258 | 1.3655 | 1.2617 | 1.0135 | 0.68258 | 0.68258 | 0.68258 | 0.94266 | 0.8808 | 0.20536 | 0 | 0 | 0
BA Business analyst | 2.7288 | 4.3741 | 1.2066 | 1.822 | 3.7414 | 3.7194 | 1.0552 | 1.1641 | 3.024 | 2.3455 | 0.70307 | 0.79436 | 2.1919 | 1.9766 | 0.73198 | 0.76494 | 0.63895 | 1.7217 | 0.4075 | 0.3058 | 0.068452 | 0 | 0 | 0
ARC Solution / technical architect | 2.6922 | 4.4619 | 0.48875 | 0.3335 | 1.6048 | 1.0715 | 0.22836 | 0.1736 | 1.3136 | 0.91908 | 0.23588 | 0.1736 | 1.0579 | 0.8813 | 0.23885 | 0.1736 | 0.20822 | 0.30629 | 0.3603 | 0.4404 | 0.10268 | 0 | 0 | 0
BE Backend developer | 0.96406 | 10.339 | 15.8523 | 17.3006 | 8.4439 | 6.0844 | 9.2483 | 10.2118 | 4.6832 | 4.3989 | 6.3528 | 6.7477 | 3.4518 | 3.7158 | 4.7651 | 4.9407 | 2.3466 | 1.3073 | 0.9375 | 0.8625 | 0.20536 | 0 | 0 | 0
FE Frontend developer | 0.66992 | 4.8542 | 7.4514 | 8.6843 | 6.0187 | 2.9052 | 4.8662 | 5.9192 | 2.3862 | 1.8628 | 2.6915 | 3.2825 | 1.7874 | 1.6199 | 2.2418 | 2.549 | 1.1409 | 0.28308 | 0.15 | 0 | 0 | 0 | 0 | 0
MOB Mobile developer | 0 | 0.70324 | 2.5522 | 2.8466 | 0.94118 | 0 | 2.3739 | 2.9325 | 0.18645 | 0.19492 | 1.2391 | 1.4348 | 0.12284 | 0 | 0.70095 | 0.92 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GIS GIS engineer | 0 | 0.8 | 2.0697 | 1.4744 | 0.3121 | 1.1872 | 2.0292 | 1.2836 | 0.026579 | 0.40655 | 0.94746 | 0.68939 | 0 | 0.069565 | 0.2 | 0.1619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DEV DevOps / infrastructure | 1.9125 | 1.6232 | 2.13 | 1.3063 | 0.11818 | 0.79891 | 0.12885 | 0 | 0.27146 | 0.74777 | 0.20342 | 0.033414 | 0.21088 | 0.67829 | 0.13143 | 0 | 0.20171 | 0.74553 | 0.39375 | 0.43125 | 0.10268 | 0 | 0 | 0
QA QA / test engineer | 0 | 0.225 | 3.6132 | 3.2093 | 10.7015 | 3.6115 | 0.6818 | 1.4627 | 8.1389 | 1.9822 | 0.51261 | 0.7666 | 6.3261 | 1.7786 | 0.41759 | 0.4051 | 5.0653 | 1.6412 | 0.16333 | 0 | 0 | 0 | 0 | 0
DATA Data migration engineer | 0.40159 | 0.13333 | 1.0554 | 2.1543 | 1.4808 | 0.78852 | 1.189 | 1.1544 | 0.73536 | 0.68575 | 0.058475 | 0.025061 | 0.070878 | 0.94407 | 1.0525 | 0.88918 | 0.51525 | 0.69 | 0 | 0 | 0 | 0 | 0 | 0
TRN Trainer / change manager | 0 | 0 | 0 | 0 | 0 | 3.2932 | 0 | 0 | 0.13671 | 2.4247 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1.955 | 0.1625 | 0.2875 | 0.068452 | 0 | 0 | 0
Total FTE | 10.8746 | 28.4493 | 37.0521 | 39.7637 | 34.7646 | 24.7174 | 22.7572 | 24.9845 | 22.3465 | 17.2297 | 13.9427 | 14.6299 | 16.5852 | 14.9258 | 11.4937 | 11.487 | 10.9195 | 9.3326 | 3.5175 | 3.2082 | 0.75298 | 0 | 0 | 0
Peak team size | 39.7637
Check: scheduled effort vs plan total | 8107.5 | 8107.5 | OK

## Milestones
Milestones
ID | Milestone | Phase | Date
23 | M0: Inception complete, Phase 1 build starts | Phase 0 | 2026-12-07
193 | M1: Phase 1 go-live | Phase 1 | 2027-04-22
195 | Phase 1 acceptance and sign-off | Phase 1 | 2027-05-14
297 | M2: Phase 2 go-live | Phase 2 | 2027-08-20
299 | Phase 2 acceptance and sign-off | Phase 2 | 2027-09-17
391 | M3: Phase 3 go-live | Phase 3 | 2027-12-22
393 | Phase 3 acceptance and sign-off | Phase 3 | 2028-01-19
471 | M4: Phase 4 go-live | Phase 4 | 2028-04-24
473 | Phase 4 acceptance and sign-off | Phase 4 | 2028-05-22
476 | Programme completion and handover to operations | Close | 2028-07-10

## Planner Import
Title | Bucket | Start Date | Due Date | Label (team) | Effort (pd) | Priority | Progress | Notes
1.1.1 PMO, planning, status reporting and steering committee: Phase 1 | All - Project governance and PMO | 2026-11-02 | 2027-05-14 | PM | 96.6 | Medium | Not started | Task: Project governance and PMO. Deliverable: Weekly status, monthly steering minutes, RAID log
1.1.2 PMO, planning, status reporting and steering committee: Phase 2 | All - Project governance and PMO | 2027-03-04 | 2027-09-16 | PM | 97.75 | Medium | Not started | Task: Project governance and PMO. Deliverable: Weekly status, monthly steering minutes, RAID log
1.1.3 PMO, planning, status reporting and steering committee: Phase 3 | All - Project governance and PMO | 2027-07-06 | 2028-01-18 | PM | 97.75 | Medium | Not started | Task: Project governance and PMO. Deliverable: Weekly status, monthly steering minutes, RAID log
1.1.4 PMO, planning, status reporting and steering committee: Phase 4 | All - Project governance and PMO | 2027-11-05 | 2028-05-19 | PM | 97.75 | Medium | Not started | Task: Project governance and PMO. Deliverable: Weekly status, monthly steering minutes, RAID log
1.1.5 Final stabilisation, knowledge transfer and handover | All - Project governance and PMO | 2028-05-15 | 2028-07-07 | PM | 126.5 | Medium | Not started | Task: Project governance and PMO. Deliverable: Handover pack, runbooks, KT sign-off
1.2.1 Change request process and impact assessments (whole programme) | All - Change control and quality | 2026-11-30 | 2028-06-09 | PM | 57.5 | Medium | Not started | Task: Change control and quality. Deliverable: CR register
1.2.2 Quality audits and phase-gate reviews (4 gates) | All - Change control and quality | 2027-03-22 | 2028-05-12 | PM | 32.2 | Medium | Not started | Task: Change control and quality. Deliverable: Gate review reports
2.1.1 Kick-off with GWMC and team onboarding | Phase 0 - Mobilisation | 2026-11-02 | 2026-11-06 | PM | 14.95 | Medium | Not started | Task: Mobilisation. Deliverable: Kick-off deck, project charter
2.1.2 Tooling: repositories, CI/CD, tracker, Teams workspace | Phase 0 - Mobilisation | 2026-11-02 | 2026-11-13 | DEV | 17.25 | Medium | Not started | Task: Mobilisation. Deliverable: Working toolchain
2.1.3 Dev and test environments provisioned | Phase 0 - Mobilisation | 2026-11-05 | 2026-11-25 | DEV | 20.7 | Medium | Not started | Task: Mobilisation. Deliverable: Dev and test clusters
2.1.4 State Data Centre slot request and network approvals | Phase 0 - Mobilisation | 2026-11-02 | 2026-12-04 | PM | 13.8 | Medium | Not started | Task: Mobilisation. Deliverable: SDC allocation letter
2.2.1 SRS walkthroughs with GWMC departments (Phase 1 modules) | Phase 0 - Requirements and design baseline | 2026-11-09 | 2026-11-27 | BA | 39.1 | Medium | Not started | Task: Requirements and design baseline. Deliverable: Workshop minutes, clarifications
2.2.2 GWMC Deployment SRS open items closed for Phase 1 | Phase 0 - Requirements and design baseline | 2026-11-16 | 2026-12-04 | BA | 17.25 | Medium | Not started | Task: Requirements and design baseline. Deliverable: Signed open-items list
2.2.3 Architecture decisions (ADR-001 to 016) reviewed and signed off | Phase 0 - Requirements and design baseline | 2026-11-09 | 2026-11-27 | ARC | 20.7 | Medium | Not started | Task: Requirements and design baseline. Deliverable: Signed ADRs
2.2.4 UX research, design system and accessibility baseline | Phase 0 - Requirements and design baseline | 2026-11-09 | 2026-12-04 | FE | 21.85 | Medium | Not started | Task: Requirements and design baseline. Deliverable: Design system, UI kit, GIGW checklist
2.2.5 Data migration strategy and legacy data assessment | Phase 0 - Requirements and design baseline | 2026-11-16 | 2026-12-04 | DATA | 18.4 | Medium | Not started | Task: Requirements and design baseline. Deliverable: Migration strategy
2.3 M0: Inception complete, Phase 1 build starts | Phase 0 - Phase 0: Inception and mobilisation | 2026-12-07 | 2026-12-07 | 0 | 0 | Important | Not started | Task: Phase 0: Inception and mobilisation. Deliverable:
3.1.1 Detailed design and contracts | Phase 1 - Platform | 2026-11-16 | 2026-11-27 | ARC | 8.05 | Medium | Not started | Task: Identity, OTP, CAPTCHA and step-up (Keycloak). Deliverable: Design note, OpenAPI and event schemas
3.1.2 Build and unit tests | Phase 1 - Platform | 2026-11-30 | 2027-01-08 | BE | 43.7 | Medium | Not started | Task: Identity, OTP, CAPTCHA and step-up (Keycloak). Deliverable: Working service
3.1.3 Component, security and contract tests | Phase 1 - Platform | 2027-01-07 | 2027-01-25 | QA | 14.95 | Medium | Not started | Task: Identity, OTP, CAPTCHA and step-up (Keycloak). Deliverable: Test report
3.2.1 Detailed design and contracts | Phase 1 - Platform | 2026-11-24 | 2026-12-07 | ARC | 5.75 | Medium | Not started | Task: Tenant, configuration console and Telangana state pack. Deliverable: Design note, OpenAPI and event schemas
3.2.2 Build and unit tests | Phase 1 - Platform | 2026-12-08 | 2027-01-18 | BE | 49.45 | Medium | Not started | Task: Tenant, configuration console and Telangana state pack. Deliverable: Working service
3.2.3 Component, security and contract tests | Phase 1 - Platform | 2027-01-14 | 2027-02-01 | QA | 11.5 | Medium | Not started | Task: Tenant, configuration console and Telangana state pack. Deliverable: Test report
3.3.1 Detailed design and contracts | Phase 1 - Platform | 2026-11-24 | 2026-12-07 | ARC | 8.05 | Medium | Not started | Task: Workflow and rules engine (Flowable BPMN and DMN). Deliverable: Design note, OpenAPI and event schemas
3.3.2 Build and unit tests | Phase 1 - Platform | 2026-12-08 | 2027-01-18 | BE | 39.1 | Medium | Not started | Task: Workflow and rules engine (Flowable BPMN and DMN). Deliverable: Working service
3.3.3 Component, security and contract tests | Phase 1 - Platform | 2027-01-14 | 2027-02-01 | QA | 12.65 | Medium | Not started | Task: Workflow and rules engine (Flowable BPMN and DMN). Deliverable: Test report
3.4.1 Detailed design and contracts | Phase 1 - Platform | 2026-11-16 | 2026-11-25 | ARC | 5.75 | Medium | Not started | Task: API gateway, BFFs and service mesh. Deliverable: Design note, OpenAPI and event schemas
3.4.2 Build and unit tests | Phase 1 - Platform | 2026-11-26 | 2026-12-29 | BE | 26.45 | Medium | Not started | Task: API gateway, BFFs and service mesh. Deliverable: Working service
3.4.3 Component, security and contract tests | Phase 1 - Platform | 2026-12-25 | 2027-01-07 | QA | 6.9 | Medium | Not started | Task: API gateway, BFFs and service mesh. Deliverable: Test report
3.5.1 Detailed design and contracts | Phase 1 - Platform | 2026-11-16 | 2026-11-25 | ARC | 6.9 | Medium | Not started | Task: Event bus, outbox/inbox library and schema registry. Deliverable: Design note, OpenAPI and event schemas
3.5.2 Build and unit tests | Phase 1 - Platform | 2026-11-26 | 2026-12-29 | BE | 24.15 | Medium | Not started | Task: Event bus, outbox/inbox library and schema registry. Deliverable: Working service
3.5.3 Component, security and contract tests | Phase 1 - Platform | 2026-12-25 | 2027-01-07 | QA | 8.05 | Medium | Not started | Task: Event bus, outbox/inbox library and schema registry. Deliverable: Test report
3.6.1 Detailed design and contracts | Phase 1 - Platform | 2026-12-09 | 2026-12-21 | ARC | 5.75 | Medium | Not started | Task: Payment service, gateway, UPI and BBPS. Deliverable: Design note, OpenAPI and event schemas
3.6.2 Build and unit tests | Phase 1 - Platform | 2026-12-22 | 2027-01-27 | BE | 36.8 | Medium | Not started | Task: Payment service, gateway, UPI and BBPS. Deliverable: Working service
3.6.3 Component, security and contract tests | Phase 1 - Platform | 2027-01-25 | 2027-02-08 | QA | 14.95 | Medium | Not started | Task: Payment service, gateway, UPI and BBPS. Deliverable: Test report
3.7.1 Detailed design and contracts | Phase 1 - Platform | 2026-12-09 | 2026-12-18 | ARC | 4.6 | Medium | Not started | Task: Notification service (DLT SMS, WhatsApp, email, IVRS). Deliverable: Design note, OpenAPI and event schemas
3.7.2 Build and unit tests | Phase 1 - Platform | 2026-12-21 | 2027-01-21 | BE | 23 | Medium | Not started | Task: Notification service (DLT SMS, WhatsApp, email, IVRS). Deliverable: Working service
3.7.3 Component, security and contract tests | Phase 1 - Platform | 2027-01-19 | 2027-02-01 | QA | 9.2 | Medium | Not started | Task: Notification service (DLT SMS, WhatsApp, email, IVRS). Deliverable: Test report
3.8.1 Detailed design and contracts | Phase 1 - Platform | 2026-11-24 | 2026-12-08 | ARC | 3.45 | Medium | Not started | Task: GIS base: PostGIS, GeoServer, base map, imagery, ward layers. Deliverable: Design note, OpenAPI and event schemas
3.8.2 Build and unit tests | Phase 1 - Platform | 2026-12-09 | 2027-01-25 | GIS | 55.2 | Medium | Not started | Task: GIS base: PostGIS, GeoServer, base map, imagery, ward layers. Deliverable: Working service
3.8.3 Component, security and contract tests | Phase 1 - Platform | 2027-01-21 | 2027-02-09 | QA | 6.9 | Medium | Not started | Task: GIS base: PostGIS, GeoServer, base map, imagery, ward layers. Deliverable: Test report
3.9.1 Detailed design and contracts | Phase 1 - Platform | 2026-12-01 | 2026-12-15 | ARC | 9.2 | Medium | Not started | Task: Document pipeline: OCR, translation, eSign, anchoring, DigiLocker. Deliverable: Design note, OpenAPI and event schemas
3.9.2 Build and unit tests | Phase 1 - Platform | 2026-12-16 | 2027-02-01 | BE | 41.4 | Medium | Not started | Task: Document pipeline: OCR, translation, eSign, anchoring, DigiLocker. Deliverable: Working service
3.9.3 Component, security and contract tests | Phase 1 - Platform | 2027-01-28 | 2027-02-16 | QA | 16.1 | Medium | Not started | Task: Document pipeline: OCR, translation, eSign, anchoring, DigiLocker. Deliverable: Test report
3.10.1 Detailed design and contracts | Phase 1 - Platform | 2026-12-16 | 2026-12-25 | ARC | 4.6 | Medium | Not started | Task: Search service (OpenSearch, Indic analysers). Deliverable: Design note, OpenAPI and event schemas
3.10.2 Build and unit tests | Phase 1 - Platform | 2026-12-28 | 2027-01-28 | BE | 16.1 | Medium | Not started | Task: Search service (OpenSearch, Indic analysers). Deliverable: Working service
3.10.3 Component, security and contract tests | Phase 1 - Platform | 2027-01-27 | 2027-02-09 | QA | 6.9 | Medium | Not started | Task: Search service (OpenSearch, Indic analysers). Deliverable: Test report
3.11.1 Detailed design and contracts | Phase 1 - Platform | 2026-12-16 | 2026-12-25 | ARC | 3.45 | Medium | Not started | Task: Audit service, SIEM feed and CERT-In logging. Deliverable: Design note, OpenAPI and event schemas
3.11.2 Build and unit tests | Phase 1 - Platform | 2026-12-28 | 2027-01-28 | BE | 20.7 | Medium | Not started | Task: Audit service, SIEM feed and CERT-In logging. Deliverable: Working service
3.11.3 Component, security and contract tests | Phase 1 - Platform | 2027-01-27 | 2027-02-09 | QA | 5.75 | Medium | Not started | Task: Audit service, SIEM feed and CERT-In logging. Deliverable: Test report
3.12.1 Detailed design and contracts | Phase 1 - Platform | 2026-12-16 | 2026-12-24 | ARC | 4.6 | Medium | Not started | Task: Aadhaar Data Vault with HSM. Deliverable: Design note, OpenAPI and event schemas
3.12.2 Build and unit tests | Phase 1 - Platform | 2026-12-25 | 2027-01-21 | BE | 18.4 | Medium | Not started | Task: Aadhaar Data Vault with HSM. Deliverable: Working service
3.12.3 Component, security and contract tests | Phase 1 - Platform | 2027-01-21 | 2027-02-01 | QA | 5.75 | Medium | Not started | Task: Aadhaar Data Vault with HSM. Deliverable: Test report
3.13.1 Detailed design and contracts | Phase 1 - Platform | 2026-12-01 | 2026-12-09 | ARC | 4.6 | Medium | Not started | Task: Adapter hub framework. Deliverable: Design note, OpenAPI and event schemas
3.13.2 Build and unit tests | Phase 1 - Platform | 2026-12-10 | 2027-01-06 | BE | 12.65 | Medium | Not started | Task: Adapter hub framework. Deliverable: Working service
3.13.3 Component, security and contract tests | Phase 1 - Platform | 2027-01-05 | 2027-01-14 | QA | 4.6 | Medium | Not started | Task: Adapter hub framework. Deliverable: Test report
3.14.1 Detailed design and contracts | Phase 1 - Platform | 2026-12-01 | 2026-12-15 | ARC | 2.3 | Medium | Not started | Task: Citizen portal and app shell (MyGWMC branding, 22-language i18n). Deliverable: Design note, OpenAPI and event schemas
3.14.2 Build and unit tests | Phase 1 - Platform | 2026-12-16 | 2027-02-01 | FE | 60.95 | Medium | Not started | Task: Citizen portal and app shell (MyGWMC branding, 22-language i18n). Deliverable: Working service
3.14.3 Component, security and contract tests | Phase 1 - Platform | 2027-01-28 | 2027-02-16 | QA | 11.5 | Medium | Not started | Task: Citizen portal and app shell (MyGWMC branding, 22-language i18n). Deliverable: Test report
3.15.1 Detailed design and contracts | Phase 1 - Platform | 2026-12-01 | 2026-12-11 | ARC | 2.3 | Medium | Not started | Task: Staff console shell, work queues and maps. Deliverable: Design note, OpenAPI and event schemas
3.15.2 Build and unit tests | Phase 1 - Platform | 2026-12-14 | 2027-01-19 | FE | 25.3 | Medium | Not started | Task: Staff console shell, work queues and maps. Deliverable: Working service
3.15.3 Component, security and contract tests | Phase 1 - Platform | 2027-01-18 | 2027-02-01 | QA | 6.9 | Medium | Not started | Task: Staff console shell, work queues and maps. Deliverable: Test report
3.16.1 Detailed design and contracts | Phase 1 - Platform | 2026-12-09 | 2026-12-22 | ARC | 3.45 | Medium | Not started | Task: Field app shell and offline sync service. Deliverable: Design note, OpenAPI and event schemas
3.16.2 Build and unit tests | Phase 1 - Platform | 2026-12-23 | 2027-02-02 | MOB | 43.7 | Medium | Not started | Task: Field app shell and offline sync service. Deliverable: Working service
3.16.3 Component, security and contract tests | Phase 1 - Platform | 2027-02-01 | 2027-02-17 | QA | 10.35 | Medium | Not started | Task: Field app shell and offline sync service. Deliverable: Test report
3.17.1 Detailed design and contracts | Phase 1 - Platform | 2027-01-08 | 2027-01-20 | ARC | 4.6 | Medium | Not started | Task: Reporting warehouse, ELT and Superset dashboards. Deliverable: Design note, OpenAPI and event schemas
3.17.2 Build and unit tests | Phase 1 - Platform | 2027-01-21 | 2027-02-26 | BE | 31.05 | Medium | Not started | Task: Reporting warehouse, ELT and Superset dashboards. Deliverable: Working service
3.17.3 Component, security and contract tests | Phase 1 - Platform | 2027-02-25 | 2027-03-11 | QA | 6.9 | Medium | Not started | Task: Reporting warehouse, ELT and Superset dashboards. Deliverable: Test report
3.18.1 Detailed design and contracts | Phase 1 - Platform | 2026-11-24 | 2026-12-03 | ARC | 2.3 | Medium | Not started | Task: Observability: OpenTelemetry, Prometheus, Grafana, Loki. Deliverable: Design note, OpenAPI and event schemas
3.18.2 Build and unit tests | Phase 1 - Platform | 2026-12-03 | 2027-01-05 | DEV | 17.25 | Medium | Not started | Task: Observability: OpenTelemetry, Prometheus, Grafana, Loki. Deliverable: Working service
3.18.3 Component, security and contract tests | Phase 1 - Platform | 2027-01-04 | 2027-01-15 | QA | 3.45 | Medium | Not started | Task: Observability: OpenTelemetry, Prometheus, Grafana, Loki. Deliverable: Test report
3.19.1 Production cluster in State Data Centre | Phase 1 - Platform | 2026-12-28 | 2027-02-05 | DEV | 24.15 | Medium | Not started | Task: Infrastructure and security (production). Deliverable: Production environment
3.19.2 DR site, replication and backup | Phase 1 - Platform | 2027-01-25 | 2027-02-26 | DEV | 16.1 | Medium | Not started | Task: Infrastructure and security (production). Deliverable: DR environment
3.19.3 HSM, secrets (OpenBao), hardening and network policies | Phase 1 - Platform | 2027-01-11 | 2027-02-12 | DEV | 14.95 | Medium | Not started | Task: Infrastructure and security (production). Deliverable: Hardening checklist
3.19.4 SIEM (Wazuh) and NTP to NIC/NPL time servers | Phase 1 - Platform | 2027-01-25 | 2027-02-19 | DEV | 9.2 | Medium | Not started | Task: Infrastructure and security (production). Deliverable: SIEM live
4.1.1 Process validation workshops and to-be sign-off | Phase 1 - 1 Property Tax | 2026-11-30 | 2026-12-16 | BA | 21.85 | Medium | Not started | Task: Module 1: Property Tax & Revenue Management. Deliverable: Signed process maps
4.1.2 LLD, data model and API/event contracts | Phase 1 - 1 Property Tax | 2026-12-11 | 2026-12-29 | ARC | 20.7 | Medium | Not started | Task: Module 1: Property Tax & Revenue Management. Deliverable: LLD, OpenAPI, schemas
4.1.3 UX wireframes and UI design | Phase 1 - 1 Property Tax | 2026-12-11 | 2026-12-29 | FE | 17.25 | Medium | Not started | Task: Module 1: Property Tax & Revenue Management. Deliverable: Approved wireframes
4.1.4 Database schema, domain logic and APIs | Phase 1 - 1 Property Tax | 2026-12-28 | 2027-03-02 | BE | 60.95 | Medium | Not started | Task: Module 1: Property Tax & Revenue Management. Deliverable: Service build
4.1.5 Workflows (BPMN) and rules (DMN) configuration | Phase 1 - 1 Property Tax | 2027-01-15 | 2027-03-03 | BE | 28.75 | Medium | Not started | Task: Module 1: Property Tax & Revenue Management. Deliverable: Deployed workflows and decision tables
4.1.6 Staff console screens | Phase 1 - 1 Property Tax | 2027-01-07 | 2027-03-10 | FE | 50.6 | Medium | Not started | Task: Module 1: Property Tax & Revenue Management. Deliverable: Staff screens
4.1.7 Citizen portal and app services | Phase 1 - 1 Property Tax | 2027-01-22 | 2027-03-10 | FE | 36.8 | Medium | Not started | Task: Module 1: Property Tax & Revenue Management. Deliverable: Citizen services live in MyGWMC
4.1.8 Field app tasks (offline) | Phase 1 - 1 Property Tax | 2027-01-22 | 2027-03-10 | MOB | 24.15 | Medium | Not started | Task: Module 1: Property Tax & Revenue Management. Deliverable: Field app plug-in
4.1.9 GIS layers, map views and spatial checks | Phase 1 - 1 Property Tax | 2027-01-07 | 2027-03-02 | GIS | 20.7 | Medium | Not started | Task: Module 1: Property Tax & Revenue Management. Deliverable: Layers and map features
4.1.10 Module interfaces (16 I-xx links): events and APIs | Phase 1 - 1 Property Tax | 2027-02-01 | 2027-03-15 | BE | 27.6 | Medium | Not started | Task: Module 1: Property Tax & Revenue Management. Deliverable: Contract-tested interfaces
4.1.11 External system adapters (7) | Phase 1 - 1 Property Tax | 2027-01-22 | 2027-03-15 | BE | 48.3 | Medium | Not started | Task: Module 1: Property Tax & Revenue Management. Deliverable: Adapters tested with provider sandboxes
4.1.12 Reports, dashboards, notices and templates (all active languages) | Phase 1 - 1 Property Tax | 2027-02-16 | 2027-03-17 | BE | 20.7 | Medium | Not started | Task: Module 1: Property Tax & Revenue Management. Deliverable: Reports and templates
4.1.13 Data migration: CDMA property, demand and arrears | Phase 1 - 1 Property Tax | 2027-01-15 | 2027-03-25 | DATA | 28.75 | Medium | Not started | Task: Module 1: Property Tax & Revenue Management. Deliverable: Migration scripts and reconciliation report
4.1.14 System integration testing | Phase 1 - 1 Property Tax | 2027-03-05 | 2027-03-30 | QA | 41.4 | Medium | Not started | Task: Module 1: Property Tax & Revenue Management. Deliverable: SIT report
4.1.15 Defect fixing and regression | Phase 1 - 1 Property Tax | 2027-03-11 | 2027-04-09 | BE | 34.5 | Medium | Not started | Task: Module 1: Property Tax & Revenue Management. Deliverable: Closed defects
4.1.16 UAT support with GWMC department | Phase 1 - 1 Property Tax | 2027-03-31 | 2027-04-14 | BA | 20.7 | Medium | Not started | Task: Module 1: Property Tax & Revenue Management. Deliverable: UAT sign-off
4.1.17 Training material and department training | Phase 1 - 1 Property Tax | 2027-04-05 | 2027-04-19 | TRN | 17.25 | Medium | Not started | Task: Module 1: Property Tax & Revenue Management. Deliverable: Trained users, manuals in Telugu and English
4.2.1 Process validation workshops and to-be sign-off | Phase 1 - 2 Water & Sewerage | 2026-11-30 | 2026-12-16 | BA | 19.55 | Medium | Not started | Task: Module 2: Water, Sewerage & Utility Billing. Deliverable: Signed process maps
4.2.2 LLD, data model and API/event contracts | Phase 1 - 2 Water & Sewerage | 2026-12-11 | 2026-12-29 | ARC | 18.4 | Medium | Not started | Task: Module 2: Water, Sewerage & Utility Billing. Deliverable: LLD, OpenAPI, schemas
4.2.3 UX wireframes and UI design | Phase 1 - 2 Water & Sewerage | 2026-12-11 | 2026-12-29 | FE | 14.95 | Medium | Not started | Task: Module 2: Water, Sewerage & Utility Billing. Deliverable: Approved wireframes
4.2.4 Database schema, domain logic and APIs | Phase 1 - 2 Water & Sewerage | 2026-12-28 | 2027-03-02 | BE | 57.5 | Medium | Not started | Task: Module 2: Water, Sewerage & Utility Billing. Deliverable: Service build
4.2.5 Workflows (BPMN) and rules (DMN) configuration | Phase 1 - 2 Water & Sewerage | 2027-01-15 | 2027-03-03 | BE | 27.6 | Medium | Not started | Task: Module 2: Water, Sewerage & Utility Billing. Deliverable: Deployed workflows and decision tables
4.2.6 Staff console screens | Phase 1 - 2 Water & Sewerage | 2027-01-07 | 2027-03-10 | FE | 48.3 | Medium | Not started | Task: Module 2: Water, Sewerage & Utility Billing. Deliverable: Staff screens
4.2.7 Citizen portal and app services | Phase 1 - 2 Water & Sewerage | 2027-01-22 | 2027-03-10 | FE | 34.5 | Medium | Not started | Task: Module 2: Water, Sewerage & Utility Billing. Deliverable: Citizen services live in MyGWMC
4.2.8 Field app tasks (offline) | Phase 1 - 2 Water & Sewerage | 2027-01-22 | 2027-03-10 | MOB | 23 | Medium | Not started | Task: Module 2: Water, Sewerage & Utility Billing. Deliverable: Field app plug-in
4.2.9 GIS layers, map views and spatial checks | Phase 1 - 2 Water & Sewerage | 2027-01-07 | 2027-03-02 | GIS | 19.55 | Medium | Not started | Task: Module 2: Water, Sewerage & Utility Billing. Deliverable: Layers and map features
4.2.10 Module interfaces (17 I-xx links): events and APIs | Phase 1 - 2 Water & Sewerage | 2027-02-01 | 2027-03-15 | BE | 29.9 | Medium | Not started | Task: Module 2: Water, Sewerage & Utility Billing. Deliverable: Contract-tested interfaces
4.2.11 External system adapters (2) | Phase 1 - 2 Water & Sewerage | 2027-01-22 | 2027-03-15 | BE | 13.8 | Medium | Not started | Task: Module 2: Water, Sewerage & Utility Billing. Deliverable: Adapters tested with provider sandboxes
4.2.12 Reports, dashboards, notices and templates (all active languages) | Phase 1 - 2 Water & Sewerage | 2027-02-16 | 2027-03-17 | BE | 19.55 | Medium | Not started | Task: Module 2: Water, Sewerage & Utility Billing. Deliverable: Reports and templates
4.2.13 Data migration: consumer, meter and arrears data | Phase 1 - 2 Water & Sewerage | 2027-01-15 | 2027-03-25 | DATA | 26.45 | Medium | Not started | Task: Module 2: Water, Sewerage & Utility Billing. Deliverable: Migration scripts and reconciliation report
4.2.14 System integration testing | Phase 1 - 2 Water & Sewerage | 2027-03-05 | 2027-03-30 | QA | 39.1 | Medium | Not started | Task: Module 2: Water, Sewerage & Utility Billing. Deliverable: SIT report
4.2.15 Defect fixing and regression | Phase 1 - 2 Water & Sewerage | 2027-03-11 | 2027-04-09 | BE | 32.2 | Medium | Not started | Task: Module 2: Water, Sewerage & Utility Billing. Deliverable: Closed defects
4.2.16 UAT support with GWMC department | Phase 1 - 2 Water & Sewerage | 2027-03-31 | 2027-04-14 | BA | 18.4 | Medium | Not started | Task: Module 2: Water, Sewerage & Utility Billing. Deliverable: UAT sign-off
4.2.17 Training material and department training | Phase 1 - 2 Water & Sewerage | 2027-04-05 | 2027-04-19 | TRN | 14.95 | Medium | Not started | Task: Module 2: Water, Sewerage & Utility Billing. Deliverable: Trained users, manuals in Telugu and English
4.3.1 Process validation workshops and to-be sign-off | Phase 1 - 3 Citizen Desk & RTI | 2026-11-30 | 2026-12-16 | BA | 18.4 | Medium | Not started | Task: Module 3: Citizen Service Desk, Grievance & RTI. Deliverable: Signed process maps
4.3.2 LLD, data model and API/event contracts | Phase 1 - 3 Citizen Desk & RTI | 2026-12-11 | 2026-12-29 | ARC | 18.4 | Medium | Not started | Task: Module 3: Citizen Service Desk, Grievance & RTI. Deliverable: LLD, OpenAPI, schemas
4.3.3 UX wireframes and UI design | Phase 1 - 3 Citizen Desk & RTI | 2026-12-11 | 2026-12-29 | FE | 13.8 | Medium | Not started | Task: Module 3: Citizen Service Desk, Grievance & RTI. Deliverable: Approved wireframes
4.3.4 Database schema, domain logic and APIs | Phase 1 - 3 Citizen Desk & RTI | 2026-12-28 | 2027-03-02 | BE | 51.75 | Medium | Not started | Task: Module 3: Citizen Service Desk, Grievance & RTI. Deliverable: Service build
4.3.5 Workflows (BPMN) and rules (DMN) configuration | Phase 1 - 3 Citizen Desk & RTI | 2027-01-15 | 2027-03-03 | BE | 24.15 | Medium | Not started | Task: Module 3: Citizen Service Desk, Grievance & RTI. Deliverable: Deployed workflows and decision tables
4.3.6 Staff console screens | Phase 1 - 3 Citizen Desk & RTI | 2027-01-07 | 2027-03-10 | FE | 43.7 | Medium | Not started | Task: Module 3: Citizen Service Desk, Grievance & RTI. Deliverable: Staff screens
4.3.7 Citizen portal and app services | Phase 1 - 3 Citizen Desk & RTI | 2027-01-22 | 2027-03-10 | FE | 31.05 | Medium | Not started | Task: Module 3: Citizen Service Desk, Grievance & RTI. Deliverable: Citizen services live in MyGWMC
4.3.8 GIS layers, map views and spatial checks | Phase 1 - 3 Citizen Desk & RTI | 2027-01-07 | 2027-03-02 | GIS | 17.25 | Medium | Not started | Task: Module 3: Citizen Service Desk, Grievance & RTI. Deliverable: Layers and map features
4.3.9 Module interfaces (5 I-xx links): events and APIs | Phase 1 - 3 Citizen Desk & RTI | 2027-02-01 | 2027-03-15 | BE | 9.2 | Medium | Not started | Task: Module 3: Citizen Service Desk, Grievance & RTI. Deliverable: Contract-tested interfaces
4.3.10 External system adapters (6) | Phase 1 - 3 Citizen Desk & RTI | 2027-01-22 | 2027-03-15 | BE | 41.4 | Medium | Not started | Task: Module 3: Citizen Service Desk, Grievance & RTI. Deliverable: Adapters tested with provider sandboxes
4.3.11 Reports, dashboards, notices and templates (all active languages) | Phase 1 - 3 Citizen Desk & RTI | 2027-02-16 | 2027-03-17 | BE | 17.25 | Medium | Not started | Task: Module 3: Citizen Service Desk, Grievance & RTI. Deliverable: Reports and templates
4.3.12 System integration testing | Phase 1 - 3 Citizen Desk & RTI | 2027-03-05 | 2027-03-30 | QA | 34.5 | Medium | Not started | Task: Module 3: Citizen Service Desk, Grievance & RTI. Deliverable: SIT report
4.3.13 Defect fixing and regression | Phase 1 - 3 Citizen Desk & RTI | 2027-03-11 | 2027-04-09 | BE | 29.9 | Medium | Not started | Task: Module 3: Citizen Service Desk, Grievance & RTI. Deliverable: Closed defects
4.3.14 UAT support with GWMC department | Phase 1 - 3 Citizen Desk & RTI | 2027-03-31 | 2027-04-14 | BA | 18.4 | Medium | Not started | Task: Module 3: Citizen Service Desk, Grievance & RTI. Deliverable: UAT sign-off
4.3.15 Training material and department training | Phase 1 - 3 Citizen Desk & RTI | 2027-04-05 | 2027-04-19 | TRN | 13.8 | Medium | Not started | Task: Module 3: Citizen Service Desk, Grievance & RTI. Deliverable: Trained users, manuals in Telugu and English
4.4.1 Process validation workshops and to-be sign-off | Phase 1 - 4 Finance & Accounting | 2026-11-30 | 2026-12-16 | BA | 18.4 | Medium | Not started | Task: Module 4: Finance & Accounting. Deliverable: Signed process maps
4.4.2 LLD, data model and API/event contracts | Phase 1 - 4 Finance & Accounting | 2026-12-11 | 2026-12-29 | ARC | 18.4 | Medium | Not started | Task: Module 4: Finance & Accounting. Deliverable: LLD, OpenAPI, schemas
4.4.3 UX wireframes and UI design | Phase 1 - 4 Finance & Accounting | 2026-12-11 | 2026-12-29 | FE | 13.8 | Medium | Not started | Task: Module 4: Finance & Accounting. Deliverable: Approved wireframes
4.4.4 Database schema, domain logic and APIs | Phase 1 - 4 Finance & Accounting | 2026-12-28 | 2027-03-02 | BE | 51.75 | Medium | Not started | Task: Module 4: Finance & Accounting. Deliverable: Service build
4.4.5 Workflows (BPMN) and rules (DMN) configuration | Phase 1 - 4 Finance & Accounting | 2027-01-15 | 2027-03-03 | BE | 24.15 | Medium | Not started | Task: Module 4: Finance & Accounting. Deliverable: Deployed workflows and decision tables
4.4.6 Staff console screens | Phase 1 - 4 Finance & Accounting | 2027-01-07 | 2027-03-10 | FE | 43.7 | Medium | Not started | Task: Module 4: Finance & Accounting. Deliverable: Staff screens
4.4.7 Module interfaces (10 I-xx links): events and APIs | Phase 1 - 4 Finance & Accounting | 2027-02-01 | 2027-03-15 | BE | 17.25 | Medium | Not started | Task: Module 4: Finance & Accounting. Deliverable: Contract-tested interfaces
4.4.8 External system adapters (5) | Phase 1 - 4 Finance & Accounting | 2027-01-22 | 2027-03-15 | BE | 34.5 | Medium | Not started | Task: Module 4: Finance & Accounting. Deliverable: Adapters tested with provider sandboxes
4.4.9 Reports, dashboards, notices and templates (all active languages) | Phase 1 - 4 Finance & Accounting | 2027-02-16 | 2027-03-17 | BE | 17.25 | Medium | Not started | Task: Module 4: Finance & Accounting. Deliverable: Reports and templates
4.4.10 Data migration: opening balances, budgets, vendors | Phase 1 - 4 Finance & Accounting | 2027-01-15 | 2027-03-25 | DATA | 24.15 | Medium | Not started | Task: Module 4: Finance & Accounting. Deliverable: Migration scripts and reconciliation report
4.4.11 System integration testing | Phase 1 - 4 Finance & Accounting | 2027-03-05 | 2027-03-30 | QA | 34.5 | Medium | Not started | Task: Module 4: Finance & Accounting. Deliverable: SIT report
4.4.12 Defect fixing and regression | Phase 1 - 4 Finance & Accounting | 2027-03-11 | 2027-04-09 | BE | 29.9 | Medium | Not started | Task: Module 4: Finance & Accounting. Deliverable: Closed defects
4.4.13 UAT support with GWMC department | Phase 1 - 4 Finance & Accounting | 2027-03-31 | 2027-04-14 | BA | 18.4 | Medium | Not started | Task: Module 4: Finance & Accounting. Deliverable: UAT sign-off
4.4.14 Training material and department training | Phase 1 - 4 Finance & Accounting | 2027-04-05 | 2027-04-19 | TRN | 13.8 | Medium | Not started | Task: Module 4: Finance & Accounting. Deliverable: Trained users, manuals in Telugu and English
4.5.1 Process validation workshops and to-be sign-off | Phase 1 - 9 Document Management | 2026-11-30 | 2026-12-16 | BA | 18.4 | Medium | Not started | Task: Module 9: Document Management System. Deliverable: Signed process maps
4.5.2 LLD, data model and API/event contracts | Phase 1 - 9 Document Management | 2026-12-11 | 2026-12-29 | ARC | 18.4 | Medium | Not started | Task: Module 9: Document Management System. Deliverable: LLD, OpenAPI, schemas
4.5.3 UX wireframes and UI design | Phase 1 - 9 Document Management | 2026-12-11 | 2026-12-29 | FE | 13.8 | Medium | Not started | Task: Module 9: Document Management System. Deliverable: Approved wireframes
4.5.4 Database schema, domain logic and APIs | Phase 1 - 9 Document Management | 2026-12-28 | 2027-03-02 | BE | 52.9 | Medium | Not started | Task: Module 9: Document Management System. Deliverable: Service build
4.5.5 Workflows (BPMN) and rules (DMN) configuration | Phase 1 - 9 Document Management | 2027-01-15 | 2027-03-03 | BE | 24.15 | Medium | Not started | Task: Module 9: Document Management System. Deliverable: Deployed workflows and decision tables
4.5.6 Staff console screens | Phase 1 - 9 Document Management | 2027-01-07 | 2027-03-10 | FE | 43.7 | Medium | Not started | Task: Module 9: Document Management System. Deliverable: Staff screens
4.5.7 Citizen portal and app services | Phase 1 - 9 Document Management | 2027-01-22 | 2027-03-10 | FE | 31.05 | Medium | Not started | Task: Module 9: Document Management System. Deliverable: Citizen services live in MyGWMC
4.5.8 Module interfaces (3 I-xx links): events and APIs | Phase 1 - 9 Document Management | 2027-02-01 | 2027-03-15 | BE | 4.6 | Medium | Not started | Task: Module 9: Document Management System. Deliverable: Contract-tested interfaces
4.5.9 External system adapters (5) | Phase 1 - 9 Document Management | 2027-01-22 | 2027-03-15 | BE | 34.5 | Medium | Not started | Task: Module 9: Document Management System. Deliverable: Adapters tested with provider sandboxes
4.5.10 Reports, dashboards, notices and templates (all active languages) | Phase 1 - 9 Document Management | 2027-02-16 | 2027-03-17 | BE | 17.25 | Medium | Not started | Task: Module 9: Document Management System. Deliverable: Reports and templates
4.5.11 Data migration: legacy files for scanning and indexing | Phase 1 - 9 Document Management | 2027-01-15 | 2027-03-25 | DATA | 24.15 | Medium | Not started | Task: Module 9: Document Management System. Deliverable: Migration scripts and reconciliation report
4.5.12 System integration testing | Phase 1 - 9 Document Management | 2027-03-05 | 2027-03-30 | QA | 34.5 | Medium | Not started | Task: Module 9: Document Management System. Deliverable: SIT report
4.5.13 Defect fixing and regression | Phase 1 - 9 Document Management | 2027-03-11 | 2027-04-09 | BE | 29.9 | Medium | Not started | Task: Module 9: Document Management System. Deliverable: Closed defects
4.5.14 UAT support with GWMC department | Phase 1 - 9 Document Management | 2027-03-31 | 2027-04-14 | BA | 18.4 | Medium | Not started | Task: Module 9: Document Management System. Deliverable: UAT sign-off
4.5.15 Training material and department training | Phase 1 - 9 Document Management | 2027-04-05 | 2027-04-19 | TRN | 13.8 | Medium | Not started | Task: Module 9: Document Management System. Deliverable: Trained users, manuals in Telugu and English
4.6.1 End-to-end integration testing (SRS E2E scenarios) | Phase 1 - Release | 2027-03-23 | 2027-04-06 | QA | 34.5 | Medium | Not started | Task: Phase 1 release, testing and go-live. Deliverable: E2E report
4.6.2 Performance and load testing (NFR-001/002) | Phase 1 - Release | 2027-03-26 | 2027-04-06 | QA | 18.4 | Medium | Not started | Task: Phase 1 release, testing and go-live. Deliverable: Performance report
4.6.3 Security audit by CERT-In empanelled auditor and fixes | Phase 1 - Release | 2027-03-31 | 2027-04-14 | QA | 24.15 | Medium | Not started | Task: Phase 1 release, testing and go-live. Deliverable: Audit certificate
4.6.4 Training of trainers and end-user training programme | Phase 1 - Release | 2027-04-07 | 2027-04-21 | TRN | 23 | Medium | Not started | Task: Phase 1 release, testing and go-live. Deliverable: Training attendance and feedback
4.6.5 Migration dress rehearsal and cut-over plan | Phase 1 - Release | 2027-04-09 | 2027-04-19 | DATA | 14.95 | Medium | Not started | Task: Phase 1 release, testing and go-live. Deliverable: Cut-over runbook
4.6.6 Production deployment and cut-over | Phase 1 - Release | 2027-04-20 | 2027-04-21 | DEV | 18.4 | Medium | Not started | Task: Phase 1 release, testing and go-live. Deliverable: Go-live
4.7 M1: Phase 1 go-live | Phase 1 - Phase 1: Foundation and revenue core | 2027-04-22 | 2027-04-22 | 0 | 0 | Important | Not started | Task: Phase 1: Foundation and revenue core. Deliverable:
4.7.1 Hypercare and stabilisation (4 weeks) | Phase 1 - Release | 2027-04-22 | 2027-05-14 | BE | 33.35 | Medium | Not started | Task: M1: Phase 1 go-live. Deliverable: Hypercare closure report
4.8 Phase 1 acceptance and sign-off | Phase 1 - Phase 1: Foundation and revenue core | 2027-05-14 | 2027-05-14 | 0 | 0 | Important | Not started | Task: Phase 1: Foundation and revenue core. Deliverable:
4.9 Phase 1 build mid-point (next phase design may start) | Phase 1 - Phase 1: Foundation and revenue core | 2027-02-16 | 2027-02-16 | 0 | 0 | Important | Not started | Task: Phase 1: Foundation and revenue core. Deliverable:
5.1.1 GIS elevation and 3D service (DTM, DSM, 3D Tiles) | Phase 2 - Platform | 2027-03-23 | 2027-06-11 | GIS | 47.15 | Medium | Not started | Task: Platform increments for Phase 2. Deliverable: Platform release
5.1.2 Hand over ward and planning layers to Town Planning (I-20) | Phase 2 - Platform | 2027-03-23 | 2027-06-11 | GIS | 14.95 | Medium | Not started | Task: Platform increments for Phase 2. Deliverable: Platform release
5.2.1 Process validation workshops and to-be sign-off | Phase 2 - 5 Trade Licence | 2027-03-04 | 2027-03-25 | BA | 16.1 | Medium | Not started | Task: Module 5: Trade Licence Management. Deliverable: Signed process maps
5.2.2 LLD, data model and API/event contracts | Phase 2 - 5 Trade Licence | 2027-03-19 | 2027-04-09 | ARC | 13.8 | Medium | Not started | Task: Module 5: Trade Licence Management. Deliverable: LLD, OpenAPI, schemas
5.2.3 UX wireframes and UI design | Phase 2 - 5 Trade Licence | 2027-03-19 | 2027-04-09 | FE | 12.65 | Medium | Not started | Task: Module 5: Trade Licence Management. Deliverable: Approved wireframes
5.2.4 Database schema, domain logic and APIs | Phase 2 - 5 Trade Licence | 2027-04-07 | 2027-06-22 | BE | 44.85 | Medium | Not started | Task: Module 5: Trade Licence Management. Deliverable: Service build
5.2.5 Workflows (BPMN) and rules (DMN) configuration | Phase 2 - 5 Trade Licence | 2027-04-29 | 2027-06-23 | BE | 20.7 | Medium | Not started | Task: Module 5: Trade Licence Management. Deliverable: Deployed workflows and decision tables
5.2.6 Staff console screens | Phase 2 - 5 Trade Licence | 2027-04-20 | 2027-07-01 | FE | 36.8 | Medium | Not started | Task: Module 5: Trade Licence Management. Deliverable: Staff screens
5.2.7 Citizen portal and app services | Phase 2 - 5 Trade Licence | 2027-05-07 | 2027-07-01 | FE | 27.6 | Medium | Not started | Task: Module 5: Trade Licence Management. Deliverable: Citizen services live in MyGWMC
5.2.8 Field app tasks (offline) | Phase 2 - 5 Trade Licence | 2027-05-07 | 2027-07-01 | MOB | 18.4 | Medium | Not started | Task: Module 5: Trade Licence Management. Deliverable: Field app plug-in
5.2.9 GIS layers, map views and spatial checks | Phase 2 - 5 Trade Licence | 2027-04-20 | 2027-06-22 | GIS | 14.95 | Medium | Not started | Task: Module 5: Trade Licence Management. Deliverable: Layers and map features
5.2.10 Module interfaces (10 I-xx links): events and APIs | Phase 2 - 5 Trade Licence | 2027-05-18 | 2027-07-07 | BE | 17.25 | Medium | Not started | Task: Module 5: Trade Licence Management. Deliverable: Contract-tested interfaces
5.2.11 External system adapters (3) | Phase 2 - 5 Trade Licence | 2027-05-07 | 2027-07-07 | BE | 20.7 | Medium | Not started | Task: Module 5: Trade Licence Management. Deliverable: Adapters tested with provider sandboxes
5.2.12 Reports, dashboards, notices and templates (all active languages) | Phase 2 - 5 Trade Licence | 2027-06-04 | 2027-07-09 | BE | 14.95 | Medium | Not started | Task: Module 5: Trade Licence Management. Deliverable: Reports and templates
5.2.13 Data migration: existing licences | Phase 2 - 5 Trade Licence | 2027-04-29 | 2027-07-20 | DATA | 21.85 | Medium | Not started | Task: Module 5: Trade Licence Management. Deliverable: Migration scripts and reconciliation report
5.2.14 System integration testing | Phase 2 - 5 Trade Licence | 2027-06-28 | 2027-07-26 | QA | 29.9 | Medium | Not started | Task: Module 5: Trade Licence Management. Deliverable: SIT report
5.2.15 Defect fixing and regression | Phase 2 - 5 Trade Licence | 2027-07-02 | 2027-08-06 | BE | 24.15 | Medium | Not started | Task: Module 5: Trade Licence Management. Deliverable: Closed defects
5.2.16 UAT support with GWMC department | Phase 2 - 5 Trade Licence | 2027-07-27 | 2027-08-12 | BA | 13.8 | Medium | Not started | Task: Module 5: Trade Licence Management. Deliverable: UAT sign-off
5.2.17 Training material and department training | Phase 2 - 5 Trade Licence | 2027-07-30 | 2027-08-17 | TRN | 12.65 | Medium | Not started | Task: Module 5: Trade Licence Management. Deliverable: Trained users, manuals in Telugu and English
5.3.1 Process validation workshops and to-be sign-off | Phase 2 - 6 User Charges | 2027-03-04 | 2027-03-25 | BA | 13.8 | Medium | Not started | Task: Module 6: User Charges Management. Deliverable: Signed process maps
5.3.2 LLD, data model and API/event contracts | Phase 2 - 6 User Charges | 2027-03-19 | 2027-04-09 | ARC | 13.8 | Medium | Not started | Task: Module 6: User Charges Management. Deliverable: LLD, OpenAPI, schemas
5.3.3 UX wireframes and UI design | Phase 2 - 6 User Charges | 2027-03-19 | 2027-04-09 | FE | 10.35 | Medium | Not started | Task: Module 6: User Charges Management. Deliverable: Approved wireframes
5.3.4 Database schema, domain logic and APIs | Phase 2 - 6 User Charges | 2027-04-07 | 2027-06-22 | BE | 39.1 | Medium | Not started | Task: Module 6: User Charges Management. Deliverable: Service build
5.3.5 Workflows (BPMN) and rules (DMN) configuration | Phase 2 - 6 User Charges | 2027-04-29 | 2027-06-23 | BE | 17.25 | Medium | Not started | Task: Module 6: User Charges Management. Deliverable: Deployed workflows and decision tables
5.3.6 Staff console screens | Phase 2 - 6 User Charges | 2027-04-20 | 2027-07-01 | FE | 32.2 | Medium | Not started | Task: Module 6: User Charges Management. Deliverable: Staff screens
5.3.7 Citizen portal and app services | Phase 2 - 6 User Charges | 2027-05-07 | 2027-07-01 | FE | 24.15 | Medium | Not started | Task: Module 6: User Charges Management. Deliverable: Citizen services live in MyGWMC
5.3.8 Field app tasks (offline) | Phase 2 - 6 User Charges | 2027-05-07 | 2027-07-01 | MOB | 16.1 | Medium | Not started | Task: Module 6: User Charges Management. Deliverable: Field app plug-in
5.3.9 GIS layers, map views and spatial checks | Phase 2 - 6 User Charges | 2027-04-20 | 2027-06-22 | GIS | 12.65 | Medium | Not started | Task: Module 6: User Charges Management. Deliverable: Layers and map features
5.3.10 Module interfaces (12 I-xx links): events and APIs | Phase 2 - 6 User Charges | 2027-05-18 | 2027-07-07 | BE | 20.7 | Medium | Not started | Task: Module 6: User Charges Management. Deliverable: Contract-tested interfaces
5.3.11 External system adapters (2) | Phase 2 - 6 User Charges | 2027-05-07 | 2027-07-07 | BE | 13.8 | Medium | Not started | Task: Module 6: User Charges Management. Deliverable: Adapters tested with provider sandboxes
5.3.12 Reports, dashboards, notices and templates (all active languages) | Phase 2 - 6 User Charges | 2027-06-04 | 2027-07-09 | BE | 11.5 | Medium | Not started | Task: Module 6: User Charges Management. Deliverable: Reports and templates
5.3.13 Data migration: existing user-charge accounts | Phase 2 - 6 User Charges | 2027-04-29 | 2027-07-20 | DATA | 18.4 | Medium | Not started | Task: Module 6: User Charges Management. Deliverable: Migration scripts and reconciliation report
5.3.14 System integration testing | Phase 2 - 6 User Charges | 2027-06-28 | 2027-07-26 | QA | 25.3 | Medium | Not started | Task: Module 6: User Charges Management. Deliverable: SIT report
5.3.15 Defect fixing and regression | Phase 2 - 6 User Charges | 2027-07-02 | 2027-08-06 | BE | 21.85 | Medium | Not started | Task: Module 6: User Charges Management. Deliverable: Closed defects
5.3.16 UAT support with GWMC department | Phase 2 - 6 User Charges | 2027-07-27 | 2027-08-12 | BA | 13.8 | Medium | Not started | Task: Module 6: User Charges Management. Deliverable: UAT sign-off
5.3.17 Training material and department training | Phase 2 - 6 User Charges | 2027-07-30 | 2027-08-17 | TRN | 10.35 | Medium | Not started | Task: Module 6: User Charges Management. Deliverable: Trained users, manuals in Telugu and English
5.4.1 Process validation workshops and to-be sign-off | Phase 2 - 11 Building Permission | 2027-03-04 | 2027-03-25 | BA | 13.8 | Medium | Not started | Task: Module 11: Building Permission Management / Integration. Deliverable: Signed process maps
5.4.2 LLD, data model and API/event contracts | Phase 2 - 11 Building Permission | 2027-03-19 | 2027-04-09 | ARC | 13.8 | Medium | Not started | Task: Module 11: Building Permission Management / Integration. Deliverable: LLD, OpenAPI, schemas
5.4.3 UX wireframes and UI design | Phase 2 - 11 Building Permission | 2027-03-19 | 2027-04-09 | FE | 10.35 | Medium | Not started | Task: Module 11: Building Permission Management / Integration. Deliverable: Approved wireframes
5.4.4 Database schema, domain logic and APIs | Phase 2 - 11 Building Permission | 2027-04-07 | 2027-06-22 | BE | 40.25 | Medium | Not started | Task: Module 11: Building Permission Management / Integration. Deliverable: Service build
5.4.5 Workflows (BPMN) and rules (DMN) configuration | Phase 2 - 11 Building Permission | 2027-04-29 | 2027-06-23 | BE | 19.55 | Medium | Not started | Task: Module 11: Building Permission Management / Integration. Deliverable: Deployed workflows and decision tables
5.4.6 Staff console screens | Phase 2 - 11 Building Permission | 2027-04-20 | 2027-07-01 | FE | 33.35 | Medium | Not started | Task: Module 11: Building Permission Management / Integration. Deliverable: Staff screens
5.4.7 Citizen portal and app services | Phase 2 - 11 Building Permission | 2027-05-07 | 2027-07-01 | FE | 24.15 | Medium | Not started | Task: Module 11: Building Permission Management / Integration. Deliverable: Citizen services live in MyGWMC
5.4.8 Field app tasks (offline) | Phase 2 - 11 Building Permission | 2027-05-07 | 2027-07-01 | MOB | 16.1 | Medium | Not started | Task: Module 11: Building Permission Management / Integration. Deliverable: Field app plug-in
5.4.9 GIS layers, map views and spatial checks | Phase 2 - 11 Building Permission | 2027-04-20 | 2027-06-22 | GIS | 13.8 | Medium | Not started | Task: Module 11: Building Permission Management / Integration. Deliverable: Layers and map features
5.4.10 Module interfaces (14 I-xx links): events and APIs | Phase 2 - 11 Building Permission | 2027-05-18 | 2027-07-07 | BE | 24.15 | Medium | Not started | Task: Module 11: Building Permission Management / Integration. Deliverable: Contract-tested interfaces
5.4.11 External system adapters (10) | Phase 2 - 11 Building Permission | 2027-05-07 | 2027-07-07 | BE | 69 | Medium | Not started | Task: Module 11: Building Permission Management / Integration. Deliverable: Adapters tested with provider sandboxes
5.4.12 Reports, dashboards, notices and templates (all active languages) | Phase 2 - 11 Building Permission | 2027-06-04 | 2027-07-09 | BE | 13.8 | Medium | Not started | Task: Module 11: Building Permission Management / Integration. Deliverable: Reports and templates
5.4.13 Data migration: permits in TG-bPASS | Phase 2 - 11 Building Permission | 2027-04-29 | 2027-07-20 | DATA | 18.4 | Medium | Not started | Task: Module 11: Building Permission Management / Integration. Deliverable: Migration scripts and reconciliation report
5.4.14 System integration testing | Phase 2 - 11 Building Permission | 2027-06-28 | 2027-07-26 | QA | 27.6 | Medium | Not started | Task: Module 11: Building Permission Management / Integration. Deliverable: SIT report
5.4.15 Defect fixing and regression | Phase 2 - 11 Building Permission | 2027-07-02 | 2027-08-06 | BE | 23 | Medium | Not started | Task: Module 11: Building Permission Management / Integration. Deliverable: Closed defects
5.4.16 UAT support with GWMC department | Phase 2 - 11 Building Permission | 2027-07-27 | 2027-08-12 | BA | 13.8 | Medium | Not started | Task: Module 11: Building Permission Management / Integration. Deliverable: UAT sign-off
5.4.17 Training material and department training | Phase 2 - 11 Building Permission | 2027-07-30 | 2027-08-17 | TRN | 10.35 | Medium | Not started | Task: Module 11: Building Permission Management / Integration. Deliverable: Trained users, manuals in Telugu and English
5.5.1 Process validation workshops and to-be sign-off | Phase 2 - 13 Town Planning | 2027-03-04 | 2027-03-25 | BA | 13.8 | Medium | Not started | Task: Module 13: Town Planning. Deliverable: Signed process maps
5.5.2 LLD, data model and API/event contracts | Phase 2 - 13 Town Planning | 2027-03-19 | 2027-04-09 | ARC | 13.8 | Medium | Not started | Task: Module 13: Town Planning. Deliverable: LLD, OpenAPI, schemas
5.5.3 UX wireframes and UI design | Phase 2 - 13 Town Planning | 2027-03-19 | 2027-04-09 | FE | 10.35 | Medium | Not started | Task: Module 13: Town Planning. Deliverable: Approved wireframes
5.5.4 Database schema, domain logic and APIs | Phase 2 - 13 Town Planning | 2027-04-07 | 2027-06-22 | BE | 40.25 | Medium | Not started | Task: Module 13: Town Planning. Deliverable: Service build
5.5.5 Workflows (BPMN) and rules (DMN) configuration | Phase 2 - 13 Town Planning | 2027-04-29 | 2027-06-23 | BE | 19.55 | Medium | Not started | Task: Module 13: Town Planning. Deliverable: Deployed workflows and decision tables
5.5.6 Staff console screens | Phase 2 - 13 Town Planning | 2027-04-20 | 2027-07-01 | FE | 33.35 | Medium | Not started | Task: Module 13: Town Planning. Deliverable: Staff screens
5.5.7 Citizen portal and app services | Phase 2 - 13 Town Planning | 2027-05-07 | 2027-07-01 | FE | 24.15 | Medium | Not started | Task: Module 13: Town Planning. Deliverable: Citizen services live in MyGWMC
5.5.8 Field app tasks (offline) | Phase 2 - 13 Town Planning | 2027-05-07 | 2027-07-01 | MOB | 16.1 | Medium | Not started | Task: Module 13: Town Planning. Deliverable: Field app plug-in
5.5.9 GIS layers, map views and spatial checks | Phase 2 - 13 Town Planning | 2027-04-20 | 2027-06-22 | GIS | 13.8 | Medium | Not started | Task: Module 13: Town Planning. Deliverable: Layers and map features
5.5.10 Module interfaces (11 I-xx links): events and APIs | Phase 2 - 13 Town Planning | 2027-05-18 | 2027-07-07 | BE | 18.4 | Medium | Not started | Task: Module 13: Town Planning. Deliverable: Contract-tested interfaces
5.5.11 External system adapters (3) | Phase 2 - 13 Town Planning | 2027-05-07 | 2027-07-07 | BE | 20.7 | Medium | Not started | Task: Module 13: Town Planning. Deliverable: Adapters tested with provider sandboxes
5.5.12 Reports, dashboards, notices and templates (all active languages) | Phase 2 - 13 Town Planning | 2027-06-04 | 2027-07-09 | BE | 13.8 | Medium | Not started | Task: Module 13: Town Planning. Deliverable: Reports and templates
5.5.13 Data migration: layouts and LRS records | Phase 2 - 13 Town Planning | 2027-04-29 | 2027-07-20 | DATA | 18.4 | Medium | Not started | Task: Module 13: Town Planning. Deliverable: Migration scripts and reconciliation report
5.5.14 System integration testing | Phase 2 - 13 Town Planning | 2027-06-28 | 2027-07-26 | QA | 27.6 | Medium | Not started | Task: Module 13: Town Planning. Deliverable: SIT report
5.5.15 Defect fixing and regression | Phase 2 - 13 Town Planning | 2027-07-02 | 2027-08-06 | BE | 23 | Medium | Not started | Task: Module 13: Town Planning. Deliverable: Closed defects
5.5.16 UAT support with GWMC department | Phase 2 - 13 Town Planning | 2027-07-27 | 2027-08-12 | BA | 13.8 | Medium | Not started | Task: Module 13: Town Planning. Deliverable: UAT sign-off
5.5.17 Training material and department training | Phase 2 - 13 Town Planning | 2027-07-30 | 2027-08-17 | TRN | 10.35 | Medium | Not started | Task: Module 13: Town Planning. Deliverable: Trained users, manuals in Telugu and English
5.6.1 Process validation workshops and to-be sign-off | Phase 2 - 18 Fire NOC | 2027-03-04 | 2027-03-25 | BA | 11.5 | Medium | Not started | Task: Module 18: Fire NOC Management. Deliverable: Signed process maps
5.6.2 LLD, data model and API/event contracts | Phase 2 - 18 Fire NOC | 2027-03-19 | 2027-04-09 | ARC | 9.2 | Medium | Not started | Task: Module 18: Fire NOC Management. Deliverable: LLD, OpenAPI, schemas
5.6.3 UX wireframes and UI design | Phase 2 - 18 Fire NOC | 2027-03-19 | 2027-04-09 | FE | 8.05 | Medium | Not started | Task: Module 18: Fire NOC Management. Deliverable: Approved wireframes
5.6.4 Database schema, domain logic and APIs | Phase 2 - 18 Fire NOC | 2027-04-07 | 2027-06-22 | BE | 29.9 | Medium | Not started | Task: Module 18: Fire NOC Management. Deliverable: Service build
5.6.5 Workflows (BPMN) and rules (DMN) configuration | Phase 2 - 18 Fire NOC | 2027-04-29 | 2027-06-23 | BE | 14.95 | Medium | Not started | Task: Module 18: Fire NOC Management. Deliverable: Deployed workflows and decision tables
5.6.6 Staff console screens | Phase 2 - 18 Fire NOC | 2027-04-20 | 2027-07-01 | FE | 25.3 | Medium | Not started | Task: Module 18: Fire NOC Management. Deliverable: Staff screens
5.6.7 Citizen portal and app services | Phase 2 - 18 Fire NOC | 2027-05-07 | 2027-07-01 | FE | 17.25 | Medium | Not started | Task: Module 18: Fire NOC Management. Deliverable: Citizen services live in MyGWMC
5.6.8 Field app tasks (offline) | Phase 2 - 18 Fire NOC | 2027-05-07 | 2027-07-01 | MOB | 11.5 | Medium | Not started | Task: Module 18: Fire NOC Management. Deliverable: Field app plug-in
5.6.9 GIS layers, map views and spatial checks | Phase 2 - 18 Fire NOC | 2027-04-20 | 2027-06-22 | GIS | 10.35 | Medium | Not started | Task: Module 18: Fire NOC Management. Deliverable: Layers and map features
5.6.10 Module interfaces (11 I-xx links): events and APIs | Phase 2 - 18 Fire NOC | 2027-05-18 | 2027-07-07 | BE | 18.4 | Medium | Not started | Task: Module 18: Fire NOC Management. Deliverable: Contract-tested interfaces
5.6.11 External system adapters (3) | Phase 2 - 18 Fire NOC | 2027-05-07 | 2027-07-07 | BE | 20.7 | Medium | Not started | Task: Module 18: Fire NOC Management. Deliverable: Adapters tested with provider sandboxes
5.6.12 Reports, dashboards, notices and templates (all active languages) | Phase 2 - 18 Fire NOC | 2027-06-04 | 2027-07-09 | BE | 11.5 | Medium | Not started | Task: Module 18: Fire NOC Management. Deliverable: Reports and templates
5.6.13 System integration testing | Phase 2 - 18 Fire NOC | 2027-06-28 | 2027-07-26 | QA | 20.7 | Medium | Not started | Task: Module 18: Fire NOC Management. Deliverable: SIT report
5.6.14 Defect fixing and regression | Phase 2 - 18 Fire NOC | 2027-07-02 | 2027-08-06 | BE | 17.25 | Medium | Not started | Task: Module 18: Fire NOC Management. Deliverable: Closed defects
5.6.15 UAT support with GWMC department | Phase 2 - 18 Fire NOC | 2027-07-27 | 2027-08-12 | BA | 9.2 | Medium | Not started | Task: Module 18: Fire NOC Management. Deliverable: UAT sign-off
5.6.16 Training material and department training | Phase 2 - 18 Fire NOC | 2027-07-30 | 2027-08-17 | TRN | 8.05 | Medium | Not started | Task: Module 18: Fire NOC Management. Deliverable: Trained users, manuals in Telugu and English
5.7.1 End-to-end integration testing (SRS E2E scenarios) | Phase 2 - Release | 2027-07-15 | 2027-08-02 | QA | 34.5 | Medium | Not started | Task: Phase 2 release, testing and go-live. Deliverable: E2E report
5.7.2 Performance and load testing (NFR-001/002) | Phase 2 - Release | 2027-07-21 | 2027-08-02 | QA | 18.4 | Medium | Not started | Task: Phase 2 release, testing and go-live. Deliverable: Performance report
5.7.3 Security audit by CERT-In empanelled auditor and fixes | Phase 2 - Release | 2027-07-27 | 2027-08-12 | QA | 24.15 | Medium | Not started | Task: Phase 2 release, testing and go-live. Deliverable: Audit certificate
5.7.4 Training of trainers and end-user training programme | Phase 2 - Release | 2027-08-03 | 2027-08-19 | TRN | 23 | Medium | Not started | Task: Phase 2 release, testing and go-live. Deliverable: Training attendance and feedback
5.7.5 Migration dress rehearsal and cut-over plan | Phase 2 - Release | 2027-08-06 | 2027-08-17 | DATA | 14.95 | Medium | Not started | Task: Phase 2 release, testing and go-live. Deliverable: Cut-over runbook
5.7.6 Production deployment and cut-over | Phase 2 - Release | 2027-08-18 | 2027-08-20 | DEV | 18.4 | Medium | Not started | Task: Phase 2 release, testing and go-live. Deliverable: Go-live
5.8 M2: Phase 2 go-live | Phase 2 - Phase 2: Regulation and licensing | 2027-08-20 | 2027-08-20 | 0 | 0 | Important | Not started | Task: Phase 2: Regulation and licensing. Deliverable:
5.8.1 Hypercare and stabilisation (4 weeks) | Phase 2 - Release | 2027-08-20 | 2027-09-16 | BE | 33.35 | Medium | Not started | Task: M2: Phase 2 go-live. Deliverable: Hypercare closure report
5.9 Phase 2 acceptance and sign-off | Phase 2 - Phase 2: Regulation and licensing | 2027-09-17 | 2027-09-17 | 0 | 0 | Important | Not started | Task: Phase 2: Regulation and licensing. Deliverable:
5.10 Phase 2 build mid-point (next phase design may start) | Phase 2 - Phase 2: Regulation and licensing | 2027-06-04 | 2027-06-04 | 0 | 0 | Important | Not started | Task: Phase 2: Regulation and licensing. Deliverable:
6.1.1 Field app scale-up and offline sync load test | Phase 3 - Platform | 2027-07-23 | 2027-10-13 | MOB | 24.15 | Medium | Not started | Task: Platform increments for Phase 3. Deliverable: Platform release
6.1.2 AVLS, CCMS and IoT ingestion pipeline | Phase 3 - Platform | 2027-07-23 | 2027-10-13 | BE | 23 | Medium | Not started | Task: Platform increments for Phase 3. Deliverable: Platform release
6.1.3 Road register moves to Engineering (I-32) | Phase 3 - Platform | 2027-07-23 | 2027-10-13 | GIS | 13.8 | Medium | Not started | Task: Platform increments for Phase 3. Deliverable: Platform release
6.2.1 Process validation workshops and to-be sign-off | Phase 3 - 7 Solid Waste | 2027-07-06 | 2027-07-27 | BA | 11.5 | Medium | Not started | Task: Module 7: Solid Waste Management. Deliverable: Signed process maps
6.2.2 LLD, data model and API/event contracts | Phase 3 - 7 Solid Waste | 2027-07-21 | 2027-08-11 | ARC | 9.2 | Medium | Not started | Task: Module 7: Solid Waste Management. Deliverable: LLD, OpenAPI, schemas
6.2.3 UX wireframes and UI design | Phase 3 - 7 Solid Waste | 2027-07-21 | 2027-08-11 | FE | 8.05 | Medium | Not started | Task: Module 7: Solid Waste Management. Deliverable: Approved wireframes
6.2.4 Database schema, domain logic and APIs | Phase 3 - 7 Solid Waste | 2027-08-09 | 2027-10-22 | BE | 31.05 | Medium | Not started | Task: Module 7: Solid Waste Management. Deliverable: Service build
6.2.5 Workflows (BPMN) and rules (DMN) configuration | Phase 3 - 7 Solid Waste | 2027-08-31 | 2027-10-25 | BE | 14.95 | Medium | Not started | Task: Module 7: Solid Waste Management. Deliverable: Deployed workflows and decision tables
6.2.6 Staff console screens | Phase 3 - 7 Solid Waste | 2027-08-20 | 2027-11-02 | FE | 25.3 | Medium | Not started | Task: Module 7: Solid Waste Management. Deliverable: Staff screens
6.2.7 Field app tasks (offline) | Phase 3 - 7 Solid Waste | 2027-09-08 | 2027-11-02 | MOB | 12.65 | Medium | Not started | Task: Module 7: Solid Waste Management. Deliverable: Field app plug-in
6.2.8 GIS layers, map views and spatial checks | Phase 3 - 7 Solid Waste | 2027-08-20 | 2027-10-22 | GIS | 10.35 | Medium | Not started | Task: Module 7: Solid Waste Management. Deliverable: Layers and map features
6.2.9 Module interfaces (13 I-xx links): events and APIs | Phase 3 - 7 Solid Waste | 2027-09-17 | 2027-11-08 | BE | 23 | Medium | Not started | Task: Module 7: Solid Waste Management. Deliverable: Contract-tested interfaces
6.2.10 External system adapters (3) | Phase 3 - 7 Solid Waste | 2027-09-08 | 2027-11-08 | BE | 20.7 | Medium | Not started | Task: Module 7: Solid Waste Management. Deliverable: Adapters tested with provider sandboxes
6.2.11 Reports, dashboards, notices and templates (all active languages) | Phase 3 - 7 Solid Waste | 2027-10-06 | 2027-11-10 | BE | 11.5 | Medium | Not started | Task: Module 7: Solid Waste Management. Deliverable: Reports and templates
6.2.12 System integration testing | Phase 3 - 7 Solid Waste | 2027-10-28 | 2027-11-25 | QA | 20.7 | Medium | Not started | Task: Module 7: Solid Waste Management. Deliverable: SIT report
6.2.13 Defect fixing and regression | Phase 3 - 7 Solid Waste | 2027-11-03 | 2027-12-08 | BE | 17.25 | Medium | Not started | Task: Module 7: Solid Waste Management. Deliverable: Closed defects
6.2.14 UAT support with GWMC department | Phase 3 - 7 Solid Waste | 2027-11-26 | 2027-12-14 | BA | 9.2 | Medium | Not started | Task: Module 7: Solid Waste Management. Deliverable: UAT sign-off
6.2.15 Training material and department training | Phase 3 - 7 Solid Waste | 2027-12-01 | 2027-12-17 | TRN | 8.05 | Medium | Not started | Task: Module 7: Solid Waste Management. Deliverable: Trained users, manuals in Telugu and English
6.3.1 Process validation workshops and to-be sign-off | Phase 3 - 10 Engineering Projects | 2027-07-06 | 2027-07-27 | BA | 12.65 | Medium | Not started | Task: Module 10: Engineering Project Management System. Deliverable: Signed process maps
6.3.2 LLD, data model and API/event contracts | Phase 3 - 10 Engineering Projects | 2027-07-21 | 2027-08-11 | ARC | 11.5 | Medium | Not started | Task: Module 10: Engineering Project Management System. Deliverable: LLD, OpenAPI, schemas
6.3.3 UX wireframes and UI design | Phase 3 - 10 Engineering Projects | 2027-07-21 | 2027-08-11 | FE | 9.2 | Medium | Not started | Task: Module 10: Engineering Project Management System. Deliverable: Approved wireframes
6.3.4 Database schema, domain logic and APIs | Phase 3 - 10 Engineering Projects | 2027-08-09 | 2027-10-22 | BE | 35.65 | Medium | Not started | Task: Module 10: Engineering Project Management System. Deliverable: Service build
6.3.5 Workflows (BPMN) and rules (DMN) configuration | Phase 3 - 10 Engineering Projects | 2027-08-31 | 2027-10-25 | BE | 16.1 | Medium | Not started | Task: Module 10: Engineering Project Management System. Deliverable: Deployed workflows and decision tables
6.3.6 Staff console screens | Phase 3 - 10 Engineering Projects | 2027-08-20 | 2027-11-02 | FE | 29.9 | Medium | Not started | Task: Module 10: Engineering Project Management System. Deliverable: Staff screens
6.3.7 Field app tasks (offline) | Phase 3 - 10 Engineering Projects | 2027-09-08 | 2027-11-02 | MOB | 13.8 | Medium | Not started | Task: Module 10: Engineering Project Management System. Deliverable: Field app plug-in
6.3.8 GIS layers, map views and spatial checks | Phase 3 - 10 Engineering Projects | 2027-08-20 | 2027-10-22 | GIS | 11.5 | Medium | Not started | Task: Module 10: Engineering Project Management System. Deliverable: Layers and map features
6.3.9 Module interfaces (9 I-xx links): events and APIs | Phase 3 - 10 Engineering Projects | 2027-09-17 | 2027-11-08 | BE | 16.1 | Medium | Not started | Task: Module 10: Engineering Project Management System. Deliverable: Contract-tested interfaces
6.3.10 External system adapters (2) | Phase 3 - 10 Engineering Projects | 2027-09-08 | 2027-11-08 | BE | 13.8 | Medium | Not started | Task: Module 10: Engineering Project Management System. Deliverable: Adapters tested with provider sandboxes
6.3.11 Reports, dashboards, notices and templates (all active languages) | Phase 3 - 10 Engineering Projects | 2027-10-06 | 2027-11-10 | BE | 11.5 | Medium | Not started | Task: Module 10: Engineering Project Management System. Deliverable: Reports and templates
6.3.12 System integration testing | Phase 3 - 10 Engineering Projects | 2027-10-28 | 2027-11-25 | QA | 23 | Medium | Not started | Task: Module 10: Engineering Project Management System. Deliverable: SIT report
6.3.13 Defect fixing and regression | Phase 3 - 10 Engineering Projects | 2027-11-03 | 2027-12-08 | BE | 19.55 | Medium | Not started | Task: Module 10: Engineering Project Management System. Deliverable: Closed defects
6.3.14 UAT support with GWMC department | Phase 3 - 10 Engineering Projects | 2027-11-26 | 2027-12-14 | BA | 11.5 | Medium | Not started | Task: Module 10: Engineering Project Management System. Deliverable: UAT sign-off
6.3.15 Training material and department training | Phase 3 - 10 Engineering Projects | 2027-12-01 | 2027-12-17 | TRN | 9.2 | Medium | Not started | Task: Module 10: Engineering Project Management System. Deliverable: Trained users, manuals in Telugu and English
6.4.1 Process validation workshops and to-be sign-off | Phase 3 - 12 Street Lights | 2027-07-06 | 2027-07-27 | BA | 8.05 | Medium | Not started | Task: Module 12: Street Light Management. Deliverable: Signed process maps
6.4.2 LLD, data model and API/event contracts | Phase 3 - 12 Street Lights | 2027-07-21 | 2027-08-11 | ARC | 6.9 | Medium | Not started | Task: Module 12: Street Light Management. Deliverable: LLD, OpenAPI, schemas
6.4.3 UX wireframes and UI design | Phase 3 - 12 Street Lights | 2027-07-21 | 2027-08-11 | FE | 5.75 | Medium | Not started | Task: Module 12: Street Light Management. Deliverable: Approved wireframes
6.4.4 Database schema, domain logic and APIs | Phase 3 - 12 Street Lights | 2027-08-09 | 2027-10-22 | BE | 21.85 | Medium | Not started | Task: Module 12: Street Light Management. Deliverable: Service build
6.4.5 Workflows (BPMN) and rules (DMN) configuration | Phase 3 - 12 Street Lights | 2027-08-31 | 2027-10-25 | BE | 9.2 | Medium | Not started | Task: Module 12: Street Light Management. Deliverable: Deployed workflows and decision tables
6.4.6 Staff console screens | Phase 3 - 12 Street Lights | 2027-08-20 | 2027-11-02 | FE | 18.4 | Medium | Not started | Task: Module 12: Street Light Management. Deliverable: Staff screens
6.4.7 Field app tasks (offline) | Phase 3 - 12 Street Lights | 2027-09-08 | 2027-11-02 | MOB | 9.2 | Medium | Not started | Task: Module 12: Street Light Management. Deliverable: Field app plug-in
6.4.8 GIS layers, map views and spatial checks | Phase 3 - 12 Street Lights | 2027-08-20 | 2027-10-22 | GIS | 6.9 | Medium | Not started | Task: Module 12: Street Light Management. Deliverable: Layers and map features
6.4.9 Module interfaces (8 I-xx links): events and APIs | Phase 3 - 12 Street Lights | 2027-09-17 | 2027-11-08 | BE | 13.8 | Medium | Not started | Task: Module 12: Street Light Management. Deliverable: Contract-tested interfaces
6.4.10 External system adapters (2) | Phase 3 - 12 Street Lights | 2027-09-08 | 2027-11-08 | BE | 13.8 | Medium | Not started | Task: Module 12: Street Light Management. Deliverable: Adapters tested with provider sandboxes
6.4.11 Reports, dashboards, notices and templates (all active languages) | Phase 3 - 12 Street Lights | 2027-10-06 | 2027-11-10 | BE | 5.75 | Medium | Not started | Task: Module 12: Street Light Management. Deliverable: Reports and templates
6.4.12 System integration testing | Phase 3 - 12 Street Lights | 2027-10-28 | 2027-11-25 | QA | 13.8 | Medium | Not started | Task: Module 12: Street Light Management. Deliverable: SIT report
6.4.13 Defect fixing and regression | Phase 3 - 12 Street Lights | 2027-11-03 | 2027-12-08 | BE | 11.5 | Medium | Not started | Task: Module 12: Street Light Management. Deliverable: Closed defects
6.4.14 UAT support with GWMC department | Phase 3 - 12 Street Lights | 2027-11-26 | 2027-12-14 | BA | 6.9 | Medium | Not started | Task: Module 12: Street Light Management. Deliverable: UAT sign-off
6.4.15 Training material and department training | Phase 3 - 12 Street Lights | 2027-12-01 | 2027-12-17 | TRN | 5.75 | Medium | Not started | Task: Module 12: Street Light Management. Deliverable: Trained users, manuals in Telugu and English
6.5.1 Process validation workshops and to-be sign-off | Phase 3 - 14 Parks & Horticulture | 2027-07-06 | 2027-07-27 | BA | 11.5 | Medium | Not started | Task: Module 14: Parks & Horticulture Management. Deliverable: Signed process maps
6.5.2 LLD, data model and API/event contracts | Phase 3 - 14 Parks & Horticulture | 2027-07-21 | 2027-08-11 | ARC | 9.2 | Medium | Not started | Task: Module 14: Parks & Horticulture Management. Deliverable: LLD, OpenAPI, schemas
6.5.3 UX wireframes and UI design | Phase 3 - 14 Parks & Horticulture | 2027-07-21 | 2027-08-11 | FE | 8.05 | Medium | Not started | Task: Module 14: Parks & Horticulture Management. Deliverable: Approved wireframes
6.5.4 Database schema, domain logic and APIs | Phase 3 - 14 Parks & Horticulture | 2027-08-09 | 2027-10-22 | BE | 31.05 | Medium | Not started | Task: Module 14: Parks & Horticulture Management. Deliverable: Service build
6.5.5 Workflows (BPMN) and rules (DMN) configuration | Phase 3 - 14 Parks & Horticulture | 2027-08-31 | 2027-10-25 | BE | 14.95 | Medium | Not started | Task: Module 14: Parks & Horticulture Management. Deliverable: Deployed workflows and decision tables
6.5.6 Staff console screens | Phase 3 - 14 Parks & Horticulture | 2027-08-20 | 2027-11-02 | FE | 25.3 | Medium | Not started | Task: Module 14: Parks & Horticulture Management. Deliverable: Staff screens
6.5.7 Citizen portal and app services | Phase 3 - 14 Parks & Horticulture | 2027-09-08 | 2027-11-02 | FE | 18.4 | Medium | Not started | Task: Module 14: Parks & Horticulture Management. Deliverable: Citizen services live in MyGWMC
6.5.8 Field app tasks (offline) | Phase 3 - 14 Parks & Horticulture | 2027-09-08 | 2027-11-02 | MOB | 12.65 | Medium | Not started | Task: Module 14: Parks & Horticulture Management. Deliverable: Field app plug-in
6.5.9 GIS layers, map views and spatial checks | Phase 3 - 14 Parks & Horticulture | 2027-08-20 | 2027-10-22 | GIS | 10.35 | Medium | Not started | Task: Module 14: Parks & Horticulture Management. Deliverable: Layers and map features
6.5.10 Module interfaces (6 I-xx links): events and APIs | Phase 3 - 14 Parks & Horticulture | 2027-09-17 | 2027-11-08 | BE | 10.35 | Medium | Not started | Task: Module 14: Parks & Horticulture Management. Deliverable: Contract-tested interfaces
6.5.11 Reports, dashboards, notices and templates (all active languages) | Phase 3 - 14 Parks & Horticulture | 2027-10-06 | 2027-11-10 | BE | 11.5 | Medium | Not started | Task: Module 14: Parks & Horticulture Management. Deliverable: Reports and templates
6.5.12 System integration testing | Phase 3 - 14 Parks & Horticulture | 2027-10-28 | 2027-11-25 | QA | 20.7 | Medium | Not started | Task: Module 14: Parks & Horticulture Management. Deliverable: SIT report
6.5.13 Defect fixing and regression | Phase 3 - 14 Parks & Horticulture | 2027-11-03 | 2027-12-08 | BE | 17.25 | Medium | Not started | Task: Module 14: Parks & Horticulture Management. Deliverable: Closed defects
6.5.14 UAT support with GWMC department | Phase 3 - 14 Parks & Horticulture | 2027-11-26 | 2027-12-14 | BA | 9.2 | Medium | Not started | Task: Module 14: Parks & Horticulture Management. Deliverable: UAT sign-off
6.5.15 Training material and department training | Phase 3 - 14 Parks & Horticulture | 2027-12-01 | 2027-12-17 | TRN | 8.05 | Medium | Not started | Task: Module 14: Parks & Horticulture Management. Deliverable: Trained users, manuals in Telugu and English
6.6.1 Process validation workshops and to-be sign-off | Phase 3 - 17 Inventory & Stores | 2027-07-06 | 2027-07-27 | BA | 11.5 | Medium | Not started | Task: Module 17: Inventory & Stores Management. Deliverable: Signed process maps
6.6.2 LLD, data model and API/event contracts | Phase 3 - 17 Inventory & Stores | 2027-07-21 | 2027-08-11 | ARC | 9.2 | Medium | Not started | Task: Module 17: Inventory & Stores Management. Deliverable: LLD, OpenAPI, schemas
6.6.3 UX wireframes and UI design | Phase 3 - 17 Inventory & Stores | 2027-07-21 | 2027-08-11 | FE | 8.05 | Medium | Not started | Task: Module 17: Inventory & Stores Management. Deliverable: Approved wireframes
6.6.4 Database schema, domain logic and APIs | Phase 3 - 17 Inventory & Stores | 2027-08-09 | 2027-10-22 | BE | 29.9 | Medium | Not started | Task: Module 17: Inventory & Stores Management. Deliverable: Service build
6.6.5 Workflows (BPMN) and rules (DMN) configuration | Phase 3 - 17 Inventory & Stores | 2027-08-31 | 2027-10-25 | BE | 12.65 | Medium | Not started | Task: Module 17: Inventory & Stores Management. Deliverable: Deployed workflows and decision tables
6.6.6 Staff console screens | Phase 3 - 17 Inventory & Stores | 2027-08-20 | 2027-11-02 | FE | 24.15 | Medium | Not started | Task: Module 17: Inventory & Stores Management. Deliverable: Staff screens
6.6.7 Module interfaces (3 I-xx links): events and APIs | Phase 3 - 17 Inventory & Stores | 2027-09-17 | 2027-11-08 | BE | 4.6 | Medium | Not started | Task: Module 17: Inventory & Stores Management. Deliverable: Contract-tested interfaces
6.6.8 External system adapters (1) | Phase 3 - 17 Inventory & Stores | 2027-09-08 | 2027-11-08 | BE | 6.9 | Medium | Not started | Task: Module 17: Inventory & Stores Management. Deliverable: Adapters tested with provider sandboxes
6.6.9 Reports, dashboards, notices and templates (all active languages) | Phase 3 - 17 Inventory & Stores | 2027-10-06 | 2027-11-10 | BE | 9.2 | Medium | Not started | Task: Module 17: Inventory & Stores Management. Deliverable: Reports and templates
6.6.10 System integration testing | Phase 3 - 17 Inventory & Stores | 2027-10-28 | 2027-11-25 | QA | 19.55 | Medium | Not started | Task: Module 17: Inventory & Stores Management. Deliverable: SIT report
6.6.11 Defect fixing and regression | Phase 3 - 17 Inventory & Stores | 2027-11-03 | 2027-12-08 | BE | 16.1 | Medium | Not started | Task: Module 17: Inventory & Stores Management. Deliverable: Closed defects
6.6.12 UAT support with GWMC department | Phase 3 - 17 Inventory & Stores | 2027-11-26 | 2027-12-14 | BA | 9.2 | Medium | Not started | Task: Module 17: Inventory & Stores Management. Deliverable: UAT sign-off
6.6.13 Training material and department training | Phase 3 - 17 Inventory & Stores | 2027-12-01 | 2027-12-17 | TRN | 8.05 | Medium | Not started | Task: Module 17: Inventory & Stores Management. Deliverable: Trained users, manuals in Telugu and English
6.7.1 End-to-end integration testing (SRS E2E scenarios) | Phase 3 - Release | 2027-11-16 | 2027-12-02 | QA | 34.5 | Medium | Not started | Task: Phase 3 release, testing and go-live. Deliverable: E2E report
6.7.2 Performance and load testing (NFR-001/002) | Phase 3 - Release | 2027-11-22 | 2027-12-02 | QA | 18.4 | Medium | Not started | Task: Phase 3 release, testing and go-live. Deliverable: Performance report
6.7.3 Security audit by CERT-In empanelled auditor and fixes | Phase 3 - Release | 2027-11-26 | 2027-12-14 | QA | 24.15 | Medium | Not started | Task: Phase 3 release, testing and go-live. Deliverable: Audit certificate
6.7.4 Training of trainers and end-user training programme | Phase 3 - Release | 2027-12-03 | 2027-12-21 | TRN | 23 | Medium | Not started | Task: Phase 3 release, testing and go-live. Deliverable: Training attendance and feedback
6.7.5 Migration dress rehearsal and cut-over plan | Phase 3 - Release | 2027-12-08 | 2027-12-17 | DATA | 14.95 | Medium | Not started | Task: Phase 3 release, testing and go-live. Deliverable: Cut-over runbook
6.7.6 Production deployment and cut-over | Phase 3 - Release | 2027-12-20 | 2027-12-22 | DEV | 18.4 | Medium | Not started | Task: Phase 3 release, testing and go-live. Deliverable: Go-live
6.8 M3: Phase 3 go-live | Phase 3 - Phase 3: Field operations | 2027-12-22 | 2027-12-22 | 0 | 0 | Important | Not started | Task: Phase 3: Field operations. Deliverable:
6.8.1 Hypercare and stabilisation (4 weeks) | Phase 3 - Release | 2027-12-22 | 2028-01-18 | BE | 33.35 | Medium | Not started | Task: M3: Phase 3 go-live. Deliverable: Hypercare closure report
6.9 Phase 3 acceptance and sign-off | Phase 3 - Phase 3: Field operations | 2028-01-19 | 2028-01-19 | 0 | 0 | Important | Not started | Task: Phase 3: Field operations. Deliverable:
6.10 Phase 3 build mid-point (next phase design may start) | Phase 3 - Phase 3: Field operations | 2027-10-06 | 2027-10-06 | 0 | 0 | Important | Not started | Task: Phase 3: Field operations. Deliverable:
7.1.1 Org hierarchy and approvers move to HR (workflow switch-over) | Phase 4 - Platform | 2027-11-24 | 2028-02-14 | BE | 17.25 | Medium | Not started | Task: Platform increments for Phase 4. Deliverable: Platform release
7.1.2 Legal and asset interim records migrated (I-30, I-42) | Phase 4 - Platform | 2027-11-24 | 2028-02-14 | DATA | 13.8 | Medium | Not started | Task: Platform increments for Phase 4. Deliverable: Platform release
7.1.3 Full cross-module MIS and state dashboards | Phase 4 - Platform | 2027-11-24 | 2028-02-14 | BE | 28.75 | Medium | Not started | Task: Platform increments for Phase 4. Deliverable: Platform release
7.2.1 Process validation workshops and to-be sign-off | Phase 4 - 8 Payroll & HR | 2027-11-05 | 2027-11-26 | BA | 12.65 | Medium | Not started | Task: Module 8: Payroll & HR Management. Deliverable: Signed process maps
7.2.2 LLD, data model and API/event contracts | Phase 4 - 8 Payroll & HR | 2027-11-22 | 2027-12-13 | ARC | 11.5 | Medium | Not started | Task: Module 8: Payroll & HR Management. Deliverable: LLD, OpenAPI, schemas
7.2.3 UX wireframes and UI design | Phase 4 - 8 Payroll & HR | 2027-11-22 | 2027-12-13 | FE | 9.2 | Medium | Not started | Task: Module 8: Payroll & HR Management. Deliverable: Approved wireframes
7.2.4 Database schema, domain logic and APIs | Phase 4 - 8 Payroll & HR | 2027-12-09 | 2028-02-23 | BE | 32.2 | Medium | Not started | Task: Module 8: Payroll & HR Management. Deliverable: Service build
7.2.5 Workflows (BPMN) and rules (DMN) configuration | Phase 4 - 8 Payroll & HR | 2027-12-31 | 2028-02-24 | BE | 16.1 | Medium | Not started | Task: Module 8: Payroll & HR Management. Deliverable: Deployed workflows and decision tables
7.2.6 Staff console screens | Phase 4 - 8 Payroll & HR | 2027-12-22 | 2028-03-03 | FE | 27.6 | Medium | Not started | Task: Module 8: Payroll & HR Management. Deliverable: Staff screens
7.2.7 Field app tasks (offline) | Phase 4 - 8 Payroll & HR | 2028-01-10 | 2028-03-03 | MOB | 12.65 | Medium | Not started | Task: Module 8: Payroll & HR Management. Deliverable: Field app plug-in
7.2.8 Module interfaces (4 I-xx links): events and APIs | Phase 4 - 8 Payroll & HR | 2028-01-19 | 2028-03-09 | BE | 6.9 | Medium | Not started | Task: Module 8: Payroll & HR Management. Deliverable: Contract-tested interfaces
7.2.9 External system adapters (2) | Phase 4 - 8 Payroll & HR | 2028-01-10 | 2028-03-09 | BE | 13.8 | Medium | Not started | Task: Module 8: Payroll & HR Management. Deliverable: Adapters tested with provider sandboxes
7.2.10 Reports, dashboards, notices and templates (all active languages) | Phase 4 - 8 Payroll & HR | 2028-02-07 | 2028-03-13 | BE | 11.5 | Medium | Not started | Task: Module 8: Payroll & HR Management. Deliverable: Reports and templates
7.2.11 Data migration: employee master and service books | Phase 4 - 8 Payroll & HR | 2027-12-31 | 2028-03-22 | DATA | 14.95 | Medium | Not started | Task: Module 8: Payroll & HR Management. Deliverable: Migration scripts and reconciliation report
7.2.12 System integration testing | Phase 4 - 8 Payroll & HR | 2028-02-29 | 2028-03-28 | QA | 21.85 | Medium | Not started | Task: Module 8: Payroll & HR Management. Deliverable: SIT report
7.2.13 Defect fixing and regression | Phase 4 - 8 Payroll & HR | 2028-03-06 | 2028-04-10 | BE | 19.55 | Medium | Not started | Task: Module 8: Payroll & HR Management. Deliverable: Closed defects
7.2.14 UAT support with GWMC department | Phase 4 - 8 Payroll & HR | 2028-03-29 | 2028-04-14 | BA | 11.5 | Medium | Not started | Task: Module 8: Payroll & HR Management. Deliverable: UAT sign-off
7.2.15 Training material and department training | Phase 4 - 8 Payroll & HR | 2028-04-03 | 2028-04-19 | TRN | 9.2 | Medium | Not started | Task: Module 8: Payroll & HR Management. Deliverable: Trained users, manuals in Telugu and English
7.3.1 Process validation workshops and to-be sign-off | Phase 4 - 15 Municipal Property | 2027-11-05 | 2027-11-26 | BA | 10.35 | Medium | Not started | Task: Module 15: Municipal Property Management. Deliverable: Signed process maps
7.3.2 LLD, data model and API/event contracts | Phase 4 - 15 Municipal Property | 2027-11-22 | 2027-12-13 | ARC | 9.2 | Medium | Not started | Task: Module 15: Municipal Property Management. Deliverable: LLD, OpenAPI, schemas
7.3.3 UX wireframes and UI design | Phase 4 - 15 Municipal Property | 2027-11-22 | 2027-12-13 | FE | 6.9 | Medium | Not started | Task: Module 15: Municipal Property Management. Deliverable: Approved wireframes
7.3.4 Database schema, domain logic and APIs | Phase 4 - 15 Municipal Property | 2027-12-09 | 2028-02-23 | BE | 25.3 | Medium | Not started | Task: Module 15: Municipal Property Management. Deliverable: Service build
7.3.5 Workflows (BPMN) and rules (DMN) configuration | Phase 4 - 15 Municipal Property | 2027-12-31 | 2028-02-24 | BE | 12.65 | Medium | Not started | Task: Module 15: Municipal Property Management. Deliverable: Deployed workflows and decision tables
7.3.6 Staff console screens | Phase 4 - 15 Municipal Property | 2027-12-22 | 2028-03-03 | FE | 21.85 | Medium | Not started | Task: Module 15: Municipal Property Management. Deliverable: Staff screens
7.3.7 Field app tasks (offline) | Phase 4 - 15 Municipal Property | 2028-01-10 | 2028-03-03 | MOB | 10.35 | Medium | Not started | Task: Module 15: Municipal Property Management. Deliverable: Field app plug-in
7.3.8 GIS layers, map views and spatial checks | Phase 4 - 15 Municipal Property | 2027-12-22 | 2028-02-23 | GIS | 9.2 | Medium | Not started | Task: Module 15: Municipal Property Management. Deliverable: Layers and map features
7.3.9 Module interfaces (12 I-xx links): events and APIs | Phase 4 - 15 Municipal Property | 2028-01-19 | 2028-03-09 | BE | 20.7 | Medium | Not started | Task: Module 15: Municipal Property Management. Deliverable: Contract-tested interfaces
7.3.10 Reports, dashboards, notices and templates (all active languages) | Phase 4 - 15 Municipal Property | 2028-02-07 | 2028-03-13 | BE | 9.2 | Medium | Not started | Task: Module 15: Municipal Property Management. Deliverable: Reports and templates
7.3.11 Data migration: asset and lease registers | Phase 4 - 15 Municipal Property | 2027-12-31 | 2028-03-22 | DATA | 12.65 | Medium | Not started | Task: Module 15: Municipal Property Management. Deliverable: Migration scripts and reconciliation report
7.3.12 System integration testing | Phase 4 - 15 Municipal Property | 2028-02-29 | 2028-03-28 | QA | 17.25 | Medium | Not started | Task: Module 15: Municipal Property Management. Deliverable: SIT report
7.3.13 Defect fixing and regression | Phase 4 - 15 Municipal Property | 2028-03-06 | 2028-04-10 | BE | 14.95 | Medium | Not started | Task: Module 15: Municipal Property Management. Deliverable: Closed defects
7.3.14 UAT support with GWMC department | Phase 4 - 15 Municipal Property | 2028-03-29 | 2028-04-14 | BA | 9.2 | Medium | Not started | Task: Module 15: Municipal Property Management. Deliverable: UAT sign-off
7.3.15 Training material and department training | Phase 4 - 15 Municipal Property | 2028-04-03 | 2028-04-19 | TRN | 6.9 | Medium | Not started | Task: Module 15: Municipal Property Management. Deliverable: Trained users, manuals in Telugu and English
7.4.1 Process validation workshops and to-be sign-off | Phase 4 - 16 Legal Cases | 2027-11-05 | 2027-11-26 | BA | 11.5 | Medium | Not started | Task: Module 16: Legal Case Management. Deliverable: Signed process maps
7.4.2 LLD, data model and API/event contracts | Phase 4 - 16 Legal Cases | 2027-11-22 | 2027-12-13 | ARC | 9.2 | Medium | Not started | Task: Module 16: Legal Case Management. Deliverable: LLD, OpenAPI, schemas
7.4.3 UX wireframes and UI design | Phase 4 - 16 Legal Cases | 2027-11-22 | 2027-12-13 | FE | 8.05 | Medium | Not started | Task: Module 16: Legal Case Management. Deliverable: Approved wireframes
7.4.4 Database schema, domain logic and APIs | Phase 4 - 16 Legal Cases | 2027-12-09 | 2028-02-23 | BE | 29.9 | Medium | Not started | Task: Module 16: Legal Case Management. Deliverable: Service build
7.4.5 Workflows (BPMN) and rules (DMN) configuration | Phase 4 - 16 Legal Cases | 2027-12-31 | 2028-02-24 | BE | 12.65 | Medium | Not started | Task: Module 16: Legal Case Management. Deliverable: Deployed workflows and decision tables
7.4.6 Staff console screens | Phase 4 - 16 Legal Cases | 2027-12-22 | 2028-03-03 | FE | 24.15 | Medium | Not started | Task: Module 16: Legal Case Management. Deliverable: Staff screens
7.4.7 Module interfaces (4 I-xx links): events and APIs | Phase 4 - 16 Legal Cases | 2028-01-19 | 2028-03-09 | BE | 6.9 | Medium | Not started | Task: Module 16: Legal Case Management. Deliverable: Contract-tested interfaces
7.4.8 External system adapters (1) | Phase 4 - 16 Legal Cases | 2028-01-10 | 2028-03-09 | BE | 6.9 | Medium | Not started | Task: Module 16: Legal Case Management. Deliverable: Adapters tested with provider sandboxes
7.4.9 Reports, dashboards, notices and templates (all active languages) | Phase 4 - 16 Legal Cases | 2028-02-07 | 2028-03-13 | BE | 9.2 | Medium | Not started | Task: Module 16: Legal Case Management. Deliverable: Reports and templates
7.4.10 Data migration: pending court cases | Phase 4 - 16 Legal Cases | 2027-12-31 | 2028-03-22 | DATA | 13.8 | Medium | Not started | Task: Module 16: Legal Case Management. Deliverable: Migration scripts and reconciliation report
7.4.11 System integration testing | Phase 4 - 16 Legal Cases | 2028-02-29 | 2028-03-28 | QA | 19.55 | Medium | Not started | Task: Module 16: Legal Case Management. Deliverable: SIT report
7.4.12 Defect fixing and regression | Phase 4 - 16 Legal Cases | 2028-03-06 | 2028-04-10 | BE | 16.1 | Medium | Not started | Task: Module 16: Legal Case Management. Deliverable: Closed defects
7.4.13 UAT support with GWMC department | Phase 4 - 16 Legal Cases | 2028-03-29 | 2028-04-14 | BA | 9.2 | Medium | Not started | Task: Module 16: Legal Case Management. Deliverable: UAT sign-off
7.4.14 Training material and department training | Phase 4 - 16 Legal Cases | 2028-04-03 | 2028-04-19 | TRN | 8.05 | Medium | Not started | Task: Module 16: Legal Case Management. Deliverable: Trained users, manuals in Telugu and English
7.5.1 Process validation workshops and to-be sign-off | Phase 4 - 19 Government Schemes | 2027-11-05 | 2027-11-26 | BA | 9.2 | Medium | Not started | Task: Module 19: Government Schemes Management. Deliverable: Signed process maps
7.5.2 LLD, data model and API/event contracts | Phase 4 - 19 Government Schemes | 2027-11-22 | 2027-12-13 | ARC | 9.2 | Medium | Not started | Task: Module 19: Government Schemes Management. Deliverable: LLD, OpenAPI, schemas
7.5.3 UX wireframes and UI design | Phase 4 - 19 Government Schemes | 2027-11-22 | 2027-12-13 | FE | 5.75 | Medium | Not started | Task: Module 19: Government Schemes Management. Deliverable: Approved wireframes
7.5.4 Database schema, domain logic and APIs | Phase 4 - 19 Government Schemes | 2027-12-09 | 2028-02-23 | BE | 24.15 | Medium | Not started | Task: Module 19: Government Schemes Management. Deliverable: Service build
7.5.5 Workflows (BPMN) and rules (DMN) configuration | Phase 4 - 19 Government Schemes | 2027-12-31 | 2028-02-24 | BE | 11.5 | Medium | Not started | Task: Module 19: Government Schemes Management. Deliverable: Deployed workflows and decision tables
7.5.6 Staff console screens | Phase 4 - 19 Government Schemes | 2027-12-22 | 2028-03-03 | FE | 20.7 | Medium | Not started | Task: Module 19: Government Schemes Management. Deliverable: Staff screens
7.5.7 Citizen portal and app services | Phase 4 - 19 Government Schemes | 2028-01-10 | 2028-03-03 | FE | 13.8 | Medium | Not started | Task: Module 19: Government Schemes Management. Deliverable: Citizen services live in MyGWMC
7.5.8 Field app tasks (offline) | Phase 4 - 19 Government Schemes | 2028-01-10 | 2028-03-03 | MOB | 9.2 | Medium | Not started | Task: Module 19: Government Schemes Management. Deliverable: Field app plug-in
7.5.9 Module interfaces (5 I-xx links): events and APIs | Phase 4 - 19 Government Schemes | 2028-01-19 | 2028-03-09 | BE | 9.2 | Medium | Not started | Task: Module 19: Government Schemes Management. Deliverable: Contract-tested interfaces
7.5.10 External system adapters (2) | Phase 4 - 19 Government Schemes | 2028-01-10 | 2028-03-09 | BE | 13.8 | Medium | Not started | Task: Module 19: Government Schemes Management. Deliverable: Adapters tested with provider sandboxes
7.5.11 Reports, dashboards, notices and templates (all active languages) | Phase 4 - 19 Government Schemes | 2028-02-07 | 2028-03-13 | BE | 8.05 | Medium | Not started | Task: Module 19: Government Schemes Management. Deliverable: Reports and templates
7.5.12 Data migration: existing beneficiaries | Phase 4 - 19 Government Schemes | 2027-12-31 | 2028-03-22 | DATA | 10.35 | Medium | Not started | Task: Module 19: Government Schemes Management. Deliverable: Migration scripts and reconciliation report
7.5.13 System integration testing | Phase 4 - 19 Government Schemes | 2028-02-29 | 2028-03-28 | QA | 16.1 | Medium | Not started | Task: Module 19: Government Schemes Management. Deliverable: SIT report
7.5.14 Defect fixing and regression | Phase 4 - 19 Government Schemes | 2028-03-06 | 2028-04-10 | BE | 14.95 | Medium | Not started | Task: Module 19: Government Schemes Management. Deliverable: Closed defects
7.5.15 UAT support with GWMC department | Phase 4 - 19 Government Schemes | 2028-03-29 | 2028-04-14 | BA | 9.2 | Medium | Not started | Task: Module 19: Government Schemes Management. Deliverable: UAT sign-off
7.5.16 Training material and department training | Phase 4 - 19 Government Schemes | 2028-04-03 | 2028-04-19 | TRN | 5.75 | Medium | Not started | Task: Module 19: Government Schemes Management. Deliverable: Trained users, manuals in Telugu and English
7.6.1 End-to-end integration testing (SRS E2E scenarios) | Phase 4 - Release | 2028-03-17 | 2028-04-04 | QA | 34.5 | Medium | Not started | Task: Phase 4 release, testing and go-live. Deliverable: E2E report
7.6.2 Performance and load testing (NFR-001/002) | Phase 4 - Release | 2028-03-23 | 2028-04-04 | QA | 18.4 | Medium | Not started | Task: Phase 4 release, testing and go-live. Deliverable: Performance report
7.6.3 Security audit by CERT-In empanelled auditor and fixes | Phase 4 - Release | 2028-03-29 | 2028-04-14 | QA | 24.15 | Medium | Not started | Task: Phase 4 release, testing and go-live. Deliverable: Audit certificate
7.6.4 Training of trainers and end-user training programme | Phase 4 - Release | 2028-04-05 | 2028-04-21 | TRN | 23 | Medium | Not started | Task: Phase 4 release, testing and go-live. Deliverable: Training attendance and feedback
7.6.5 Migration dress rehearsal and cut-over plan | Phase 4 - Release | 2028-04-10 | 2028-04-19 | DATA | 14.95 | Medium | Not started | Task: Phase 4 release, testing and go-live. Deliverable: Cut-over runbook
7.6.6 Production deployment and cut-over | Phase 4 - Release | 2028-04-20 | 2028-04-24 | DEV | 18.4 | Medium | Not started | Task: Phase 4 release, testing and go-live. Deliverable: Go-live
7.7 M4: Phase 4 go-live | Phase 4 - Phase 4: Administration and welfare | 2028-04-24 | 2028-04-24 | 0 | 0 | Important | Not started | Task: Phase 4: Administration and welfare. Deliverable:
7.7.1 Hypercare and stabilisation (4 weeks) | Phase 4 - Release | 2028-04-24 | 2028-05-19 | BE | 33.35 | Medium | Not started | Task: M4: Phase 4 go-live. Deliverable: Hypercare closure report
7.8 Phase 4 acceptance and sign-off | Phase 4 - Phase 4: Administration and welfare | 2028-05-22 | 2028-05-22 | 0 | 0 | Important | Not started | Task: Phase 4: Administration and welfare. Deliverable:
7.9 Phase 4 build mid-point (next phase design may start) | Phase 4 - Phase 4: Administration and welfare | 2028-02-07 | 2028-02-07 | 0 | 0 | Important | Not started | Task: Phase 4: Administration and welfare. Deliverable:
8.1 Programme completion and handover to operations | Close - Programme close | 2028-07-10 | 2028-07-10 | 0 | 0 | Important | Not started | Task: Programme close. Deliverable:

## MS Project Import
ID | Name | Outline Level | Duration | Start | Finish | Predecessors | Resource Names | Work
1 | Programme management and governance | 1 | 440d | 2026-11-02 | 2028-07-07
2 | Project governance and PMO | 2 | 440d | 2026-11-02 | 2028-07-07
3 | PMO, planning, status reporting and steering committee: Phase 1 | 3 | 140d | 2026-11-02 | 2027-05-14 |  | PM | 773h
4 | PMO, planning, status reporting and steering committee: Phase 2 | 3 | 141d | 2027-03-04 | 2027-09-16 |  | PM | 782h
5 | PMO, planning, status reporting and steering committee: Phase 3 | 3 | 141d | 2027-07-06 | 2028-01-18 |  | PM | 782h
6 | PMO, planning, status reporting and steering committee: Phase 4 | 3 | 141d | 2027-11-05 | 2028-05-19 |  | PM | 782h
7 | Final stabilisation, knowledge transfer and handover | 3 | 40d | 2028-05-15 | 2028-07-07 |  | PM | 1012h
8 | Change control and quality | 2 | 400d | 2026-11-30 | 2028-06-09
9 | Change request process and impact assessments (whole programme) | 3 | 400d | 2026-11-30 | 2028-06-09 |  | PM | 460h
10 | Quality audits and phase-gate reviews (4 gates) | 3 | 300d | 2027-03-22 | 2028-05-12 |  | PM | 258h
11 | Phase 0: Inception and mobilisation | 1 | 26d | 2026-11-02 | 2026-12-07
12 | Mobilisation | 2 | 25d | 2026-11-02 | 2026-12-04
13 | Kick-off with GWMC and team onboarding | 3 | 5d | 2026-11-02 | 2026-11-06 |  | PM | 120h
14 | Tooling: repositories, CI/CD, tracker, Teams workspace | 3 | 10d | 2026-11-02 | 2026-11-13 |  | DEV | 138h
15 | Dev and test environments provisioned | 3 | 15d | 2026-11-05 | 2026-11-25 |  | DEV | 166h
16 | State Data Centre slot request and network approvals | 3 | 25d | 2026-11-02 | 2026-12-04 |  | PM | 110h
17 | Requirements and design baseline | 2 | 20d | 2026-11-09 | 2026-12-04
18 | SRS walkthroughs with GWMC departments (Phase 1 modules) | 3 | 15d | 2026-11-09 | 2026-11-27 | 13 | BA | 313h
19 | GWMC Deployment SRS open items closed for Phase 1 | 3 | 15d | 2026-11-16 | 2026-12-04 |  | BA | 138h
20 | Architecture decisions (ADR-001 to 016) reviewed and signed off | 3 | 15d | 2026-11-09 | 2026-11-27 |  | ARC | 166h
21 | UX research, design system and accessibility baseline | 3 | 20d | 2026-11-09 | 2026-12-04 |  | FE | 175h
22 | Data migration strategy and legacy data assessment | 3 | 15d | 2026-11-16 | 2026-12-04 |  | DATA | 147h
23 | M0: Inception complete, Phase 1 build starts | 2 | 0d | 2026-12-07 | 2026-12-07 | 18,20
24 | Platform foundation (built in Phase 1) | 1 | 84d | 2026-11-16 | 2027-03-11
25 | Identity, OTP, CAPTCHA and step-up (Keycloak) | 2 | 51d | 2026-11-16 | 2027-01-25
26 | Detailed design and contracts | 3 | 10d | 2026-11-16 | 2026-11-27 | 20 | ARC | 64h
27 | Build and unit tests | 3 | 30d | 2026-11-30 | 2027-01-08 |  | BE | 350h
28 | Component, security and contract tests | 3 | 13d | 2027-01-07 | 2027-01-25 |  | QA | 120h
29 | Tenant, configuration console and Telangana state pack | 2 | 50d | 2026-11-24 | 2027-02-01
30 | Detailed design and contracts | 3 | 10d | 2026-11-24 | 2026-12-07 | 20 | ARC | 46h
31 | Build and unit tests | 3 | 30d | 2026-12-08 | 2027-01-18 |  | BE | 396h
32 | Component, security and contract tests | 3 | 13d | 2027-01-14 | 2027-02-01 |  | QA | 92h
33 | Workflow and rules engine (Flowable BPMN and DMN) | 2 | 50d | 2026-11-24 | 2027-02-01
34 | Detailed design and contracts | 3 | 10d | 2026-11-24 | 2026-12-07 | 20 | ARC | 64h
35 | Build and unit tests | 3 | 30d | 2026-12-08 | 2027-01-18 |  | BE | 313h
36 | Component, security and contract tests | 3 | 13d | 2027-01-14 | 2027-02-01 |  | QA | 101h
37 | API gateway, BFFs and service mesh | 2 | 39d | 2026-11-16 | 2027-01-07
38 | Detailed design and contracts | 3 | 8d | 2026-11-16 | 2026-11-25 | 20 | ARC | 46h
39 | Build and unit tests | 3 | 24d | 2026-11-26 | 2026-12-29 |  | BE | 212h
40 | Component, security and contract tests | 3 | 10d | 2026-12-25 | 2027-01-07 |  | QA | 55h
41 | Event bus, outbox/inbox library and schema registry | 2 | 39d | 2026-11-16 | 2027-01-07
42 | Detailed design and contracts | 3 | 8d | 2026-11-16 | 2026-11-25 | 20 | ARC | 55h
43 | Build and unit tests | 3 | 24d | 2026-11-26 | 2026-12-29 |  | BE | 193h
44 | Component, security and contract tests | 3 | 10d | 2026-12-25 | 2027-01-07 |  | QA | 64h
45 | Payment service, gateway, UPI and BBPS | 2 | 44d | 2026-12-09 | 2027-02-08
46 | Detailed design and contracts | 3 | 9d | 2026-12-09 | 2026-12-21 | 20 | ARC | 46h
47 | Build and unit tests | 3 | 27d | 2026-12-22 | 2027-01-27 |  | BE | 294h
48 | Component, security and contract tests | 3 | 11d | 2027-01-25 | 2027-02-08 |  | QA | 120h
49 | Notification service (DLT SMS, WhatsApp, email, IVRS) | 2 | 39d | 2026-12-09 | 2027-02-01
50 | Detailed design and contracts | 3 | 8d | 2026-12-09 | 2026-12-18 | 20 | ARC | 37h
51 | Build and unit tests | 3 | 24d | 2026-12-21 | 2027-01-21 |  | BE | 184h
52 | Component, security and contract tests | 3 | 10d | 2027-01-19 | 2027-02-01 |  | QA | 74h
53 | GIS base: PostGIS, GeoServer, base map, imagery, ward layers | 2 | 56d | 2026-11-24 | 2027-02-09
54 | Detailed design and contracts | 3 | 11d | 2026-11-24 | 2026-12-08 | 20 | ARC | 28h
55 | Build and unit tests | 3 | 34d | 2026-12-09 | 2027-01-25 |  | GIS | 442h
56 | Component, security and contract tests | 3 | 14d | 2027-01-21 | 2027-02-09 |  | QA | 55h
57 | Document pipeline: OCR, translation, eSign, anchoring, DigiLocker | 2 | 56d | 2026-12-01 | 2027-02-16
58 | Detailed design and contracts | 3 | 11d | 2026-12-01 | 2026-12-15 | 20 | ARC | 74h
59 | Build and unit tests | 3 | 34d | 2026-12-16 | 2027-02-01 |  | BE | 331h
60 | Component, security and contract tests | 3 | 14d | 2027-01-28 | 2027-02-16 |  | QA | 129h
61 | Search service (OpenSearch, Indic analysers) | 2 | 40d | 2026-12-16 | 2027-02-09
62 | Detailed design and contracts | 3 | 8d | 2026-12-16 | 2026-12-25 | 20 | ARC | 37h
63 | Build and unit tests | 3 | 24d | 2026-12-28 | 2027-01-28 |  | BE | 129h
64 | Component, security and contract tests | 3 | 10d | 2027-01-27 | 2027-02-09 |  | QA | 55h
65 | Audit service, SIEM feed and CERT-In logging | 2 | 40d | 2026-12-16 | 2027-02-09
66 | Detailed design and contracts | 3 | 8d | 2026-12-16 | 2026-12-25 | 20 | ARC | 28h
67 | Build and unit tests | 3 | 24d | 2026-12-28 | 2027-01-28 |  | BE | 166h
68 | Component, security and contract tests | 3 | 10d | 2027-01-27 | 2027-02-09 |  | QA | 46h
69 | Aadhaar Data Vault with HSM | 2 | 34d | 2026-12-16 | 2027-02-01
70 | Detailed design and contracts | 3 | 7d | 2026-12-16 | 2026-12-24 | 20 | ARC | 37h
71 | Build and unit tests | 3 | 20d | 2026-12-25 | 2027-01-21 |  | BE | 147h
72 | Component, security and contract tests | 3 | 8d | 2027-01-21 | 2027-02-01 |  | QA | 46h
73 | Adapter hub framework | 2 | 33d | 2026-12-01 | 2027-01-14
74 | Detailed design and contracts | 3 | 7d | 2026-12-01 | 2026-12-09 | 20 | ARC | 37h
75 | Build and unit tests | 3 | 20d | 2026-12-10 | 2027-01-06 |  | BE | 101h
76 | Component, security and contract tests | 3 | 8d | 2027-01-05 | 2027-01-14 |  | QA | 37h
77 | Citizen portal and app shell (MyGWMC branding, 22-language i18n) | 2 | 56d | 2026-12-01 | 2027-02-16
78 | Detailed design and contracts | 3 | 11d | 2026-12-01 | 2026-12-15 | 20 | ARC | 18h
79 | Build and unit tests | 3 | 34d | 2026-12-16 | 2027-02-01 |  | FE | 488h
80 | Component, security and contract tests | 3 | 14d | 2027-01-28 | 2027-02-16 |  | QA | 92h
81 | Staff console shell, work queues and maps | 2 | 45d | 2026-12-01 | 2027-02-01
82 | Detailed design and contracts | 3 | 9d | 2026-12-01 | 2026-12-11 | 20 | ARC | 18h
83 | Build and unit tests | 3 | 27d | 2026-12-14 | 2027-01-19 |  | FE | 202h
84 | Component, security and contract tests | 3 | 11d | 2027-01-18 | 2027-02-01 |  | QA | 55h
85 | Field app shell and offline sync service | 2 | 51d | 2026-12-09 | 2027-02-17
86 | Detailed design and contracts | 3 | 10d | 2026-12-09 | 2026-12-22 | 20 | ARC | 28h
87 | Build and unit tests | 3 | 30d | 2026-12-23 | 2027-02-02 |  | MOB | 350h
88 | Component, security and contract tests | 3 | 13d | 2027-02-01 | 2027-02-17 |  | QA | 83h
89 | Reporting warehouse, ELT and Superset dashboards | 2 | 45d | 2027-01-08 | 2027-03-11
90 | Detailed design and contracts | 3 | 9d | 2027-01-08 | 2027-01-20 | 20 | ARC | 37h
91 | Build and unit tests | 3 | 27d | 2027-01-21 | 2027-02-26 |  | BE | 248h
92 | Component, security and contract tests | 3 | 11d | 2027-02-25 | 2027-03-11 |  | QA | 55h
93 | Observability: OpenTelemetry, Prometheus, Grafana, Loki | 2 | 39d | 2026-11-24 | 2027-01-15
94 | Detailed design and contracts | 3 | 8d | 2026-11-24 | 2026-12-03 | 20 | ARC | 18h
95 | Build and unit tests | 3 | 24d | 2026-12-03 | 2027-01-05 |  | DEV | 138h
96 | Component, security and contract tests | 3 | 10d | 2027-01-04 | 2027-01-15 |  | QA | 28h
97 | Infrastructure and security (production) | 2 | 45d | 2026-12-28 | 2027-02-26
98 | Production cluster in State Data Centre | 3 | 30d | 2026-12-28 | 2027-02-05 |  | DEV | 193h
99 | DR site, replication and backup | 3 | 25d | 2027-01-25 | 2027-02-26 |  | DEV | 129h
100 | HSM, secrets (OpenBao), hardening and network policies | 3 | 25d | 2027-01-11 | 2027-02-12 |  | DEV | 120h
101 | SIEM (Wazuh) and NTP to NIC/NPL time servers | 3 | 20d | 2027-01-25 | 2027-02-19 |  | DEV | 74h
102 | Phase 1: Foundation and revenue core | 1 | 120d | 2026-11-30 | 2027-05-14
103 | Module 1: Property Tax & Revenue Management | 2 | 101d | 2026-11-30 | 2027-04-19
104 | Process validation workshops and to-be sign-off | 3 | 13d | 2026-11-30 | 2026-12-16 | 23 | BA | 175h
105 | LLD, data model and API/event contracts | 3 | 13d | 2026-12-11 | 2026-12-29 | 104 | ARC | 166h
106 | UX wireframes and UI design | 3 | 13d | 2026-12-11 | 2026-12-29 | 104 | FE | 138h
107 | Database schema, domain logic and APIs | 3 | 47d | 2026-12-28 | 2027-03-02 | 105 | BE | 488h
108 | Workflows (BPMN) and rules (DMN) configuration | 3 | 34d | 2027-01-15 | 2027-03-03 | 105 | BE | 230h
109 | Staff console screens | 3 | 45d | 2027-01-07 | 2027-03-10 | 106 | FE | 405h
110 | Citizen portal and app services | 3 | 34d | 2027-01-22 | 2027-03-10 | 106 | FE | 294h
111 | Field app tasks (offline) | 3 | 34d | 2027-01-22 | 2027-03-10 | 106 | MOB | 193h
112 | GIS layers, map views and spatial checks | 3 | 39d | 2027-01-07 | 2027-03-02 | 105 | GIS | 166h
113 | Module interfaces (16 I-xx links): events and APIs | 3 | 31d | 2027-02-01 | 2027-03-15 | 107 | BE | 221h
114 | External system adapters (7) | 3 | 37d | 2027-01-22 | 2027-03-15 | 105 | BE | 386h
115 | Reports, dashboards, notices and templates (all active languages) | 3 | 22d | 2027-02-16 | 2027-03-17 | 107 | BE | 166h
116 | Data migration: CDMA property, demand and arrears | 3 | 50d | 2027-01-15 | 2027-03-25 | 105 | DATA | 230h
117 | System integration testing | 3 | 18d | 2027-03-05 | 2027-03-30 | 107,109 | QA | 331h
118 | Defect fixing and regression | 3 | 22d | 2027-03-11 | 2027-04-09 | 117 | BE | 276h
119 | UAT support with GWMC department | 3 | 11d | 2027-03-31 | 2027-04-14 | 117 | BA | 166h
120 | Training material and department training | 3 | 11d | 2027-04-05 | 2027-04-19 | 119 | TRN | 138h
121 | Module 2: Water, Sewerage & Utility Billing | 2 | 101d | 2026-11-30 | 2027-04-19
122 | Process validation workshops and to-be sign-off | 3 | 13d | 2026-11-30 | 2026-12-16 | 23 | BA | 156h
123 | LLD, data model and API/event contracts | 3 | 13d | 2026-12-11 | 2026-12-29 | 122 | ARC | 147h
124 | UX wireframes and UI design | 3 | 13d | 2026-12-11 | 2026-12-29 | 122 | FE | 120h
125 | Database schema, domain logic and APIs | 3 | 47d | 2026-12-28 | 2027-03-02 | 123 | BE | 460h
126 | Workflows (BPMN) and rules (DMN) configuration | 3 | 34d | 2027-01-15 | 2027-03-03 | 123 | BE | 221h
127 | Staff console screens | 3 | 45d | 2027-01-07 | 2027-03-10 | 124 | FE | 386h
128 | Citizen portal and app services | 3 | 34d | 2027-01-22 | 2027-03-10 | 124 | FE | 276h
129 | Field app tasks (offline) | 3 | 34d | 2027-01-22 | 2027-03-10 | 124 | MOB | 184h
130 | GIS layers, map views and spatial checks | 3 | 39d | 2027-01-07 | 2027-03-02 | 123 | GIS | 156h
131 | Module interfaces (17 I-xx links): events and APIs | 3 | 31d | 2027-02-01 | 2027-03-15 | 125 | BE | 239h
132 | External system adapters (2) | 3 | 37d | 2027-01-22 | 2027-03-15 | 123 | BE | 110h
133 | Reports, dashboards, notices and templates (all active languages) | 3 | 22d | 2027-02-16 | 2027-03-17 | 125 | BE | 156h
134 | Data migration: consumer, meter and arrears data | 3 | 50d | 2027-01-15 | 2027-03-25 | 123 | DATA | 212h
135 | System integration testing | 3 | 18d | 2027-03-05 | 2027-03-30 | 125,127 | QA | 313h
136 | Defect fixing and regression | 3 | 22d | 2027-03-11 | 2027-04-09 | 135 | BE | 258h
137 | UAT support with GWMC department | 3 | 11d | 2027-03-31 | 2027-04-14 | 135 | BA | 147h
138 | Training material and department training | 3 | 11d | 2027-04-05 | 2027-04-19 | 137 | TRN | 120h
139 | Module 3: Citizen Service Desk, Grievance & RTI | 2 | 101d | 2026-11-30 | 2027-04-19
140 | Process validation workshops and to-be sign-off | 3 | 13d | 2026-11-30 | 2026-12-16 | 23 | BA | 147h
141 | LLD, data model and API/event contracts | 3 | 13d | 2026-12-11 | 2026-12-29 | 140 | ARC | 147h
142 | UX wireframes and UI design | 3 | 13d | 2026-12-11 | 2026-12-29 | 140 | FE | 110h
143 | Database schema, domain logic and APIs | 3 | 47d | 2026-12-28 | 2027-03-02 | 141 | BE | 414h
144 | Workflows (BPMN) and rules (DMN) configuration | 3 | 34d | 2027-01-15 | 2027-03-03 | 141 | BE | 193h
145 | Staff console screens | 3 | 45d | 2027-01-07 | 2027-03-10 | 142 | FE | 350h
146 | Citizen portal and app services | 3 | 34d | 2027-01-22 | 2027-03-10 | 142 | FE | 248h
147 | GIS layers, map views and spatial checks | 3 | 39d | 2027-01-07 | 2027-03-02 | 141 | GIS | 138h
148 | Module interfaces (5 I-xx links): events and APIs | 3 | 31d | 2027-02-01 | 2027-03-15 | 143 | BE | 74h
149 | External system adapters (6) | 3 | 37d | 2027-01-22 | 2027-03-15 | 141 | BE | 331h
150 | Reports, dashboards, notices and templates (all active languages) | 3 | 22d | 2027-02-16 | 2027-03-17 | 143 | BE | 138h
151 | System integration testing | 3 | 18d | 2027-03-05 | 2027-03-30 | 143,145 | QA | 276h
152 | Defect fixing and regression | 3 | 22d | 2027-03-11 | 2027-04-09 | 151 | BE | 239h
153 | UAT support with GWMC department | 3 | 11d | 2027-03-31 | 2027-04-14 | 151 | BA | 147h
154 | Training material and department training | 3 | 11d | 2027-04-05 | 2027-04-19 | 153 | TRN | 110h
155 | Module 4: Finance & Accounting | 2 | 101d | 2026-11-30 | 2027-04-19
156 | Process validation workshops and to-be sign-off | 3 | 13d | 2026-11-30 | 2026-12-16 | 23 | BA | 147h
157 | LLD, data model and API/event contracts | 3 | 13d | 2026-12-11 | 2026-12-29 | 156 | ARC | 147h
158 | UX wireframes and UI design | 3 | 13d | 2026-12-11 | 2026-12-29 | 156 | FE | 110h
159 | Database schema, domain logic and APIs | 3 | 47d | 2026-12-28 | 2027-03-02 | 157 | BE | 414h
160 | Workflows (BPMN) and rules (DMN) configuration | 3 | 34d | 2027-01-15 | 2027-03-03 | 157 | BE | 193h
161 | Staff console screens | 3 | 45d | 2027-01-07 | 2027-03-10 | 158 | FE | 350h
162 | Module interfaces (10 I-xx links): events and APIs | 3 | 31d | 2027-02-01 | 2027-03-15 | 159 | BE | 138h
163 | External system adapters (5) | 3 | 37d | 2027-01-22 | 2027-03-15 | 157 | BE | 276h
164 | Reports, dashboards, notices and templates (all active languages) | 3 | 22d | 2027-02-16 | 2027-03-17 | 159 | BE | 138h
165 | Data migration: opening balances, budgets, vendors | 3 | 50d | 2027-01-15 | 2027-03-25 | 157 | DATA | 193h
166 | System integration testing | 3 | 18d | 2027-03-05 | 2027-03-30 | 159,161 | QA | 276h
167 | Defect fixing and regression | 3 | 22d | 2027-03-11 | 2027-04-09 | 166 | BE | 239h
168 | UAT support with GWMC department | 3 | 11d | 2027-03-31 | 2027-04-14 | 166 | BA | 147h
169 | Training material and department training | 3 | 11d | 2027-04-05 | 2027-04-19 | 168 | TRN | 110h
170 | Module 9: Document Management System | 2 | 101d | 2026-11-30 | 2027-04-19
171 | Process validation workshops and to-be sign-off | 3 | 13d | 2026-11-30 | 2026-12-16 | 23 | BA | 147h
172 | LLD, data model and API/event contracts | 3 | 13d | 2026-12-11 | 2026-12-29 | 171 | ARC | 147h
173 | UX wireframes and UI design | 3 | 13d | 2026-12-11 | 2026-12-29 | 171 | FE | 110h
174 | Database schema, domain logic and APIs | 3 | 47d | 2026-12-28 | 2027-03-02 | 172 | BE | 423h
175 | Workflows (BPMN) and rules (DMN) configuration | 3 | 34d | 2027-01-15 | 2027-03-03 | 172 | BE | 193h
176 | Staff console screens | 3 | 45d | 2027-01-07 | 2027-03-10 | 173 | FE | 350h
177 | Citizen portal and app services | 3 | 34d | 2027-01-22 | 2027-03-10 | 173 | FE | 248h
178 | Module interfaces (3 I-xx links): events and APIs | 3 | 31d | 2027-02-01 | 2027-03-15 | 174 | BE | 37h
179 | External system adapters (5) | 3 | 37d | 2027-01-22 | 2027-03-15 | 172 | BE | 276h
180 | Reports, dashboards, notices and templates (all active languages) | 3 | 22d | 2027-02-16 | 2027-03-17 | 174 | BE | 138h
181 | Data migration: legacy files for scanning and indexing | 3 | 50d | 2027-01-15 | 2027-03-25 | 172 | DATA | 193h
182 | System integration testing | 3 | 18d | 2027-03-05 | 2027-03-30 | 174,176 | QA | 276h
183 | Defect fixing and regression | 3 | 22d | 2027-03-11 | 2027-04-09 | 182 | BE | 239h
184 | UAT support with GWMC department | 3 | 11d | 2027-03-31 | 2027-04-14 | 182 | BA | 147h
185 | Training material and department training | 3 | 11d | 2027-04-05 | 2027-04-19 | 184 | TRN | 110h
186 | Phase 1 release, testing and go-live | 2 | 22d | 2027-03-23 | 2027-04-21
187 | End-to-end integration testing (SRS E2E scenarios) | 3 | 11d | 2027-03-23 | 2027-04-06 | 117,135,151,166,182 | QA | 276h
188 | Performance and load testing (NFR-001/002) | 3 | 8d | 2027-03-26 | 2027-04-06 |  | QA | 147h
189 | Security audit by CERT-In empanelled auditor and fixes | 3 | 11d | 2027-03-31 | 2027-04-14 |  | QA | 193h
190 | Training of trainers and end-user training programme | 3 | 11d | 2027-04-07 | 2027-04-21 |  | TRN | 184h
191 | Migration dress rehearsal and cut-over plan | 3 | 7d | 2027-04-09 | 2027-04-19 |  | DATA | 120h
192 | Production deployment and cut-over | 3 | 2d | 2027-04-20 | 2027-04-21 | 189,191,119,137,153,168,184 | DEV | 147h
193 | M1: Phase 1 go-live | 2 | 0d | 2027-04-22 | 2027-04-22 | 192
194 | Hypercare and stabilisation (4 weeks) | 3 | 17d | 2027-04-22 | 2027-05-14 | 193 | BE | 267h
195 | Phase 1 acceptance and sign-off | 2 | 0d | 2027-05-14 | 2027-05-14 | 194
196 | Phase 1 build mid-point (next phase design may start) | 2 | 0d | 2027-02-16 | 2027-02-16
197 | Phase 2: Regulation and licensing | 1 | 142d | 2027-03-04 | 2027-09-17
198 | Platform increments for Phase 2 | 2 | 59d | 2027-03-23 | 2027-06-11
199 | GIS elevation and 3D service (DTM, DSM, 3D Tiles) | 3 | 59d | 2027-03-23 | 2027-06-11 |  | GIS | 377h
200 | Hand over ward and planning layers to Town Planning (I-20) | 3 | 59d | 2027-03-23 | 2027-06-11 |  | GIS | 120h
201 | Module 5: Trade Licence Management | 2 | 119d | 2027-03-04 | 2027-08-17
202 | Process validation workshops and to-be sign-off | 3 | 16d | 2027-03-04 | 2027-03-25 | 196 | BA | 129h
203 | LLD, data model and API/event contracts | 3 | 16d | 2027-03-19 | 2027-04-09 | 202 | ARC | 110h
204 | UX wireframes and UI design | 3 | 16d | 2027-03-19 | 2027-04-09 | 202 | FE | 101h
205 | Database schema, domain logic and APIs | 3 | 55d | 2027-04-07 | 2027-06-22 | 203 | BE | 359h
206 | Workflows (BPMN) and rules (DMN) configuration | 3 | 40d | 2027-04-29 | 2027-06-23 | 203 | BE | 166h
207 | Staff console screens | 3 | 53d | 2027-04-20 | 2027-07-01 | 204 | FE | 294h
208 | Citizen portal and app services | 3 | 40d | 2027-05-07 | 2027-07-01 | 204 | FE | 221h
209 | Field app tasks (offline) | 3 | 40d | 2027-05-07 | 2027-07-01 | 204 | MOB | 147h
210 | GIS layers, map views and spatial checks | 3 | 46d | 2027-04-20 | 2027-06-22 | 203 | GIS | 120h
211 | Module interfaces (10 I-xx links): events and APIs | 3 | 37d | 2027-05-18 | 2027-07-07 | 205 | BE | 138h
212 | External system adapters (3) | 3 | 44d | 2027-05-07 | 2027-07-07 | 203 | BE | 166h
213 | Reports, dashboards, notices and templates (all active languages) | 3 | 26d | 2027-06-04 | 2027-07-09 | 205 | BE | 120h
214 | Data migration: existing licences | 3 | 59d | 2027-04-29 | 2027-07-20 | 203 | DATA | 175h
215 | System integration testing | 3 | 21d | 2027-06-28 | 2027-07-26 | 205,207 | QA | 239h
216 | Defect fixing and regression | 3 | 26d | 2027-07-02 | 2027-08-06 | 215 | BE | 193h
217 | UAT support with GWMC department | 3 | 13d | 2027-07-27 | 2027-08-12 | 215 | BA | 110h
218 | Training material and department training | 3 | 13d | 2027-07-30 | 2027-08-17 | 217 | TRN | 101h
219 | Module 6: User Charges Management | 2 | 119d | 2027-03-04 | 2027-08-17
220 | Process validation workshops and to-be sign-off | 3 | 16d | 2027-03-04 | 2027-03-25 | 196 | BA | 110h
221 | LLD, data model and API/event contracts | 3 | 16d | 2027-03-19 | 2027-04-09 | 220 | ARC | 110h
222 | UX wireframes and UI design | 3 | 16d | 2027-03-19 | 2027-04-09 | 220 | FE | 83h
223 | Database schema, domain logic and APIs | 3 | 55d | 2027-04-07 | 2027-06-22 | 221 | BE | 313h
224 | Workflows (BPMN) and rules (DMN) configuration | 3 | 40d | 2027-04-29 | 2027-06-23 | 221 | BE | 138h
225 | Staff console screens | 3 | 53d | 2027-04-20 | 2027-07-01 | 222 | FE | 258h
226 | Citizen portal and app services | 3 | 40d | 2027-05-07 | 2027-07-01 | 222 | FE | 193h
227 | Field app tasks (offline) | 3 | 40d | 2027-05-07 | 2027-07-01 | 222 | MOB | 129h
228 | GIS layers, map views and spatial checks | 3 | 46d | 2027-04-20 | 2027-06-22 | 221 | GIS | 101h
229 | Module interfaces (12 I-xx links): events and APIs | 3 | 37d | 2027-05-18 | 2027-07-07 | 223 | BE | 166h
230 | External system adapters (2) | 3 | 44d | 2027-05-07 | 2027-07-07 | 221 | BE | 110h
231 | Reports, dashboards, notices and templates (all active languages) | 3 | 26d | 2027-06-04 | 2027-07-09 | 223 | BE | 92h
232 | Data migration: existing user-charge accounts | 3 | 59d | 2027-04-29 | 2027-07-20 | 221 | DATA | 147h
233 | System integration testing | 3 | 21d | 2027-06-28 | 2027-07-26 | 223,225 | QA | 202h
234 | Defect fixing and regression | 3 | 26d | 2027-07-02 | 2027-08-06 | 233 | BE | 175h
235 | UAT support with GWMC department | 3 | 13d | 2027-07-27 | 2027-08-12 | 233 | BA | 110h
236 | Training material and department training | 3 | 13d | 2027-07-30 | 2027-08-17 | 235 | TRN | 83h
237 | Module 11: Building Permission Management / Integration | 2 | 119d | 2027-03-04 | 2027-08-17
238 | Process validation workshops and to-be sign-off | 3 | 16d | 2027-03-04 | 2027-03-25 | 196 | BA | 110h
239 | LLD, data model and API/event contracts | 3 | 16d | 2027-03-19 | 2027-04-09 | 238 | ARC | 110h
240 | UX wireframes and UI design | 3 | 16d | 2027-03-19 | 2027-04-09 | 238 | FE | 83h
241 | Database schema, domain logic and APIs | 3 | 55d | 2027-04-07 | 2027-06-22 | 239 | BE | 322h
242 | Workflows (BPMN) and rules (DMN) configuration | 3 | 40d | 2027-04-29 | 2027-06-23 | 239 | BE | 156h
243 | Staff console screens | 3 | 53d | 2027-04-20 | 2027-07-01 | 240 | FE | 267h
244 | Citizen portal and app services | 3 | 40d | 2027-05-07 | 2027-07-01 | 240 | FE | 193h
245 | Field app tasks (offline) | 3 | 40d | 2027-05-07 | 2027-07-01 | 240 | MOB | 129h
246 | GIS layers, map views and spatial checks | 3 | 46d | 2027-04-20 | 2027-06-22 | 239 | GIS | 110h
247 | Module interfaces (14 I-xx links): events and APIs | 3 | 37d | 2027-05-18 | 2027-07-07 | 241 | BE | 193h
248 | External system adapters (10) | 3 | 44d | 2027-05-07 | 2027-07-07 | 239 | BE | 552h
249 | Reports, dashboards, notices and templates (all active languages) | 3 | 26d | 2027-06-04 | 2027-07-09 | 241 | BE | 110h
250 | Data migration: permits in TG-bPASS | 3 | 59d | 2027-04-29 | 2027-07-20 | 239 | DATA | 147h
251 | System integration testing | 3 | 21d | 2027-06-28 | 2027-07-26 | 241,243 | QA | 221h
252 | Defect fixing and regression | 3 | 26d | 2027-07-02 | 2027-08-06 | 251 | BE | 184h
253 | UAT support with GWMC department | 3 | 13d | 2027-07-27 | 2027-08-12 | 251 | BA | 110h
254 | Training material and department training | 3 | 13d | 2027-07-30 | 2027-08-17 | 253 | TRN | 83h
255 | Module 13: Town Planning | 2 | 119d | 2027-03-04 | 2027-08-17
256 | Process validation workshops and to-be sign-off | 3 | 16d | 2027-03-04 | 2027-03-25 | 196 | BA | 110h
257 | LLD, data model and API/event contracts | 3 | 16d | 2027-03-19 | 2027-04-09 | 256 | ARC | 110h
258 | UX wireframes and UI design | 3 | 16d | 2027-03-19 | 2027-04-09 | 256 | FE | 83h
259 | Database schema, domain logic and APIs | 3 | 55d | 2027-04-07 | 2027-06-22 | 257 | BE | 322h
260 | Workflows (BPMN) and rules (DMN) configuration | 3 | 40d | 2027-04-29 | 2027-06-23 | 257 | BE | 156h
261 | Staff console screens | 3 | 53d | 2027-04-20 | 2027-07-01 | 258 | FE | 267h
262 | Citizen portal and app services | 3 | 40d | 2027-05-07 | 2027-07-01 | 258 | FE | 193h
263 | Field app tasks (offline) | 3 | 40d | 2027-05-07 | 2027-07-01 | 258 | MOB | 129h
264 | GIS layers, map views and spatial checks | 3 | 46d | 2027-04-20 | 2027-06-22 | 257 | GIS | 110h
265 | Module interfaces (11 I-xx links): events and APIs | 3 | 37d | 2027-05-18 | 2027-07-07 | 259 | BE | 147h
266 | External system adapters (3) | 3 | 44d | 2027-05-07 | 2027-07-07 | 257 | BE | 166h
267 | Reports, dashboards, notices and templates (all active languages) | 3 | 26d | 2027-06-04 | 2027-07-09 | 259 | BE | 110h
268 | Data migration: layouts and LRS records | 3 | 59d | 2027-04-29 | 2027-07-20 | 257 | DATA | 147h
269 | System integration testing | 3 | 21d | 2027-06-28 | 2027-07-26 | 259,261 | QA | 221h
270 | Defect fixing and regression | 3 | 26d | 2027-07-02 | 2027-08-06 | 269 | BE | 184h
271 | UAT support with GWMC department | 3 | 13d | 2027-07-27 | 2027-08-12 | 269 | BA | 110h
272 | Training material and department training | 3 | 13d | 2027-07-30 | 2027-08-17 | 271 | TRN | 83h
273 | Module 18: Fire NOC Management | 2 | 119d | 2027-03-04 | 2027-08-17
274 | Process validation workshops and to-be sign-off | 3 | 16d | 2027-03-04 | 2027-03-25 | 196 | BA | 92h
275 | LLD, data model and API/event contracts | 3 | 16d | 2027-03-19 | 2027-04-09 | 274 | ARC | 74h
276 | UX wireframes and UI design | 3 | 16d | 2027-03-19 | 2027-04-09 | 274 | FE | 64h
277 | Database schema, domain logic and APIs | 3 | 55d | 2027-04-07 | 2027-06-22 | 275 | BE | 239h
278 | Workflows (BPMN) and rules (DMN) configuration | 3 | 40d | 2027-04-29 | 2027-06-23 | 275 | BE | 120h
279 | Staff console screens | 3 | 53d | 2027-04-20 | 2027-07-01 | 276 | FE | 202h
280 | Citizen portal and app services | 3 | 40d | 2027-05-07 | 2027-07-01 | 276 | FE | 138h
281 | Field app tasks (offline) | 3 | 40d | 2027-05-07 | 2027-07-01 | 276 | MOB | 92h
282 | GIS layers, map views and spatial checks | 3 | 46d | 2027-04-20 | 2027-06-22 | 275 | GIS | 83h
283 | Module interfaces (11 I-xx links): events and APIs | 3 | 37d | 2027-05-18 | 2027-07-07 | 277 | BE | 147h
284 | External system adapters (3) | 3 | 44d | 2027-05-07 | 2027-07-07 | 275 | BE | 166h
285 | Reports, dashboards, notices and templates (all active languages) | 3 | 26d | 2027-06-04 | 2027-07-09 | 277 | BE | 92h
286 | System integration testing | 3 | 21d | 2027-06-28 | 2027-07-26 | 277,279 | QA | 166h
287 | Defect fixing and regression | 3 | 26d | 2027-07-02 | 2027-08-06 | 286 | BE | 138h
288 | UAT support with GWMC department | 3 | 13d | 2027-07-27 | 2027-08-12 | 286 | BA | 74h
289 | Training material and department training | 3 | 13d | 2027-07-30 | 2027-08-17 | 288 | TRN | 64h
290 | Phase 2 release, testing and go-live | 2 | 27d | 2027-07-15 | 2027-08-20
291 | End-to-end integration testing (SRS E2E scenarios) | 3 | 13d | 2027-07-15 | 2027-08-02 | 215,233,251,269,286 | QA | 276h
292 | Performance and load testing (NFR-001/002) | 3 | 9d | 2027-07-21 | 2027-08-02 |  | QA | 147h
293 | Security audit by CERT-In empanelled auditor and fixes | 3 | 13d | 2027-07-27 | 2027-08-12 |  | QA | 193h
294 | Training of trainers and end-user training programme | 3 | 13d | 2027-08-03 | 2027-08-19 |  | TRN | 184h
295 | Migration dress rehearsal and cut-over plan | 3 | 8d | 2027-08-06 | 2027-08-17 |  | DATA | 120h
296 | Production deployment and cut-over | 3 | 3d | 2027-08-18 | 2027-08-20 | 293,295,217,235,253,271,288 | DEV | 147h
297 | M2: Phase 2 go-live | 2 | 0d | 2027-08-20 | 2027-08-20 | 296
298 | Hypercare and stabilisation (4 weeks) | 3 | 20d | 2027-08-20 | 2027-09-16 | 297 | BE | 267h
299 | Phase 2 acceptance and sign-off | 2 | 0d | 2027-09-17 | 2027-09-17 | 298
300 | Phase 2 build mid-point (next phase design may start) | 2 | 0d | 2027-06-04 | 2027-06-04
301 | Phase 3: Field operations | 1 | 142d | 2027-07-06 | 2028-01-19
302 | Platform increments for Phase 3 | 2 | 59d | 2027-07-23 | 2027-10-13
303 | Field app scale-up and offline sync load test | 3 | 59d | 2027-07-23 | 2027-10-13 |  | MOB | 193h
304 | AVLS, CCMS and IoT ingestion pipeline | 3 | 59d | 2027-07-23 | 2027-10-13 |  | BE | 184h
305 | Road register moves to Engineering (I-32) | 3 | 59d | 2027-07-23 | 2027-10-13 |  | GIS | 110h
306 | Module 7: Solid Waste Management | 2 | 119d | 2027-07-06 | 2027-12-17
307 | Process validation workshops and to-be sign-off | 3 | 16d | 2027-07-06 | 2027-07-27 | 300 | BA | 92h
308 | LLD, data model and API/event contracts | 3 | 16d | 2027-07-21 | 2027-08-11 | 307 | ARC | 74h
309 | UX wireframes and UI design | 3 | 16d | 2027-07-21 | 2027-08-11 | 307 | FE | 64h
310 | Database schema, domain logic and APIs | 3 | 55d | 2027-08-09 | 2027-10-22 | 308 | BE | 248h
311 | Workflows (BPMN) and rules (DMN) configuration | 3 | 40d | 2027-08-31 | 2027-10-25 | 308 | BE | 120h
312 | Staff console screens | 3 | 53d | 2027-08-20 | 2027-11-02 | 309 | FE | 202h
313 | Field app tasks (offline) | 3 | 40d | 2027-09-08 | 2027-11-02 | 309 | MOB | 101h
314 | GIS layers, map views and spatial checks | 3 | 46d | 2027-08-20 | 2027-10-22 | 308 | GIS | 83h
315 | Module interfaces (13 I-xx links): events and APIs | 3 | 37d | 2027-09-17 | 2027-11-08 | 310 | BE | 184h
316 | External system adapters (3) | 3 | 44d | 2027-09-08 | 2027-11-08 | 308 | BE | 166h
317 | Reports, dashboards, notices and templates (all active languages) | 3 | 26d | 2027-10-06 | 2027-11-10 | 310 | BE | 92h
318 | System integration testing | 3 | 21d | 2027-10-28 | 2027-11-25 | 310,312 | QA | 166h
319 | Defect fixing and regression | 3 | 26d | 2027-11-03 | 2027-12-08 | 318 | BE | 138h
320 | UAT support with GWMC department | 3 | 13d | 2027-11-26 | 2027-12-14 | 318 | BA | 74h
321 | Training material and department training | 3 | 13d | 2027-12-01 | 2027-12-17 | 320 | TRN | 64h
322 | Module 10: Engineering Project Management System | 2 | 119d | 2027-07-06 | 2027-12-17
323 | Process validation workshops and to-be sign-off | 3 | 16d | 2027-07-06 | 2027-07-27 | 300 | BA | 101h
324 | LLD, data model and API/event contracts | 3 | 16d | 2027-07-21 | 2027-08-11 | 323 | ARC | 92h
325 | UX wireframes and UI design | 3 | 16d | 2027-07-21 | 2027-08-11 | 323 | FE | 74h
326 | Database schema, domain logic and APIs | 3 | 55d | 2027-08-09 | 2027-10-22 | 324 | BE | 285h
327 | Workflows (BPMN) and rules (DMN) configuration | 3 | 40d | 2027-08-31 | 2027-10-25 | 324 | BE | 129h
328 | Staff console screens | 3 | 53d | 2027-08-20 | 2027-11-02 | 325 | FE | 239h
329 | Field app tasks (offline) | 3 | 40d | 2027-09-08 | 2027-11-02 | 325 | MOB | 110h
330 | GIS layers, map views and spatial checks | 3 | 46d | 2027-08-20 | 2027-10-22 | 324 | GIS | 92h
331 | Module interfaces (9 I-xx links): events and APIs | 3 | 37d | 2027-09-17 | 2027-11-08 | 326 | BE | 129h
332 | External system adapters (2) | 3 | 44d | 2027-09-08 | 2027-11-08 | 324 | BE | 110h
333 | Reports, dashboards, notices and templates (all active languages) | 3 | 26d | 2027-10-06 | 2027-11-10 | 326 | BE | 92h
334 | System integration testing | 3 | 21d | 2027-10-28 | 2027-11-25 | 326,328 | QA | 184h
335 | Defect fixing and regression | 3 | 26d | 2027-11-03 | 2027-12-08 | 334 | BE | 156h
336 | UAT support with GWMC department | 3 | 13d | 2027-11-26 | 2027-12-14 | 334 | BA | 92h
337 | Training material and department training | 3 | 13d | 2027-12-01 | 2027-12-17 | 336 | TRN | 74h
338 | Module 12: Street Light Management | 2 | 119d | 2027-07-06 | 2027-12-17
339 | Process validation workshops and to-be sign-off | 3 | 16d | 2027-07-06 | 2027-07-27 | 300 | BA | 64h
340 | LLD, data model and API/event contracts | 3 | 16d | 2027-07-21 | 2027-08-11 | 339 | ARC | 55h
341 | UX wireframes and UI design | 3 | 16d | 2027-07-21 | 2027-08-11 | 339 | FE | 46h
342 | Database schema, domain logic and APIs | 3 | 55d | 2027-08-09 | 2027-10-22 | 340 | BE | 175h
343 | Workflows (BPMN) and rules (DMN) configuration | 3 | 40d | 2027-08-31 | 2027-10-25 | 340 | BE | 74h
344 | Staff console screens | 3 | 53d | 2027-08-20 | 2027-11-02 | 341 | FE | 147h
345 | Field app tasks (offline) | 3 | 40d | 2027-09-08 | 2027-11-02 | 341 | MOB | 74h
346 | GIS layers, map views and spatial checks | 3 | 46d | 2027-08-20 | 2027-10-22 | 340 | GIS | 55h
347 | Module interfaces (8 I-xx links): events and APIs | 3 | 37d | 2027-09-17 | 2027-11-08 | 342 | BE | 110h
348 | External system adapters (2) | 3 | 44d | 2027-09-08 | 2027-11-08 | 340 | BE | 110h
349 | Reports, dashboards, notices and templates (all active languages) | 3 | 26d | 2027-10-06 | 2027-11-10 | 342 | BE | 46h
350 | System integration testing | 3 | 21d | 2027-10-28 | 2027-11-25 | 342,344 | QA | 110h
351 | Defect fixing and regression | 3 | 26d | 2027-11-03 | 2027-12-08 | 350 | BE | 92h
352 | UAT support with GWMC department | 3 | 13d | 2027-11-26 | 2027-12-14 | 350 | BA | 55h
353 | Training material and department training | 3 | 13d | 2027-12-01 | 2027-12-17 | 352 | TRN | 46h
354 | Module 14: Parks & Horticulture Management | 2 | 119d | 2027-07-06 | 2027-12-17
355 | Process validation workshops and to-be sign-off | 3 | 16d | 2027-07-06 | 2027-07-27 | 300 | BA | 92h
356 | LLD, data model and API/event contracts | 3 | 16d | 2027-07-21 | 2027-08-11 | 355 | ARC | 74h
357 | UX wireframes and UI design | 3 | 16d | 2027-07-21 | 2027-08-11 | 355 | FE | 64h
358 | Database schema, domain logic and APIs | 3 | 55d | 2027-08-09 | 2027-10-22 | 356 | BE | 248h
359 | Workflows (BPMN) and rules (DMN) configuration | 3 | 40d | 2027-08-31 | 2027-10-25 | 356 | BE | 120h
360 | Staff console screens | 3 | 53d | 2027-08-20 | 2027-11-02 | 357 | FE | 202h
361 | Citizen portal and app services | 3 | 40d | 2027-09-08 | 2027-11-02 | 357 | FE | 147h
362 | Field app tasks (offline) | 3 | 40d | 2027-09-08 | 2027-11-02 | 357 | MOB | 101h
363 | GIS layers, map views and spatial checks | 3 | 46d | 2027-08-20 | 2027-10-22 | 356 | GIS | 83h
364 | Module interfaces (6 I-xx links): events and APIs | 3 | 37d | 2027-09-17 | 2027-11-08 | 358 | BE | 83h
365 | Reports, dashboards, notices and templates (all active languages) | 3 | 26d | 2027-10-06 | 2027-11-10 | 358 | BE | 92h
366 | System integration testing | 3 | 21d | 2027-10-28 | 2027-11-25 | 358,360 | QA | 166h
367 | Defect fixing and regression | 3 | 26d | 2027-11-03 | 2027-12-08 | 366 | BE | 138h
368 | UAT support with GWMC department | 3 | 13d | 2027-11-26 | 2027-12-14 | 366 | BA | 74h
369 | Training material and department training | 3 | 13d | 2027-12-01 | 2027-12-17 | 368 | TRN | 64h
370 | Module 17: Inventory & Stores Management | 2 | 119d | 2027-07-06 | 2027-12-17
371 | Process validation workshops and to-be sign-off | 3 | 16d | 2027-07-06 | 2027-07-27 | 300 | BA | 92h
372 | LLD, data model and API/event contracts | 3 | 16d | 2027-07-21 | 2027-08-11 | 371 | ARC | 74h
373 | UX wireframes and UI design | 3 | 16d | 2027-07-21 | 2027-08-11 | 371 | FE | 64h
374 | Database schema, domain logic and APIs | 3 | 55d | 2027-08-09 | 2027-10-22 | 372 | BE | 239h
375 | Workflows (BPMN) and rules (DMN) configuration | 3 | 40d | 2027-08-31 | 2027-10-25 | 372 | BE | 101h
376 | Staff console screens | 3 | 53d | 2027-08-20 | 2027-11-02 | 373 | FE | 193h
377 | Module interfaces (3 I-xx links): events and APIs | 3 | 37d | 2027-09-17 | 2027-11-08 | 374 | BE | 37h
378 | External system adapters (1) | 3 | 44d | 2027-09-08 | 2027-11-08 | 372 | BE | 55h
379 | Reports, dashboards, notices and templates (all active languages) | 3 | 26d | 2027-10-06 | 2027-11-10 | 374 | BE | 74h
380 | System integration testing | 3 | 21d | 2027-10-28 | 2027-11-25 | 374,376 | QA | 156h
381 | Defect fixing and regression | 3 | 26d | 2027-11-03 | 2027-12-08 | 380 | BE | 129h
382 | UAT support with GWMC department | 3 | 13d | 2027-11-26 | 2027-12-14 | 380 | BA | 74h
383 | Training material and department training | 3 | 13d | 2027-12-01 | 2027-12-17 | 382 | TRN | 64h
384 | Phase 3 release, testing and go-live | 2 | 27d | 2027-11-16 | 2027-12-22
385 | End-to-end integration testing (SRS E2E scenarios) | 3 | 13d | 2027-11-16 | 2027-12-02 | 318,334,350,366,380 | QA | 276h
386 | Performance and load testing (NFR-001/002) | 3 | 9d | 2027-11-22 | 2027-12-02 |  | QA | 147h
387 | Security audit by CERT-In empanelled auditor and fixes | 3 | 13d | 2027-11-26 | 2027-12-14 |  | QA | 193h
388 | Training of trainers and end-user training programme | 3 | 13d | 2027-12-03 | 2027-12-21 |  | TRN | 184h
389 | Migration dress rehearsal and cut-over plan | 3 | 8d | 2027-12-08 | 2027-12-17 |  | DATA | 120h
390 | Production deployment and cut-over | 3 | 3d | 2027-12-20 | 2027-12-22 | 387,389,320,336,352,368,382 | DEV | 147h
391 | M3: Phase 3 go-live | 2 | 0d | 2027-12-22 | 2027-12-22 | 390
392 | Hypercare and stabilisation (4 weeks) | 3 | 20d | 2027-12-22 | 2028-01-18 | 391 | BE | 267h
393 | Phase 3 acceptance and sign-off | 2 | 0d | 2028-01-19 | 2028-01-19 | 392
394 | Phase 3 build mid-point (next phase design may start) | 2 | 0d | 2027-10-06 | 2027-10-06
395 | Phase 4: Administration and welfare | 1 | 142d | 2027-11-05 | 2028-05-22
396 | Platform increments for Phase 4 | 2 | 59d | 2027-11-24 | 2028-02-14
397 | Org hierarchy and approvers move to HR (workflow switch-over) | 3 | 59d | 2027-11-24 | 2028-02-14 |  | BE | 138h
398 | Legal and asset interim records migrated (I-30, I-42) | 3 | 59d | 2027-11-24 | 2028-02-14 |  | DATA | 110h
399 | Full cross-module MIS and state dashboards | 3 | 59d | 2027-11-24 | 2028-02-14 |  | BE | 230h
400 | Module 8: Payroll & HR Management | 2 | 119d | 2027-11-05 | 2028-04-19
401 | Process validation workshops and to-be sign-off | 3 | 16d | 2027-11-05 | 2027-11-26 | 394 | BA | 101h
402 | LLD, data model and API/event contracts | 3 | 16d | 2027-11-22 | 2027-12-13 | 401 | ARC | 92h
403 | UX wireframes and UI design | 3 | 16d | 2027-11-22 | 2027-12-13 | 401 | FE | 74h
404 | Database schema, domain logic and APIs | 3 | 55d | 2027-12-09 | 2028-02-23 | 402 | BE | 258h
405 | Workflows (BPMN) and rules (DMN) configuration | 3 | 40d | 2027-12-31 | 2028-02-24 | 402 | BE | 129h
406 | Staff console screens | 3 | 53d | 2027-12-22 | 2028-03-03 | 403 | FE | 221h
407 | Field app tasks (offline) | 3 | 40d | 2028-01-10 | 2028-03-03 | 403 | MOB | 101h
408 | Module interfaces (4 I-xx links): events and APIs | 3 | 37d | 2028-01-19 | 2028-03-09 | 404 | BE | 55h
409 | External system adapters (2) | 3 | 44d | 2028-01-10 | 2028-03-09 | 402 | BE | 110h
410 | Reports, dashboards, notices and templates (all active languages) | 3 | 26d | 2028-02-07 | 2028-03-13 | 404 | BE | 92h
411 | Data migration: employee master and service books | 3 | 59d | 2027-12-31 | 2028-03-22 | 402 | DATA | 120h
412 | System integration testing | 3 | 21d | 2028-02-29 | 2028-03-28 | 404,406 | QA | 175h
413 | Defect fixing and regression | 3 | 26d | 2028-03-06 | 2028-04-10 | 412 | BE | 156h
414 | UAT support with GWMC department | 3 | 13d | 2028-03-29 | 2028-04-14 | 412 | BA | 92h
415 | Training material and department training | 3 | 13d | 2028-04-03 | 2028-04-19 | 414 | TRN | 74h
416 | Module 15: Municipal Property Management | 2 | 119d | 2027-11-05 | 2028-04-19
417 | Process validation workshops and to-be sign-off | 3 | 16d | 2027-11-05 | 2027-11-26 | 394 | BA | 83h
418 | LLD, data model and API/event contracts | 3 | 16d | 2027-11-22 | 2027-12-13 | 417 | ARC | 74h
419 | UX wireframes and UI design | 3 | 16d | 2027-11-22 | 2027-12-13 | 417 | FE | 55h
420 | Database schema, domain logic and APIs | 3 | 55d | 2027-12-09 | 2028-02-23 | 418 | BE | 202h
421 | Workflows (BPMN) and rules (DMN) configuration | 3 | 40d | 2027-12-31 | 2028-02-24 | 418 | BE | 101h
422 | Staff console screens | 3 | 53d | 2027-12-22 | 2028-03-03 | 419 | FE | 175h
423 | Field app tasks (offline) | 3 | 40d | 2028-01-10 | 2028-03-03 | 419 | MOB | 83h
424 | GIS layers, map views and spatial checks | 3 | 46d | 2027-12-22 | 2028-02-23 | 418 | GIS | 74h
425 | Module interfaces (12 I-xx links): events and APIs | 3 | 37d | 2028-01-19 | 2028-03-09 | 420 | BE | 166h
426 | Reports, dashboards, notices and templates (all active languages) | 3 | 26d | 2028-02-07 | 2028-03-13 | 420 | BE | 74h
427 | Data migration: asset and lease registers | 3 | 59d | 2027-12-31 | 2028-03-22 | 418 | DATA | 101h
428 | System integration testing | 3 | 21d | 2028-02-29 | 2028-03-28 | 420,422 | QA | 138h
429 | Defect fixing and regression | 3 | 26d | 2028-03-06 | 2028-04-10 | 428 | BE | 120h
430 | UAT support with GWMC department | 3 | 13d | 2028-03-29 | 2028-04-14 | 428 | BA | 74h
431 | Training material and department training | 3 | 13d | 2028-04-03 | 2028-04-19 | 430 | TRN | 55h
432 | Module 16: Legal Case Management | 2 | 119d | 2027-11-05 | 2028-04-19
433 | Process validation workshops and to-be sign-off | 3 | 16d | 2027-11-05 | 2027-11-26 | 394 | BA | 92h
434 | LLD, data model and API/event contracts | 3 | 16d | 2027-11-22 | 2027-12-13 | 433 | ARC | 74h
435 | UX wireframes and UI design | 3 | 16d | 2027-11-22 | 2027-12-13 | 433 | FE | 64h
436 | Database schema, domain logic and APIs | 3 | 55d | 2027-12-09 | 2028-02-23 | 434 | BE | 239h
437 | Workflows (BPMN) and rules (DMN) configuration | 3 | 40d | 2027-12-31 | 2028-02-24 | 434 | BE | 101h
438 | Staff console screens | 3 | 53d | 2027-12-22 | 2028-03-03 | 435 | FE | 193h
439 | Module interfaces (4 I-xx links): events and APIs | 3 | 37d | 2028-01-19 | 2028-03-09 | 436 | BE | 55h
440 | External system adapters (1) | 3 | 44d | 2028-01-10 | 2028-03-09 | 434 | BE | 55h
441 | Reports, dashboards, notices and templates (all active languages) | 3 | 26d | 2028-02-07 | 2028-03-13 | 436 | BE | 74h
442 | Data migration: pending court cases | 3 | 59d | 2027-12-31 | 2028-03-22 | 434 | DATA | 110h
443 | System integration testing | 3 | 21d | 2028-02-29 | 2028-03-28 | 436,438 | QA | 156h
444 | Defect fixing and regression | 3 | 26d | 2028-03-06 | 2028-04-10 | 443 | BE | 129h
445 | UAT support with GWMC department | 3 | 13d | 2028-03-29 | 2028-04-14 | 443 | BA | 74h
446 | Training material and department training | 3 | 13d | 2028-04-03 | 2028-04-19 | 445 | TRN | 64h
447 | Module 19: Government Schemes Management | 2 | 119d | 2027-11-05 | 2028-04-19
448 | Process validation workshops and to-be sign-off | 3 | 16d | 2027-11-05 | 2027-11-26 | 394 | BA | 74h
449 | LLD, data model and API/event contracts | 3 | 16d | 2027-11-22 | 2027-12-13 | 448 | ARC | 74h
450 | UX wireframes and UI design | 3 | 16d | 2027-11-22 | 2027-12-13 | 448 | FE | 46h
451 | Database schema, domain logic and APIs | 3 | 55d | 2027-12-09 | 2028-02-23 | 449 | BE | 193h
452 | Workflows (BPMN) and rules (DMN) configuration | 3 | 40d | 2027-12-31 | 2028-02-24 | 449 | BE | 92h
453 | Staff console screens | 3 | 53d | 2027-12-22 | 2028-03-03 | 450 | FE | 166h
454 | Citizen portal and app services | 3 | 40d | 2028-01-10 | 2028-03-03 | 450 | FE | 110h
455 | Field app tasks (offline) | 3 | 40d | 2028-01-10 | 2028-03-03 | 450 | MOB | 74h
456 | Module interfaces (5 I-xx links): events and APIs | 3 | 37d | 2028-01-19 | 2028-03-09 | 451 | BE | 74h
457 | External system adapters (2) | 3 | 44d | 2028-01-10 | 2028-03-09 | 449 | BE | 110h
458 | Reports, dashboards, notices and templates (all active languages) | 3 | 26d | 2028-02-07 | 2028-03-13 | 451 | BE | 64h
459 | Data migration: existing beneficiaries | 3 | 59d | 2027-12-31 | 2028-03-22 | 449 | DATA | 83h
460 | System integration testing | 3 | 21d | 2028-02-29 | 2028-03-28 | 451,453 | QA | 129h
461 | Defect fixing and regression | 3 | 26d | 2028-03-06 | 2028-04-10 | 460 | BE | 120h
462 | UAT support with GWMC department | 3 | 13d | 2028-03-29 | 2028-04-14 | 460 | BA | 74h
463 | Training material and department training | 3 | 13d | 2028-04-03 | 2028-04-19 | 462 | TRN | 46h
464 | Phase 4 release, testing and go-live | 2 | 27d | 2028-03-17 | 2028-04-24
465 | End-to-end integration testing (SRS E2E scenarios) | 3 | 13d | 2028-03-17 | 2028-04-04 | 412,428,443,460 | QA | 276h
466 | Performance and load testing (NFR-001/002) | 3 | 9d | 2028-03-23 | 2028-04-04 |  | QA | 147h
467 | Security audit by CERT-In empanelled auditor and fixes | 3 | 13d | 2028-03-29 | 2028-04-14 |  | QA | 193h
468 | Training of trainers and end-user training programme | 3 | 13d | 2028-04-05 | 2028-04-21 |  | TRN | 184h
469 | Migration dress rehearsal and cut-over plan | 3 | 8d | 2028-04-10 | 2028-04-19 |  | DATA | 120h
470 | Production deployment and cut-over | 3 | 3d | 2028-04-20 | 2028-04-24 | 467,469,414,430,445,462 | DEV | 147h
471 | M4: Phase 4 go-live | 2 | 0d | 2028-04-24 | 2028-04-24 | 470
472 | Hypercare and stabilisation (4 weeks) | 3 | 20d | 2028-04-24 | 2028-05-19 | 471 | BE | 267h
473 | Phase 4 acceptance and sign-off | 2 | 0d | 2028-05-22 | 2028-05-22 | 472
474 | Phase 4 build mid-point (next phase design may start) | 2 | 0d | 2028-02-07 | 2028-02-07
475 | Programme close | 1 | 1d | 2028-07-10 | 2028-07-10
476 | Programme completion and handover to operations | 2 | 0d | 2028-07-10 | 2028-07-10 | 473

## Risks
ID | Risk | Impact | Likelihood | Owner | Mitigation | Linked tasks
R1 | State Data Centre slot or network approvals delayed | High | Medium | PM / GWMC IT | Request in week 1; start on cloud test environment; keep Helm charts identical | Phase 0 SDC request; production cluster
R2 | CDMA access and legacy property data quality | High | High | Data lead / GWMC Revenue | Early data assessment, integrate mode first, reconciliation reports, dress rehearsals | Module 1 migration; Phase 1 cut-over
R3 | Department availability for workshops and UAT | High | Medium | PM / Commissioner office | Named nodal officers per department; fixed calendar agreed at kick-off | D1 and T3 subtasks
R4 | External system sandboxes (TG-bPASS, fire, IGRS, PFMS, DigiLocker) not available on time | Medium | High | Architect | Stub adapters behind the same contracts; escalate through GWMC | B8 adapter subtasks
R5 | Security audit findings delay go-live | High | Medium | Architect / QA lead | Secure SDLC scans every sprint; pre-audit internal VAPT | Phase VAPT tasks
R6 | Scope growth from new department requests | Medium | High | PM | Change control process with impact assessment and steering approval | Change control
R7 | Hiring and ramp-up of GIS and mobile skills | Medium | Medium | Hake management | Use Resource Loading to hire 6 to 8 weeks ahead; cross-train | Resource Loading
R8 | Language coverage and translation quality for notices | Medium | Medium | BA lead | Bhashini plus human review for statutory notices; Telugu first | B9 subtasks